## Slide 1
August 2015
Capital and Risk
Transformation
Meeting with the Federal Reserve Bank –
Risk Transformation
Notes: 1

## Slide 2: Agenda for today’s meeting – Risk Transformation
  Workstream overview and primary goals
  Project plan summary
  Deep-dives on key progress
  Other??
Update after content has been finalized

## Slide 3
Risk CART Goals and Objectives:
To improve the fundamentals of risk management and address the root causes of foundational deficiencies in risk management capabilities, our top priorities are to:
• Develop a risk appetite statement for SHUSA that will inform and constrain risk-taking across the
enterprise, and will ultimately be cascaded throughout the organization and embedded in key processes and
business decision-making
• Compile a register of material risks to inform the Board and senior management, and for use in critical
processes including capital planning and stress-testing
• Perform a talent assessment that will lead to a stronger, more capable risk staff
• Articulate three lines of defense principles to serve as a guide for implementing the target operating model
for risk management.
Current State
Target State
Sub-workstream
  Risk Governance and Organization
  Risk Appetite
2
1
  Weak Board and senior management oversight
  Unclear roles and responsibilities across the three lines of defense
  Duplication of functions and misaligned staff capabilities with the skills
  Fragmented risk tolerance framework
  Not properly calibrated to the risk profile of the business
  Framework not cascaded consistently across subsidiaries and business units
  Not embedded in the organization’s processes
  Consequences of breaches are neither articulated nor enforced
  Strengthened oversight through training and effective committee
  Redesigned and implemented Operating Model in alignment with the three lines of defense governance principles
  Solid talent management mechanism
  Consistently cascaded throughout the organization
  Risk Appetite embedded in key processes and business decision-making across the institution, including strategic/capital planning and stress testing, new product approval, and outsourcing decisions
  Ultimate guideline for decision-making and risk-reward optimization across the enterprise
Notes: 3
MVA-040502-303-2011xxxx-VMS3-k
3
MVA-040504-303-2011xxxx-VMS3-k
3

## Slide 4
Current State
Target State
Sub-workstream
  Risk ID & Measurement
3
  Risk Management Processes
4
  Risk identification processes do not match up to those of our U.S. peers or to supervisory expectations
  Limited progress implementing the three lines of defense model
  Lack of enhanced governance and oversight across the BHC
  A concise and comprehensive compendium of the organization’s material risks for senior management and the Board, and for use in downstream applications, such as capital planning
  Enhanced material risk identification process in time for use in scenario generation
  Enhanced foundational risk identification processes and data sources aligned with established multi-year objectives
  Consistent management of individual risk types yet flexible enough to meet the needs of specific businesses
  Risk Monitoring / Risk Reporting
5
  Enhanced ability to monitor risks and report on them in an action oriented and timely manner with improved data quality
  Inconsistent management of individual risk types across the enterprise
  Unidentified approach, process, and tools-based weaknesses within key risk types in each legal entity and business unit
  Lack governance and oversight across the BHC
  Insufficient data quality and technology applications
  Distinct risk reporting formats and content across legal entities caused by siloed business units
Risk CART Goals and Objectives (Cont’d):
Notes: 4
MVA-040502-303-2011xxxx-VMS3-k
4
MVA-040504-303-2011xxxx-VMS3-k
4

## Slide 5: Risk Transformation - Summary
Key deliverables
Key dependencies
Due by
Sub-workstreams in Risk Transformation
Summary of FRB feedback
Potential execution risks
New governance guidelines did not provide the needed clarity on how the company should conduct its affairs
The board reporting framework is inadequate; materials presented at board and senior management committees are unclear or inconsistent
Insufficient definition of a consolidated risk appetite statement and limit structure including level and types of risk the holding company is willing to assume from subsidiaries
Risk identification process does not identify nor appropriately account for all risks when assessing capital needs
Risk governance and organization: organizational structure of risk management to enforce the risk appetite statement, and oversight by the SHUSA Boards
Risk appetite: establish and communicate Board approved risk appetite
Risk ID & measurement: tools and processes to quantify the enterprise’s risks
Risk management processes: measurement and management of the enterprise’s risks and application to strategic business decisions
Risk monitoring / Risk reporting: summarize enterprise’s key risks for internal and external stakeholders
    Data availability and data quality across enterprise
    Management of dependencies and related activities spanning multiple Risk workstreams (e.g. RAS, target operating model, reporting framework and templates)
    Execution risk due to effective transfer of knowledge and capabilities from external resources / consultants
    Staffing and skills requirements of the Target Operating Model will be determined for all three lines of defense during the implementation planning process; significant gaps may affect deliverables in years 2-3
    Model Development: Development of commercial ratings models
    Model Risk Management: Validation of commercial ratings models
    Finance:
      Liquidity Data Mart and tools to support analytics process by second line of defense liquidity risk management
      Implementation of the TOM across IHC entities to support LRM Framework implementation including stress testing scenarios and LST calculations (stressed inflows/outflows >90 days, non-maturity deposits)
    Data & IT:
      IT development to support Commercial Risk Rating implementation / embedding in relevant processes
      IT development for RAS, Risk ID and Risk reporting (pending planned definition of business/data requirements)
    First Line: Input to Material Risk Program (business line / segment Material Risk Inventories)
11/30/15
Develop SHUSA, SBNA, and SCUSA RAS, and obtain approvals
01/12/16
Initial embedding of top-level RAS in material SHUSA processes and plan further embedding across the enterprise
01/15/16
Develop and execute Material Risk Program
11/30/15
    Draft SHUSA’s Governance and Oversight Framework Document
09/30/16
Define multiyear plan to achieve a sound target state risk culture
    Rollout Commercial Risk Ratings
07/29/16
10/02/15
Implement near-term changes to Risk org / reporting lines
12/11/15
    Risk Operating Model design and implementation planning
05/27/16
Review foundational Risk ID processes / build multiyear objectives
01/08/16
Enhanced top of the house risk policies and 3 LOD articulation
09/07/15
    Define target exec. mgmt. risk reporting landscape
07/31/15
    Implement routine Risk-Business reviews with reports
Key deliverables section updated to current
Duplicative to information on slide 3, may delete

## Slide 6: Risk Transformation project plan(1/5) – Risk Gov. & Org. Current
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  11/30/15
  07/31/15
  8/15/15
  09/30/15
  09/30/15
  09/30/15
  10/31/15
  11/30/15
  01/31/16
  01/15/16
  01/31/16
Ongoing
07/31/15
01/08/16
05/02/17
  10/02/15
  07/17/15
  12/11/15
  12/11/15
  08/12/16
  10/14/16
  Ongoing
  04/01/16
  09/30/16
  12/18/15
  01/02/17
  04/04/17
  07/15/15
  07/15/15
  07/15/15
  08/01/15
  08/01/15
  07/15/15
  10/01/15
  11/01/15
  12/01/15
  12/01/15
  01/3/16
02/01/16
07/13/15
10/05/15
06/22/15
  08/03/15
  06/22/15
  07/13/15
  07/13/15
  12/14/15
  08/15/16
  01/25/16
  02/01/16
  07/01/16
  06/15/16
  04/01/16
  07/01/16
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn/ Briongos
  Gunn/ Briongos
  Gunn/ Briongos
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  1 Implementation finish date may be refined during the design phase
  Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize
    Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company
    Define target state committee structure including Board and Management committees
    Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries
    Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines
    Develop policy framework, establish overall policies including guidelines for approval of policies
    Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries
    Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans
    Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting
    Establish comprehensive implementation plans to address these gaps over a multi-year period
Execute against multi-year plan for Risk Transformation
Implement routine Risk-Business reviews with standardized materials and reports
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)
Design Operating Model across risk types aligned with principles of 3 LOD, develop rollout plans and implement
      Identify and implement near term changes to the risk organization and reporting lines across SHUSA
      Review of existing 1st LoD structure and capabilities
      Design detailed operating model and implementation plans for all risk types ex. Op risk
      Design detailed operating model and implementation plans for Op Risk
      Implement the redesigned Operating Model for all the risks
      Post Implementation Review
  Rollout communication and training for organizational changes related to 3 LOD
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
  Define multiyear plan to achieve a sound target state risk culture
  Assess existing Risk Management Performance Scorecards and identify gaps
  Rollout systematic performance assessments and risk-based compensation structures
  Diagnose retention challenge and design recruitment and retention mechanisms
Status
  33%
  10%
  5%
  33%
  95%
  24%
  18%
The finish date technically is supposed to be 10/14/16. The finish date in Project sent to Fed is 05/02/17 because Project defaults manual schedule so doesn't reflect new finish date automatically.

## Slide 7: Risk Transformation project plan(2/5) – Risk Appetite Current
  Deliverables
    Milestones under the deliverable
    Completed
Deliverables / milestones
Finish
Sub-workstream
Start
Risk Appetite Statement (RAS)
  Develop SHUSA (top-level), SBNA, and SCUSA RAS, and obtain approvals
    Design SHUSA (top-level), SBNA, and SCUSA RAS
    Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences)
    Articulate SHUSA (top-level), SBNA, and SCUSA RAS approval process, and train the Board on the approach and their role
    Secure SHUSA (top-level), SBNA, and SCUSA RAS Board Approval
Communicate Board-approved SHUSA (top-level), SBNA, and SCUSA RAS to enterprise
Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals
    NY RAS design and approval
    Puerto Rico RAS design and approval
    Miami RAS design and approval
Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise
    Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links
    Initiate implementation of RAS in all material processes
    Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement
    Cascade the embedding of the risk appetite statement for key processes across the organization
    Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process
    Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics
06/08/15
  06/08/15
  07/06/15
  08/31/15
  11/23/15
  12/01/15
  02/01/16
  02/01/16
  02/01/16
  02/01/16
  11/02/15
  11/02/15
  11/30/15
  01/01/16
  01/01/16
  04/01/16
  10/03/16
11/30/15
  09/11/15
  09/15/15
  11/30/15
  11/30/15
  02/24/16
  06/30/16
  06/30/16
  06/30/16
  06/30/16
  01/12/16
  11/27/15
  01/12/16
  06/30/16
  06/30/16
  09/30/16
  06/30/17
  Smith/ Parrish
  Smith/ Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
Owner
Status
66%
  87%
  59%
  16%

## Slide 8: Risk Transformation project plan(3/5) – Risk ID & Measurement Current
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk ID & Measurement
  Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives
    Assess foundational Risk ID processes and ensure complete foundational risk inventory is in place
    Review each foundational Risk ID process, identify deficiencies in data, technology and processes, and use gap analyses to determine how to optimize
    Develop remediation plans for foundational Risk ID processes
  01/18/16
  01/18/16
  02/29/16
  04/27/16
  Smith
  05/27/16
  02/26/16
  05/13/16
  05/27/16
  Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.)
  Updated SHUSA Risk taxonomy for Material Risk Program
  Updated material risk inventory template and guidance for Material Risk Program
  Develop training materials, policies and procedures based on updated Material Risk Program process
  05/30/16
  11/30/15
  01/18/16
  02/29/16
  Smith
  Allaire
  Allaire
  Allaire
  05/31/171
  01/15/16
  02/26/16
  06/17/16
  Deliverables
    Milestones under the deliverable
    Completed
    Create risk inventory for the SHUSA, hold workshops for aggregation
    Preparation for Aggregation to create SHUSA Material Risk Inventory
    Hold SHUSA Aggregation Workshops (include 2nd LOD challenge)
    Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge)
    Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge)
    Draft Risk ID and Assessment Policy and obtain approvals
    Establish clear linkage of MRP outputs to capital planning scenario design process
  10/05/15
  10/05/15
  10/12/15
  10/26/15
  11/09/15
  10/26/15
  10/12/15
  01/15/16
  10/19/15
  10/26/15
  11/09/15
  12/04/15
  01/15/16
  12/04/15
  1 Implementation finish date may be refined during the design phase
  2 Refer to Model Development and Model Risk Management workstreams for relevant dates on development and validation
  01/15/16
  05/01/15
  10/02/15
  07/31/15
  10/02/15
  02/02/15
  02/02/15
  05/28/15
  05/28/15
  08/03/15
    Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology)
    Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance)
    Create risk inventory for the Subsidiaries / Business Entities and hold workshops for aggregation
    Compile Business Line / Segment Material Risk Inventory
    Hold Subsidiary / Business Entity Aggregation Workshops (include 2nd LOD challenge) and Governance (Material Risk Inventory Reviews / Approvals)
  Allaire
Status
  76%
  87%
  50%

## Slide 9: Risk Transformation project plan(4/5) – Risk Management Processes Current
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk Management Processes
  Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements
  Design Liquidity Stress Test Challenge Process Framework and get approvals
  Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA
  Rollout Commercial Risk Ratings
    Establish governance and oversight on commercial risk ratings governance
    Redesign CRE rating models
      CRE model development and validation (refer to Model Dev. / Model Risk workstreams1)
      CRE UAT / pilot testing
      CRE end-user training
      CRE initial model implementation / rollout
  11/30/15
  12/31/15
  03/31/16
  07/29/16
  07/31/15
  05/27/16
  11/18/15
  04/01/16
  05/27/16
  05/06/16
  11/03/14
  06/01/15
  02/01/16
  06/01/15
  06/01/15
  06/29/15
  06/29/15
  01/04/16
  01/18/16
  02/29/16
  Aya
  Aya / Lasso
  Hennessy / Cuervo
  Spector
  Deliverables
    Milestones under the deliverable
    Completed
  1 Refer to Model Development and Model Risk Management workstreams for relevant dates on development and validation
    Redesign C&I rating models
      C&I model development and validation (refer to Model Dev. / Model Risk workstreams1)
      C&I UAT / pilot testing
      C&I end-user training
      C&I initial model implementation / rollout
    Create requirement definitions for long-term technology solution for CRE and C&I model implementation
  Conduct gap analyses across risk types focusing on methodology, tools, processes, and expectations as defined by the operating model and benchmark to industry practice
  Create remediation plans to address gaps and initiate remediation actions
  07/29/16
  01/14/16
  06/03/16
  07/29/16
  07/01/16
  04/15/16
  09/30/16
  12/02/16
  06/22/15
  06/22/15
  03/21/16
  03/21/16
  06/06/16
  09/01/15
  07/01/16
  08/03/16
  Hennessy / Smith
  Hennessy / Smith
Status
  44%
  37%
  22%
  13%
  52%
  5%
  21%

## Slide 10: Risk Transformation project plan(5/5) – Risk Monitoring/Reporting Current
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk Monitoring / Risk Reporting
  Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols
    Document detailed business and data requirements for SHUSA Monthly Risk Report and deliver to T&O for BCBS 239 compliance
  Define target exec. mgmt. risk reporting landscape and scope of remediation (linked to committee structure)
  Identify risk aggregation needs and cultivate dedicated resources to manage reporting
  Develop and implement Wave 1 of exec. mgmt. reporting enhancements
    Develop template reports for Wave 1 and socialize
    Roll-out of Wave 1 reports (similar process for all waves)
      Review business/data requirements for interim and target state of Wave 1 reports and update as needed
      Identify and document data gaps and develop remediation plans
      Pilot reports using available data (manual where necessary)
      Collect feedback from key stakeholders and refine reports
      Implement refined reports in-production
  Develop and implement Wave 2 of exec. mgmt. reporting enhancements
    Development of template reports and socialization of Wave 2 (based on materiality)
    Roll-out of Wave 2 reports (similar process as Wave 1)
  Develop and implement Wave 3 of exec. mgmt. reporting enhancements
    Development of template reports and socialization of Wave 3 (Remaining Entities)
    Roll- out of Wave 3 reports (similar process as Wave 1)
  Execute on Remediation Plans and Roll-out Enhanced Reports
  Develop and launch additional waves of reporting enhancements as needed
  Refine data requirements/resources to enhance quality of reports
  Develop quality assurance plans and controls for newly enhanced reports
  Assess resource needs and implement additional refinements to monitoring requirements
  08/17/15
  08/17/15
  09/07/15
  01/29/16
  11/09/15
  09/25/15
  11/09/15
  10/23/15
  11/09/15
  10/09/15
  11/06/15
  11/09/15
  12/28/15
  10/30/15
  12/28/15
  04/01/16
  01/29/16
  04/01/16
  01/02/17
  09/30/16
  09/30/16
  09/30/16
  03/31/17
  06/15/15
  06/15/15
  07/27/15
  08/31/15
  08/31/15
  08/31/15
  09/28/15
  09/28/15
  09/28/15
  09/28/15
  10/26/15
  11/06/15
  10/05/15
  10/05/15
  11/02/15
  12/28/15
  12/28/15
  02/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  04/01/16
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Coutinho
  Deliverables
    Milestones under the deliverable
    Completed
Status
  99%
  3%
  9%

## Slide 11: The Risk Transformation workstream has been making early progress and is working towards a number of near-term planned deliverables
Highlighted achievements to-date
Focus on deliverables next 6 months
Sub-workstream
  Risk Governance and Oversight
  Risk Appetite
2
  Risk ID & Measurement
3
1
  Risk Management Processes
4
  Educated Board and senior committees on respective responsibilities regarding RAS and RAS metrics
  Material risks for enterprise identified and documented
  Qualitative components of RAS complete
  Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance) completed
  Significant progress in creating risk inventory for the Subsidiaries / Business Entities and hold workshops for aggregation
  Complete “Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize”
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans
  Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)
  Complete development of and obtain Board approval for SHUSA (top-level), SBNA, and SCUSA RAS
  Test Strategic Plan against RAS
  Initiate embedding of RAS in material SHUSA processes; plan for embedding across enterprise
  Risk Monitoring / Risk Reporting
5
  Assessed current risk reporting landscape; “quick-win” enhancements made to priority reports and reporting protocols
  Target risk reporting landscape defined
  Develop and implement Waves 1 and 2 of executive management reporting enhancements
  Identify risk aggregation needs; cultivate dedicated resources to manage reporting
  Credit Risk Rating governance implemented
  CRE Model Developed
  Liquidity Stress Test Challenge Process Framework Prepared
  Hire Head of Credit Risk Rating
  CRE and C&I rating models redesigned and validated
  Liquidity risk management (“LRM”) gaps analyzed and remediated IHC requirements
  Defined target state committee structure including Board and Management committees
  Implemented routine Risk-Business reviews with standardized materials and reports
  Progress in “Design Operating Model across risk types aligned with principles of 3 LOD, develop rollout plans and implement”
  Create risk inventory for the SHUSA, hold workshops for aggregation
  Update SHUSA Risk taxonomy for Material Risk Program
  Update material risk inventory template and guidance for Material Risk Program

## Slide 12: Deep-dives in Risk ID and Measurement -Principles and Target State
BAU top risks refresh
Activity: Discussion during senior management meeting
Purpose: Bring risks to attention of management on a regular basis; refresh of key “top-of-mind” risks that may not have been identified, fully addressed, or changed
Target State
At Least Quarterly
+
Material Risk Program: Material Risk Inventories,
1-on-1 interviews and Synthesis Meeting
Annual
BAU bottom-up material risks refresh
Activity: Update of material risk inventory at Business Segment level to reflect latest information (Incidences, issues, findings etc.)
Purpose: Identify new risks, increased materiality of risk types, or issues that are not being actively controlled / need remediation
Principles
Transparency: Simple and clearly defined approach and process
Accuracy: Continuous improvement of foundational risk data inputs
Robustness: Clearly defined and robust process aligned with BAU activities
Effectiveness: Integration of risk identification into day-to-day risk management activities
Timeliness: Regular, sustainable BAU refresh of risk inventories
Ownership: Clear business ownership for risk identification

## Slide 13: Deep-dives in Risk ID and Measurement Improvements compared to 2014 and plan to reach the Target State
  Risks collected through structured templates,
  Explicit documentation of relevant Foundational Inputs and important business considerations (e.g., new products, off-balance sheet risks)
  Decision to implement an enterprise GRC tool
  1st LoD3 staff responsible for initial Bottom-Up Risk ID
  Integration of Foundational Inputs into Material Risk Program where available
  Senior Business leader involvement in Business Line Inventory
  Initial development of Risk Appetite Statement and ORM4 policies
  Commenced Issue Mgmt. pilot
  2015
Material Risk Program
Risk Identification Process
  Clear requirements from Capital Planning for Scenario Analysis
  Board Reporting on Top Risks envisioned
  Clear guidance and training on Risk Capture, Materiality, Assessment, Aggregation & Enrichment, Roles & Responsibilities
  Enhanced governance process around Material Risks
  Structured approach to Bottom-Up execution
  Top-down Risk ID interviews with Senior Management
Foundational Inputs
Centralized Repositories
Risk Inventories
Risk Management
  Phased implementation of Enterprise-wide GRC System
  Link of information from transparent centralized repositories to Material Risk Inventories
  Rollout of Issue Management and Loss Data Capture platform for tracking and resolution of issues
  Further refinement and integration of additional Foundational Inputs (e.g. loss data and issue mgmt.)
  Implementation plan for RCSA across the organization
  Build out of 1st LoD capacity for risk and control activities
  Implementation of revised New Product Assessment
  Implementation of ORM polices related to data / info capture
  2016
  Integration of Risk ID and Material Risk Program into Business-as-usual Risk management
  Development of remediation plan for risks and issues identified in 2015
  Implementation of Risk ID and Material Risk Program policies, standards, and procedures
  Development of sustainable approach for Material Risk Program refreshes of top-down risk ID, bottom-up inventories, and review / challenge process with Executives
Phased rollout of RCSA in line with implementation of redesigned Operating Model
Rollout of IRM5, Business Continuity Mgmt. and Vendor Risk Mgmt. tools
  2017
  Execute remediation plans for Risks and Issues identified
  Implementation of software tool for Material Risk Inventories
  No GRC2 system
  Non-repeatable / non- transparent capture of Risks
No RCSA1
No clear incorporation of Foundational Inputs into Material Risk synthesis
  2014
  No linkage to Capital Planning, Board Reporting, or Risk Appetite
  No Top-Down process with demonstrable review / challenge
  Deficient Bottom-Up process
  1) Risk and Control Self-Assessment 2)Governance, Risk, and Compliance 3) Line of Defense 4) Operational Risk Management 5) Information Risk Management

## Slide 14: Deep-dives in Governance-Principles and Target State Governance work stream has defined key principles in order to build an effective Committee structure
Target State
Principles
  Simple and balanced: Structure should balance simplicity (fewer committees) and the workload (more committees)
  Delineated: Scope of responsibilities should be well-defined and avoid overlap between committees
  Delegating: Committees should delegate specific decisions to their sub-committees and ensure that committees’ agendas remain manageable
Accountable & influential: Committees should be advisors or decision-makers instructing management to enforce decisions
  Board Level committees: assist the Board in its oversight and discharge of responsibilities.
  Management Level-1 committees: mirroring the Board committee structure, they operate in a strategic manner to facilitate the execution of responsibilities of senior executives
  Management Level-2 committees: advisors and decision-makers for the Level 1 management committees they report to, they have clear delegated authority and further subject matter expertise.

## Slide 15: Deep-dives in Governance-Principles and Target State New Governance structure will be finalized through the Governance framework and the updated committee charters before end of year
  2015 (2nd Half)
Governance Structure | Reviewed current committee structure and identified challenges Defined principles for structure revisions Drafted committee structure, socialized and refined Defined committees high-level roles and responsibilities Approve new committee structure (pending) | Subsidiaries adopt SHUSA’s Governance structure and adjust where applicable
Committees Charters | Mapped committees key responsibilities to new committee structure Drafted committee charters, socialized and refined (on-going) Approve new committee charters (pending) | Subsidiary committee charters finalized and approved
Governance Implementation | SHUSA’s committees start meeting under their new charter & membership (Q4) | New committee structure embedded into SHUSA’s processes and procedures Subsidiaries committees start meeting under their new charter & membership
  2016 (1st Half)
Key: Green = task completed

## Slide 16: Risk Appetite Statement
Risk Transformation
Placeholder: Update pending to Tue.

## Slide 17: Appendix

## Slide 18: Change Tracker Summary
Sub-workstream | Change Name | Requested Change | Impact of not engaging in the Change | Affected Milestones/Deliverables
Risk Governance and Organization | Risk Culture - delay in execution | Push out the dates for execution of the following deliverable and subordinate tasks: "Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment" | Risk survey data will have reduced value for assessing current state and informing the risk culture roadmap; leadership responsible for setting the "Tone from the Top" may not be fully settled in the organization; potential for employee "survey fatigue" | (D) "Articulate desired risk culture by setting the ‘Tone from the Top’ and conducting a risk culture assessment"
 | Target Operating Model – modified execution methodology and timeline | Adjusted start date of "Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)" Adjusted execution methodology of "Design Operating Model across all risk types aligned with principles of 3 LOD, develop rollout plans and implement" by combining risk types Include Op Risk into project scope | Not implementing the change implies a longer and complicated schedule | (D) “Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)” (D) Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement

## Slide 19: Change Tracker Summary
Sub-workstream | Change Name | Requested Change | Impact of not engaging in the Change | Affected Milestones/Deliverables
Risk Appetite Statement | Change in development process | Change in approach to Risk Appetite Statement development for SHUSA, SBNA & SCUSA. Instead of original plan to create SHUSA RAS first and cascade to SBNA and SCUSA, all three RAS will be developed in parallel (Board approval of all three now targeted by 11/30/15, previously approval for all three would have been by 12/31/15). | Not implementing the change implies a longer comparative timeline for completion and delivery of the SBNA and SCUSA RASs and a more complex project plan inherent to the cascading of the SHUSA RAS to SBNA and SCUSA | (D) Design SHUSA (top-level), SBNA, and SCUSA RAS Various other deliverables/milestones within RAS sub-workstream (e.g. Define approach for cascading SHUSA-level RAS to subsidiaries and below – no longer relevant)
Risk Management | Name Changes | Changing the title of Deliverable tasks (WBS 3.3 & 3.4) to more accurately reflect their contents | The tasks will be inaccurately named in terms of what is actually scheduled to be done in this specific section | (D) Redesign C&I rating model and validation (Previously: Rollout C&I rating model and validation) (D) Redesign CRE rating model and validation (Previously: Rollout CRE rating model and validation)

## Slide 20: Risk Transformation project plan – Risk Gov. & Org. Original
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  11/30/15
  07/31/15
  8/15/15
  09/30/15
  09/30/15
  09/30/15
  10/31/15
  11/30/15
  01/31/16
  01/15/16
  01/31/16
Ongoing
07/31/15
01/08/16
04/01/16
  10/02/15
  10/02/15
  11/06/15
  10/02/15
  11/06/15
  11/09/161
  01/22/16
  01/25/171
  04/01/16
  04/04/171
  Ongoing
  07/15/15
  07/15/15
  07/15/15
  08/01/15
  08/01/15
  07/15/15
  10/01/15
  11/01/15
  12/01/15
  12/01/15
  01/3/16
02/01/16
07/13/15
07/13/15
08/03/15
  08/03/15
  08/03/15
  08/31/15
  08/31/15
  10/05/15
  11/09/15
  11/16/15
  01/25/16
  02/01/16
  04/04/16
  01/25/16
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  1 Implementation finish date may be refined during the design phase
  Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize
    Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company
    Define target state committee structure including Board and Management committees
    Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries
    Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines
    Develop policy framework, establish overall policies including guidelines for approval of policies
    Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries
    Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans
    Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting
    Establish comprehensive implementation plans to address these gaps over a multi-year period
Execute against multi-year plan for Risk Transformation
Implement routine Risk-Business reviews with standardized materials and reports
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
    Identify and implement near term changes to the risk organization and reporting lines across SHUSA
    Determine the prioritization of detailed operating model design and rollout by risk type / function
    Design detailed operating model and implementation plans for Risk Type / Function A & B (Most likely Credit, ERM + RAS + Strategic)
      Define detailed organizational structure and assess talent needs including target headcounts and skill sets
      Develop rollout plan
    Implement the redesigned Operating Model for Risk Type / Function A & B
    Design detailed operating model and implementation plans for Risk Type / Function C & D (Most likely Market & Liquidity, Compliance)
    Implement the redesigned Operating Model for Risk Type / Function C & D
    Design detailed operating model and implementation plans for Risk Type / Function E & F (Most likely Risk Management Information, Capital Risk)
    Implement the redesigned Operating Model for Risk Type / Function E & F
  Rollout communication and training for organizational changes related to 3 LOD

## Slide 21: Risk Transformation project plan – Risk Gov. & Org. Original
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  10/02/15 09/30/16
  12/18/15
  01/02/17
  04/04/17
  08/03/15
  07/01/16
  06/15/16
  04/01/16
  07/01/16
  Gunn
  Gunn
  Gunn/ Briongos
  Gunn/ Briongos
  Gunn/ Briongos
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
  Define multiyear plan to achieve a sound target state risk culture
  Assess existing Risk Management Performance Scorecards and identify gaps
  Rollout systematic performance assessments and risk-based compensation structures
  Diagnose retention challenge and design recruitment and retention mechanisms

## Slide 22: Risk Transformation project plan – Risk Gov. & Org. Change Index
Deliverables / milestones
Finish
Start
Change Made
  11/30/15
  07/31/15
  8/15/15
  09/30/15
  09/30/15
  09/30/15
  10/31/15
  11/30/15
  01/31/16
  01/15/16
  01/31/16
Ongoing
07/31/15
01/08/16
04/04/17
  10/02/15
  10/02/15
  11/06/15
  10/02/15
  11/06/15
  11/09/161
  01/22/16
  01/25/171
  04/01/16
  04/04/171
  Ongoing
  07/15/15
  07/15/15
  07/15/15
  08/01/15
  08/01/15
  07/15/15
  10/01/15
  11/01/15
  12/01/15
  12/01/15
  01/3/16
02/01/16
07/13/15
07/13/15
08/03/15
  08/03/15
  08/03/15
  08/31/15
  08/31/15
  10/05/15
  11/09/15
  11/16/15
  01/25/16
  02/01/16
  04/04/16
  01/25/16
  Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize
    Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company
    Define target state committee structure including Board and Management committees
    Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries
    Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines
    Develop policy framework, establish overall policies including guidelines for approval of policies
    Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries
    Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans
    Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting
    Establish comprehensive implementation plans to address these gaps over a multi-year period
  Execute against multi-year plan for Risk Transformation
  Implement routine Risk-Business reviews with standardized materials and reports
  Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)
  Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
    Identify and implement near term changes to the risk organization and reporting lines across SHUSA
    Determine the prioritization of detailed operating model design and rollout by risk type / function
    Design detailed operating model and implementation plans for Risk Type / Function A & B (Most likely Credit, ERM + RAS + Strategic)
      Define detailed organizational structure and assess talent needs including target headcounts and skill sets
      Develop rollout plan
    Implement the redesigned Operating Model for Risk Type / Function A & B
    Design detailed operating model and implementation plans for Risk Type / Function C & D (Most likely Market & Liquidity, Compliance)
    Implement the redesigned Operating Model for Risk Type / Function C & D
    Design detailed operating model and implementation plans for Risk Type / Function E & F (Most likely Risk Management Information, Capital Risk)
    Implement the redesigned Operating Model for Risk Type / Function E & F
  Rollout communication and training for organizational changes related to 3 LOD
  No change
    No change
    No change
    No change
    No change
    No change
    No change
    No change
  No change
    No change
    No change
  No change
  No change
  Date change; Start: 10/5/15
  Date change; Start: 06/22/15, Finish: 05/02/17
    Added “Review of existing 1st LoD structure and capabilities” 06/22/15-07/17/15
    Adjusted to “Design detailed operating model and implementation plans for all risk types ex. Op risk” 07/13/15-12/11/15
    Added “Design detailed operating model and implementation plans for Op Risk” to scope 07/13/15-12/11/15
    Adjusted to “Implement the redesigned Operating Model for all the tasks” 12/14/15-08/12/16
    Added “Post Implementation Review” 08/15/16-10/14/16
The finish date technically is supposed to be 10/14/16. The finish date in Project sent to Fed is 05/02/17 because Project defaults manual schedule so doesn't reflect new finish date automatically.

## Slide 23: Risk Transformation project plan – Risk Gov. & Org. Change Index
Deliverables / milestones
Finish
Start
Change Made
  10/02/15 09/30/16
  12/18/15
  01/02/17
  04/04/17
  08/03/15
  07/01/16
  06/15/16
  04/01/16
  07/01/16
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
  Define multiyear plan to achieve a sound target state risk culture
  Assess existing Risk Management Performance Scorecards and identify gaps
  Rollout systematic performance assessments and risk-based compensation structures
  Diagnose retention challenge and design recruitment and retention mechanisms
  Date change; Start: 02/01/16, Finish: 04/01/16
  No change
  No change
  No change
  No change

## Slide 24: Risk Transformation project plan – Risk Appetite Original
  Deliverables
    Milestones under the deliverable
    Completed
  Smith/ Parrish
  Smith/ Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
  Smith / Parrish
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
Risk Appetite Statement (RAS)
  Develop interim RAS for SBNA and SCUSA, and begin ongoing monitoring
  Develop SHUSA, SBNA, and SCUSA RAS, and obtain approvals
    Develop SHUSA-level RAS (top-down approach)
    Develop SBNA- and SCUSA-level RAS (bottom-up approach), ensuring alignment to SHUSA RAS
    Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences)
    Secure Board approval of SHUSA, SBNA, and SCUSA RAS
Communicate Board-approved SHUSA, SBNA, and SCUSA RAS to enterprise
Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals
    NY RAS design and approval
    Puerto Rico RAS design and approval
    Miami RAS design and approval
Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise
    Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links
    Initiate implementation of RAS in all material processes
    Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement
    Cascade the embedding of the risk appetite statement for key processes across the organization
    Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process
    Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics
06/08/15
06/08/15
  06/08/15
  06/08/15
  07/06/15
  08/31/15
  12/01/15
  02/01/16
  02/01/16
  02/01/16
  02/01/16
  11/02/15
  11/02/15
  11/30/15
  01/01/16
  01/01/16
  04/01/16
  10/03/16
09/30/15
12/31/15
  08/28/15
  11/20/15
  11/20/15
  12/31/15
  02/24/16
  06/30/16
  06/30/16
  06/30/16
  06/30/16
  01/12/16
  11/27/15
  01/12/16
  06/30/16
  06/30/16
  09/30/16
  06/30/17

## Slide 25: Risk Transformation project plan – Risk Appetite Change Index
Deliverables / milestones
Finish
Start
  1. Develop interim RAS for SBNA and SCUSA, and begin ongoing monitoring
  2. Develop SHUSA, SBNA, and SCUSA RAS, and obtain approvals
    Develop SHUSA-level RAS (top-down approach)
    Develop SBNA- and SCUSA-level RAS (bottom-up approach), ensuring alignment to SHUSA RAS
    Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences)
    Secure Board approval of SHUSA, SBNA, and SCUSA RAS
3. Communicate Board-approved SHUSA, SBNA, and SCUSA RAS to enterprise
4. Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals
    NY RAS design and approval
    Puerto Rico RAS design and approval
    Miami RAS design and approval
5. Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise
    Identify key processes (e.g. strategic planning, capital planning) and update process maps with explicit RAS links
    Initiate implementation of RAS in all material processes
    6. Continue to cascade the risk appetite statement for the remainder of subsidiaries and business units and ensure alignment with overall SHUSA risk appetite statement
    7. Cascade the embedding of the risk appetite statement for key processes across the organization
    8. Continue to communicate risk appetite statement throughout the enterprise, including training in the new escalation and remediation process
    9. Periodically enhance risk appetite statement based on the latest results of material risk identification and improved risk measurement across the enterprise; including incorporation of risk-based capital metrics
06/08/15
06/08/15
  06/08/15
  06/08/15
  07/06/15
  08/31/15
  12/01/15
  02/01/16
  02/01/16
  02/01/16
  02/01/16
  11/02/15
  11/02/15
  11/30/15
  01/01/16
  01/01/16
  04/01/16
  10/03/16
09/30/15
11/30/15
  08/28/15
  11/20/15
  11/20/15
  12/31/15
  02/24/16
  06/30/16
  06/30/16
  06/30/16
  06/30/16
  01/12/16
  11/27/15
  01/12/16
  06/30/16
  06/30/16
  09/30/16
  06/30/17
Change Made
  1. DELETED; SHUSA, SBNA, and SCUSA RAS development now synchronized
  2. Changed finish date to 11/30/15 due to RAS development and approval synchronization; Changed “SHUSA” to “SHUSA (top-level)”
    DELETED; due to synchronization of SHUSA, SBNA, and SCUSA RASs
    Changed to: “Design SHUSA (top-level), SBNA, and SCUSA RAS”; changed finish date to 9/11/15
    Finish date changed to 9/15/15 due to synchronization; intent is to have RAS ongoing process documentation available to accompany RAS drafts for Sept. 2015 Board review
    Finish date changed to 11/30/15 to reflect synchronization of SHUSA, SBNA, and SCUSA RAS development and approval; changed “SHUSA” to “SHUSA (top-level)
3. No change
4. No change
    No change
    No change
    No change
5. No change
    No change
    No change
    6. No change
    7. No change
    8. No change
    9. No change

## Slide 26: Risk Transformation project plan – Risk Management Original
Deliverables / milestones
Sub-workstream
Start
Owner
Finish
Risk Management Processes
  Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements
  Design Liquidity Stress Test Challenge Process Framework and get approvals
  Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA
  Rollout Commercial Risk Ratings
    Establish governance and oversight on commercial risk ratings governance
    Rollout redesigned CRE rating models
      CRE model development and validation (refer to Model Dev. / Model Risk workstreams2)
      CRE UAT / pilot testing
      CRE end-user training
      CRE initial model implementation / rollout
  11/30/15
  12/31/15
  03/31/16
  07/29/16
  07/31/15
  05/27/16
  11/18/15
  04/01/16
  05/27/16
  05/06/16
  11/03/14
  06/01/15
  02/01/16
  05/04/15
  06/01/15
  06/29/15
  06/29/15
  02/01/16
  02/01/16
  04/04/16
  Aya
  Aya / Lasso
  Hennessy / Cuervo
  Spector
  Deliverables
    Milestones under the deliverable
    Completed
  1 Implementation finish date may be refined during the design phase
  2 Refer to Model Development and Model Risk Management workstreams for relevant dates on development and validation
    Rollout redesigned C&I rating models
      C&I model development and validation (refer to Model Dev. / Model Risk workstreams1)
      C&I UAT / pilot testing
      C&I end-user training
      C&I initial model implementation / rollout
    Create requirement definitions for long-term technology solution for CRE and C&I model implementation
  Conduct gap analyses across risk types focusing on methodology, tools, processes, and expectations as defined by the operating model and benchmark to industry practice
  Create remediation plans to address gaps and initiate remediation actions
  07/29/16
  01/14/16
  06/03/16
  07/29/16
  07/01/16
  04/15/16
  09/30/16
  12/04/16
  06/22/15
  06/22/15
  04/04/16
  04/04/16
  06/06/16
  05/04/15
  07/01/16
  08/03/16
  Hennessy / Smith
  Hennessy / Smith

## Slide 27: Risk Transformation project plan – Risk Management Change Index
Deliverables / milestones
Finish
Start
Change Made
  Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements
  Design Liquidity Stress Test Challenge Process Framework and get approvals
  Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA
  Rollout Commercial Risk Ratings
    Establish governance and oversight on commercial risk ratings governance
    Rollout Redesigned CRE rating models
      CRE model development and validation (refer to Model Dev. / Model Risk workstreams2)
      CRE UAT / pilot testing
      CRE end-user training
      CRE initial model implementation / rollout
  11/30/15
  12/31/15
  03/31/16
  07/29/16
  07/31/15
  05/27/16
  11/18/15
  04/01/16
  05/27/16
  05/06/16
  11/03/14
  06/01/15
  02/01/16
  05/04/15
  06/01/15
  06/29/15
  06/29/15
  02/01/16
  02/01/16
  04/04/16
    Rollout Redesigned C&I rating models
      C&I model development and validation (refer to Model Dev. / Model Risk workstreams1)
      C&I UAT / pilot testing
      C&I end-user training
      C&I initial model implementation / rollout
    Create requirement definitions for long-term technology solution for CRE and C&I model implementation
  Conduct gap analyses across risk types focusing on methodology, tools, processes, and expectations as defined by the operating model and benchmark to industry practice
  Create remediation plans to address gaps and initiate remediation actions
  07/29/16
  01/14/16
  06/03/16
  07/29/16
  07/01/16
  04/15/16
  09/30/16
  12/04/16
  06/22/15
  06/22/15
  04/04/16
  04/04/16
  06/06/16
  05/04/15
  07/01/16
  08/03/16
  No Changes
  No Changes
  No Changes
  Start date changed to 6/1/15 due to subtasks
    No Changes
    Title Changed to reflect subtasks
      No changes
      Start date changed to 1/4/16
      Start date changed to 1/18/16
      Start date changed to 2/29/16
    Title Changed to reflect subtasks
      No changes
      Start date changed to 3/21/16
      Start date changed to 3/21/16
      No Change
    Start date changed to 9/1/15
  No Changes
  End Date changed to 12/2/16 (12/4/16 is a Sunday)