## Sheet1
WBS | Task Name | Start | Finish | Duration | % Complete | Entity | Contact | Notes | Update Notes
0 | RT_Risk Governance & Organization | 2015-06-15 | 2017-05-02 | 492d? | 11%
1 | Risk Governance & Organization Deliverables | 2015-07-31 | 2017-04-04 | 438d? | 0%
1.1 | DELIVERABLE: Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-11-30 | 2015-11-30 | 0d | 0% | SHUSA | B. Gunn
1.2 | DELIVERABLE: Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2016-01-31 | 2016-01-31 | 0d | 0% | SHUSA | B. Gunn
1.3 | DELIVERABLE: Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | SHUSA
1.4 | DELIVERABLE: Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA
1.5 | DELIVERABLE: Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2016-01-08 | 2016-01-08 | 0d | 0% | SHUSA |  | Need further discussion to finalize
1.6 | DELIVERABLE: Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-10-02 | 2015-10-02 | 0d | 0% | SHUSA | B. Gunn
1.7 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | SHUSA | B. Gunn
1.8 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-04-01 | 2016-04-01 | 0d | 0% | SHUSA | B. Gunn
1.9 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-09-30 | 2016-09-30 | 0d | 0% | SHUSA | B. Gunn
1.1 | DELIVERABLE: Assess existing Risk Management Performance Scorecards and identify gaps | 2015-12-18 | 2015-12-18 | 0d | 100% | SHUSA | B. Gunn/C. Briongos
1.11 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2017-01-02 | 2017-01-02 | 0d | 0% | SHUSA | B. Gunn/C. Briongos
1.12 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2017-04-04 | 2017-04-04 | 0d | 0% | SHUSA | B. Gunn/C. Briongos
2 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | 99d | 37% | SHUSA | B. Gunn
2.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA | B. Gunn
2.1.1 | MILESTONE: Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA
2.1.1.1 | Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA |  | Documentation Required
2.1.1.2 | Syndicate with key stakeholders and get necessary approvals for the guiding principles | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA
2.1.1.3 | Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA | John Hennessy / Edward Smith
2.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 2015-07-15 | 2015-08-15 | 24d | 100% | SHUSA | B. Gunn
2.2.1 | MILESTONE: Final landscape validated with Brian | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA
2.2.2 | MILESTONE: Socialization with Chris Pfirrman, Jerry Plush, Scott Powell | 2015-07-31 | 2015-08-07 | 6d | 100% | SHUSA
2.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-08-01 | 2015-09-30 | 44d | 56% | SHUSA | B. Gunn
2.3.1 | MILESTONE: Establish R&R of committees | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA
2.3.1.1 | Risk committees (draft and socialisation with Risk managers) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA
2.3.1.2 | Non-risk committees (draft) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA
2.3.1.3 | Socialization with key stakeholders | 2015-07-24 | 2015-07-31 | 6d | 100% | SHUSA
2.3.1.4 | Establish R&R of committees complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA
2.3.2 | MILESTONE: Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) | 2015-07-27 | 2015-08-14 | 15d | 100% | SHUSA | C. Antoine
2.3.2.1 | Risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | SHUSA |  | High-level description
2.3.2.2 | Non-risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | SHUSA |  | All decentralized for SBNA and SCUSA
2.3.2.3 | Socialization with key stakeholders | 2015-08-03 | 2015-08-14 | 10d | 100% | SHUSA | C. Antoine | Aligned with TOM (Brian engaged on this in the charter work)
2.3.2.4 | Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) complete | 2015-08-14 | 2015-08-14 | 0d | 100% | SHUSA | C. Antoine
2.3.3 | MILESTONE: Design of charter template | 2015-07-27 | 2015-08-10 | 11d | 100% | SHUSA | C. Antoine
2.3.3.1 | Overall structure of charter | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA |  | ERMC drafted, shared with Brian and Legal
2.3.3.2 | Structure of the Roles and responsibilities section | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA |  | Documentation Required
2.3.3.3 | Socialization / alignment with Brian & Chris Pfirrman | 2015-07-31 | 2015-08-07 | 6d | 100% | SHUSA |  | Done, Brian wants to see example of it now
2.3.3.4 | Design of charter template complete | 2015-08-10 | 2015-08-10 | 0d | 100% | SHUSA | C. Antoine
2.3.4 | MILESTONE: Design SHUSA - Group Governance Mechanisms | 2015-07-27 | 2015-08-31 | 26d | 68% | SHUSA | B. Elena
2.3.4.1 | Review of current documentation | 2015-07-27 | 2015-08-03 | 6d | 100% | SHUSA |  | Ask Olivia / Elena
2.3.4.2 | Benchmark / IC of FBO's practices | 2015-07-27 | 2015-08-17 | 16d | 100% | SHUSA |  | Ask Olivia / Elena
2.3.4.3 | Articulate High-level Governance Mechanisms | 2015-08-03 | 2015-08-31 | 21d | 36% | SHUSA | B. Elena | Ask Olivia / Elena
2.3.4.3.1 | Articulation / formalization (in a ppt document) | 2015-08-03 | 2015-08-24 | 16d | 50% | SHUSA | B. Elena | Documentation Required; Ask Olivia / Elena
2.3.4.3.2 | Socialization and Brian sign-off | 2015-08-24 | 2015-08-31 | 6d | 0% | SHUSA | B. Elena | Documentation Required; Ask Olivia / Elena
2.3.4.4 | Design SHUSA - Group Governance Mechanisms complete | 2015-08-31 | 2015-08-31 | 0d | 20% | SHUSA | B. Elena
2.3.5 | MILESTONE: Complete Charter Drafting | 2015-07-27 | 2015-09-28 | 46d | 39% | SHUSA | C. Antoine
2.3.5.1 | Risk Committees charters | 2015-07-27 | 2015-09-21 | 41d | 58% | SHUSA | C. Antoine
2.3.5.1.1 | ERMC charters | 2015-07-27 | 2015-08-24 | 21d | 100% | SHUSA |  | Documentation Required; Board Risk Committee will not be written in this round so this item is technically done (100%)
2.3.5.1.2 | Finalize by adding the approvals from other risk committees | 2015-09-14 | 2015-09-21 | 6d | 0% | SHUSA | C. Antoine
2.3.5.1.3 | Model Risk Management | 2015-07-27 | 2015-08-17 | 16d | 100% | SHUSA
2.3.5.1.4 | Credit Risk & ALLL & Executive Credit | 2015-08-10 | 2015-09-07 | 21d | 60% | SHUSA | C. Antoine | Documentation Required; CRC in review process, Executive Credit and ALLL drafted
2.3.5.1.5 | New Product | 2015-08-10 | 2015-09-07 | 21d | 100% | SHUSA | C. Antoine | Documentation Required
2.3.5.1.6 | Compliance | 2015-08-24 | 2015-09-14 | 16d | 40% | SHUSA | C. Antoine | Documentation Required; First draft completed
2.3.5.1.7 | Operational Risk | 2015-08-24 | 2015-09-14 | 16d | 0% | SHUSA | C. Antoine | Documentation Required
2.3.5.1.8 | Market | 2015-08-24 | 2015-09-14 | 16d | 0% | SHUSA | C. Antoine | Documentation Required
2.3.5.2 | Finance Committees charters (ALCO) | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA | C. Antoine
2.3.5.2.1 | ALCO | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA | C. Antoine | Documentation Required
2.3.5.2.2 | Liquidity | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA | C. Antoine | Documentation Required
2.3.5.3 | Other Committees charters (Executive, HR, Comp etc.) | 2015-08-10 | 2015-09-21 | 31d | 6% | SHUSA | B. Elena
2.3.5.3.1 | Board Committees | 2015-08-10 | 2015-08-31 | 16d | 0% | SHUSA | B. Elena | Documentation Required; Update will most likely be postponed
2.3.5.3.2 | Management committees | 2015-08-24 | 2015-09-21 | 21d | 10% | SHUSA | B. Elena | Documentation Required; Executive Management Committee charter was drafted
2.3.5.4 | Charter Drafting complete | 2015-09-28 | 2015-09-28 | 0d | 0% | SHUSA | B. Elena
2.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | SHUSA | B. Gunn
2.4.1 | MILESTONE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | SHUSA | B. Elena
2.4.1.1 | Document organization structure for SHUSA and subsidiaries, along with reporting lines | 2015-08-01 | 2015-09-30 | 44d | 10% | SHUSA | B. Elena | Documentation Required
2.4.1.2 | Define roles and responsibilities, including decision rights, escalation protocols etc. | 2015-08-01 | 2015-09-30 | 44d | 10% | SHUSA | B. Elena | Documentation Required
2.4.1.3 | Define reporting lines for legal and audit | 2015-08-01 | 2015-09-30 | 44d | 0% | SHUSA
2.4.1.4 | Document the overarching organization structure of SHUSA and its subsidiaries complete | 2015-09-30 | 2015-09-30 | 0d | 0% | SHUSA | B. Elena
2.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | SHUSA | B. Gunn
2.5.1 | MILESTONE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | SHUSA | B. Elena
2.5.1.1 | Establish overarching Policy Framework including guidelines for approval | 2015-07-15 | 2015-08-12 | 21d | 75% | SHUSA |  | To be discussed (part of the Governance playbook)
2.5.1.2 | Establish prioritized policies and procedures across functions | 2015-07-15 | 2015-09-30 | 56d | 0% | SHUSA
2.5.1.3 | Develop policy framework, establish overall policies including guidelines for approval of policies complete | 2015-09-30 | 2015-09-30 | 0d | 0% | SHUSA | B. Elena
2.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA | B. Gunn
2.6.1 | MILESTONE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA
2.6.1.1 | Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA
2.6.1.2 | Define priority reports for each function across SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA
2.6.1.3 | Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries complete | 2015-10-31 | 2015-10-31 | 0d | 0% | SHUSA
2.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | SHUSA | B. Gunn
2.7.1 | MILESTONE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | SHUSA
2.7.1.1 | Syndicate with subsidiaries, and refine framework document | 2015-11-01 | 2015-11-22 | 17d | 0% | SHUSA
2.7.1.2 | Review for completeness of IHC EPS rules | 2015-11-01 | 2015-11-22 | 17d | 0% | SHUSA
2.7.1.3 | Get approvals from SHUSA and subsidiary Boards | 2015-11-22 | 2015-11-29 | 7d | 0% | SHUSA
2.7.1.4 | Syndicate Governance and Oversight Framework document Complete | 2015-11-29 | 2015-11-29 | 0d | 0% | SHUSA
2.8 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | 45d | 0% | SHUSA | B. Gunn
2.8.1 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2015-12-01 | 2016-01-15 | 34d | 0% | SHUSA
2.8.1.1 | Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 2015-12-01 | 2015-12-31 | 23d | 0% | SHUSA
2.8.1.2 | Synthesize key gaps and syndicate with stakeholders | 2016-01-04 | 2016-01-15 | 10d | 0% | SHUSA
2.8.1.3 | Conduct gap analysis Complete | 2016-01-15 | 2016-01-15 | 1d | 0% | SHUSA
2.8.2 | Establish comprehensive implementation plans to address these gaps over a multi-year period | 2016-01-04 | 2016-01-31 | 21d | 0% | SHUSA
2.9 | Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | SHUSA
2.1 | Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-13 | 2015-07-31 | 15d | 100% | SHUSA
2.10.1 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA | B. Gunn
2.10.1.1 | MILESTONE: Review meeting cadence, attendees and agenda established | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA
2.10.1.1.1 | Identify review meeting attendees | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA
2.10.1.1.2 | Establish review meeting calendar | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA |  | Documentation Required
2.10.1.1.3 | Define review meeting agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA |  | Documentation Required
2.10.2 | DELIVERABLE: Review and select existing reports for review meeting | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA | B. Gunn
2.10.2.1 | MILESTONE: Existing reports reviewed and selected | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA
2.10.2.1.1 | Review existing risk reports | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA
2.10.2.1.2 | Selecty existing reports | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA
2.10.2.1.3 | Implement Routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA
2.11 | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2015-10-05 | 2016-01-08 | 70d | 0% | SHUSA |  | Need further discussion to finalize
2.12 | Assess existing Risk Management Performance Scorecards and identify gaps | 2015-06-15 | 2015-12-18 | 135d | 64% | SHUSA | B. Gunn/C. Briongos
2.12.1 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | SHUSA | B. Gunn/C. Briongos | included from legacy CEP plan; justified / coordinated with the (round 2) enhancements below
2.12.1.1 | MILESTONE: Quick Win Enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | SHUSA
2.12.1.1.1 | Submit 1st Submission of Year to Date Figures from Data Feed Owners | 2015-06-15 | 2015-07-09 | 19d | 100% | SHUSA
2.12.1.1.2 | Create Mid Year RMPS to Share with Managers | 2015-07-10 | 2015-07-31 | 16d | 100% | SHUSA |  | Documentation Required
2.12.1.1.3 | Quick Win Enhancements to existing Risk Management Performance Scorecards Complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA
2.12.2 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA | B. Gunn/C. Briongos | need to justify / coordinate with the quick win enhancements above
2.12.2.1 | MILESTONE: Enhance Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA
2.12.2.1.1 | Perform high level assessment and remediation of performance scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA
2.12.2.1.2 | Assessment and Remediation of Performance Scorecards Complete | 2015-11-27 | 2015-11-27 | 0d | 0% | SHUSA
3 | Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | B. Gunn
3.1 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | B. Gunn
3.1.1 | MILESTONE: Risk organizational structure charts and subsidiary reporting schemes submitted to and approved by CRO (SHUSA) | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | B. Elena | Ops Risk
3.1.1.1 | Formalize subsidiary CRO reporting lines, socialize and refine solution (SHUSA) | 2015-08-03 | 2015-08-14 | 10d | 50% | SHUSA | B. Elena
3.1.1.2 | Define implications of reporting lines (for Performance assessment and hiring/firing authority) (SHUSA) | 2015-08-10 | 2015-08-21 | 10d | 100% | SHUSA | B. Elena
3.1.1.3 | Design 1st LoD Risk organization leadership structure including the role of RCO (SHUSA) | 2015-08-03 | 2015-09-04 | 25d | 0% | SHUSA | B. Elena | Documentation Required | Uncertain. Dependent on follow up BCO meeting with Scott
3.1.1.4 | Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 2015-10-02 | 2015-10-02 | 0d | 0% | SHUSA
4 | Design Operating Model across all risk types aligned with principles of 3 LOD, develop rollout plans and implement | 2015-06-22 | 2017-05-02 | 487d | 6% | SHUSA | B. Gunn | Ops Risk
4.1 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 2015-06-22 | 2015-07-17 | 20d | 100% | SHUSA
4.2 | DELIVERABLE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 110d? | 29% | SHUSA | B. Gunn
4.2.1 | MILESTONE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 110d? | 29% | SHUSA
4.2.1.1 | Strengthening Second LOD reporting: Determine high level subsidiary CRO reporting lines | 2015-07-13 | 2015-07-27 | 11d | 0% | SHUSA | B. Gunn
4.2.1.2 | Strengthening Second LOD reporting: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 0% | SHUSA | B. Gunn
4.2.1.3 | Designing the Business Control Officers: Initial high level design | 2015-07-13 | 2015-07-27 | 11d | 100% | SHUSA
4.2.1.4 | Designing the Business Control Officers: Detailed roles and responsibilities design | 2015-07-20 | 2015-08-03 | 11d | 100% | SHUSA
4.2.1.5 | Designing the Business Control Officers: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 100% | SHUSA
4.2.1.6 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100% | SHUSA
4.2.1.7 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100% | SHUSA
4.2.1.8 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 11d | 100% | SHUSA
4.2.1.9 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 95% | SHUSA | M. Tony | Documentation Required; In progress, waiting for finalized stakeholder from Risk MI
4.2.1.10 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 100% | SHUSA | M. Tony
4.2.1.11 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 100% | SHUSA | M. Tony
4.2.1.12 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 21d | 50% | SHUSA | M. Tony |  | ERM, compliance, and risk MI have not been reviewed
4.2.1.13 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 16d | 25% | SHUSA | M. Tony | Documentation Required | ERM, compliance, and risk MI have not been reviewed
4.2.1.14 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 75% | SHUSA | M. Tony
4.2.1.15 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 25% | SHUSA | M. Tony
4.2.1.16 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 21d | 0% | SHUSA | M. Tony
4.2.1.17 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 31d | 0% | SHUSA | M. Tony
4.2.1.18 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | SHUSA | M. Tony
4.2.1.19 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 21d | 0% | SHUSA | M. Tony | Documentation Required
4.2.1.20 | Review frameworks and policies to ensure alignment to TOM design and clear articulation of 3LoD design | 2015-10-05 | 2015-12-11 | 50d? | 0% | SHUSA
4.2.1.21 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 21d | 0% | SHUSA
4.2.1.22 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 16d | 0% | SHUSA
4.2.1.23 | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 21d | 0% | SHUSA
4.2.1.24 | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 16d | 0% | SHUSA
4.2.1.25 | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 15d | 0% | SHUSA |  | Documentation Required
4.2.1.26 | Operating model and implementation plans for all risk types ex. Op Risk complete | 2015-12-11 | 2015-12-11 | 0d | 0% | SHUSA |  | Estimate timeline is 9 months subject to change based on final plan
4.3 | DELIVERABLE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 110d | 21% | SHUSA | B. Gunn
4.3.1 | MILESTONE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 110d | 21% | SHUSA
4.3.1.1 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100% | SHUSA
4.3.1.2 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100% | SHUSA
4.3.1.3 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 9d | 100% | SHUSA | M. Tony
4.3.1.4 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 95% | SHUSA | M. Tony | Documentation Required; In progress, meeting on Thur. to confirm minor changes
4.3.1.5 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 100% | SHUSA | M. Tony
4.3.1.6 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 100% | SHUSA | M. Tony
4.3.1.7 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 21d | 50% | SHUSA | M. Tony
4.3.1.8 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 16d | 0% | SHUSA | M. Tony | Documentation Required
4.3.1.9 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 0% | SHUSA | M. Tony
4.3.1.10 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 50% | SHUSA | M. Tony
4.3.1.11 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 21d | 0% | SHUSA | M. Tony
4.3.1.12 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 31d | 0% | SHUSA | M. Tony
4.3.1.13 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | SHUSA | M. Tony
4.3.1.14 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 21d | 0% | SHUSA |  | Documentation Required
4.3.1.15 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 21d | 0% | SHUSA
4.3.1.16 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 16d | 0% | SHUSA
4.3.1.17 | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 21d | 0% | SHUSA
4.3.1.18 | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 16d | 0% | SHUSA
4.3.1.19 | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 15d | 0% | SHUSA |  | Documentation Required
4.3.1.20 | Operating model and implementation plans for Op Risk complete | 2015-12-11 | 2015-12-11 | 0d | 0% | SHUSA
4.4 | Implement the redesigned Operating Model for all the risks | 2015-12-14 | 2016-08-12 | 175d | 0% | SHUSA | B. Gunn
4.4.1 | Implement redesigned Operating Model for SHUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | SHUSA
4.4.2 | Implement redesigned Operating Model for SBNA | 2015-12-14 | 2016-08-12 | 175d | 0% | SBNA
4.4.3 | Implement redesigned Operating Model for SCUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | SCUSA
4.4.4 | Implement redesigned Operating Model for Puerto Rico | 2015-12-14 | 2016-08-12 | 175d | 0% | Banco Santander Puerto Rico
4.4.5 | Implement redesigned Operating Model for Miami | 2015-12-14 | 2016-08-12 | 175d | 0% | Banco Santander International (BSI Miami)
4.4.6 | Implement redesigned Operating Model for NY | 2015-12-14 | 2016-08-12 | 175d | 0% | Santander Investment Securities (SIS NY)
4.5 | DELIVERABLE: Post Implementation Review | 2016-08-15 | 2016-10-14 | 45d | 0% | SHUSA | B. Gunn
4.5.1 | MILESTONE: Post Implementation Review Conducted | 2016-08-15 | 2016-10-14 | 45d | 0% | SHUSA
4.5.1.1 | Post Implementation Review | 2016-08-15 | 2016-10-14 | 45d | 0% | SHUSA
4.5.1.2 | MILESTONE: Post Implementation Review Conducted | 2016-10-14 | 2016-10-14 | 0d | 0% | SHUSA
4.6 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-02-01 | 2016-04-01 | 45d | 0% | SHUSA | B. Gunn
4.6.1 | MILESTONE: Strong and Desired Risk Culture Defined | 2016-02-01 | 2016-04-01 | 45d | 0% | SHUSA
4.6.1.1 | Determine the survey population and tailor survey as needed (1 week) | 2016-02-01 | 2016-02-05 | 5d | 0% | SHUSA
4.6.1.2 | Deploy culture survey and collect responses (2-3 week) | 2016-02-01 | 2016-02-19 | 15d | 0% | SHUSA
4.6.1.3 | Aggregate and analyze survey results (2-3 weeks) | 2016-02-22 | 2016-03-11 | 15d | 0% | SHUSA |  | Documentation Required
4.6.1.4 | Conduct 3-4 targeted focus groups or workshops to refine and validate the insights (1-2 weeks) - goes in parallel with 3. | 2016-02-29 | 2016-03-18 | 15d | 0% | SHUSA
4.6.1.5 | Review findings, document current state risk culture and priritize focus areas (1 week) | 2016-03-21 | 2016-04-01 | 10d | 0% | SHUSA
4.6.1.6 | MILESTONE: Strong and Desired Risk Culture Defined | 2016-04-01 | 2016-04-01 | 0d | 0% | SHUSA
4.7 | Long Term Planning Package | 2016-01-25 | 2017-04-04 | 312d? | 0% | SHUSA
4.7.1 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2016-04-01 | 2017-01-02 | 197d? | 0% | SHUSA | B. Gunn/C. Briongos
4.7.1.1 | MILESTONE: Design risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.1.1.1 | Benchmark of risk-based compensation practices in the industry | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.1.1.2 | Risk-based compensation proposals and refinement with stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.1.1.3 | Impact analysis of new frameworks on compensation levels | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.1.1.4 | Formalization of new risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.1.1.5 | Risk-based compensation structure formalized | 2016-06-30 | 2016-06-30 | 0d | 0% | SHUSA
4.7.1.2 | MILESTONE: Communication and stakeholder engagement | 2016-04-01 | 2016-09-30 | 131d? | 0% | SHUSA
4.7.1.2.1 | Design of communication plan | 2016-04-01 | 2016-06-30 | 65d? | 0% | SHUSA
4.7.1.2.2 | Development of communication materials | 2016-04-01 | 2016-06-30 | 65d? | 0% | SHUSA
4.7.1.2.3 | Execution of communication plan | 2016-06-30 | 2016-09-30 | 67d? | 0% | SHUSA
4.7.1.2.4 | Stakeholder communication complete | 2016-09-30 | 2016-09-30 | 0d | 0% | SHUSA
4.7.1.3 | MILESTONE: Updates to performance assessment templates | 2016-07-01 | 2017-01-02 | 132d? | 0% | SHUSA
4.7.1.3.1 | Inventory of performance assessment templates at SHUSA, SBNA and SCUSA | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA
4.7.1.3.2 | Update of template in accordance with risk-based compensation framework | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA
4.7.1.3.3 | Socialization, training of stakeholders and roll-out of new templates | 2016-09-30 | 2017-01-02 | 67d? | 0% | SHUSA
4.7.1.3.4 | Performance assessment templates updated | 2016-12-31 | 2016-12-31 | 0d | 0% | SHUSA
4.7.2 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | SHUSA | B. Gunn
4.7.2.1 | MILESTONE: Communications to emphasize progress being made / share best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA
4.7.2.1.1 | Assessment of progress being made & best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA
4.7.2.1.2 | Design of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA
4.7.2.1.3 | Development of communications materials | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA
4.7.2.1.4 | Delivery of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA
4.7.2.1.5 | Progress communications delivered | 2016-04-22 | 2016-04-22 | 0d | 0% | SHUSA
4.7.2.2 | MILESTONE: Convey organizational changes to the enterprise | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.2.2.1 | Development of materials | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.2.2.2 | Delivery of communication to stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA
4.7.2.2.3 | Organizational changes communicated to enterprise | 2016-06-30 | 2016-06-30 | 0d | 0% | SHUSA
4.7.2.3 | MILESTONE: Enterprise-wide training and development of job descriptions with explicit focus on three lines of defense | 2016-07-01 | 2017-01-02 | 132d | 0% | SHUSA
4.7.2.3.1 | Design of training curriculum & idenfification of key recepients as a result of post-implementation reviews | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA
4.7.2.3.2 | Development of training materials | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA
4.7.2.3.3 | Delivery of training to priority recipients | 2016-09-30 | 2017-01-02 | 67d? | 0% | SHUSA
4.7.2.3.4 | Identification of key functions requiring job description updates | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA
4.7.2.3.5 | Development of job descriptions with explicit focus on three lines of defense | 2016-09-30 | 2017-01-02 | 67d? | 0% | SHUSA
4.7.2.3.6 | Job descriptions complete and enterprise-wide training delivered | 2016-12-31 | 2016-12-31 | 0d | 0% | SHUSA
4.7.3 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2016-07-01 | 2017-04-04 | 198d? | 0% | SHUSA | B. Gunn/C. Briongos
4.7.3.1 | MILESTONE: Design recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA
4.7.3.1.1 | Diagnostic of retention challenges | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA
4.7.3.1.2 | Design of new possible retention mechanisms | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA
4.7.3.1.3 | Milestone: Design of new possible retention mechanisms complete | 2016-09-30 | 2016-09-30 | 0d | 0% | SHUSA
4.7.3.2 | MILESTONE: Action plans for necessary remediation efforts | 2016-10-03 | 2017-04-04 | 132d? | 0% | SHUSA
4.7.3.2.1 | Selection of key remediation initiatives with key stakeholders | 2016-10-03 | 2017-01-04 | 68d? | 0% | SHUSA
4.7.3.2.2 | Planning of initiatives between SHUSA and its subsidiaries | 2016-10-03 | 2017-01-04 | 68d? | 0% | SHUSA
4.7.3.2.3 | Rollout of initiatives at SHUSA | 2016-10-03 | 2017-01-04 | 68d? | 0% | SHUSA
4.7.3.2.4 | Rollout of initiatives at other subsidiaries | 2017-01-02 | 2017-04-04 | 67d | 0% | SHUSA
4.7.3.2.5 | Recruitment and retention intiatives introduced throughout enterprise | 2017-04-04 | 2017-04-04 | 0d | 0% | SHUSA
4.7.4 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA | B. Gunn
4.7.4.1 | MILESTONE: Create multi-year plan that describes interventions | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA
4.7.4.2 | MILESTONE: Syndicate plan with key stakeholders and get approvals | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA
4.7.4.3 | MILESTONE: Diagnostics of risk culture; multi-year plan to achieve premier risk culture in place | 2016-09-30 | 2016-09-30 | 0d | 0% | SHUSA

## Sheet2
Current | [14 empty] | Original
Unique Activity Code | Deliverable ID | WBS | Task Name | Start | Finish | Duration | % Complete | Entity | Primary Commitment | Secondary Commitment | Tertiary Commitment | Contact | Notes | Dependency | Task Name | Start | Finish | Duration | % Complete | Task Name | Start | Finish
RG0 |  | 0 | RT_Risk Governance & Organization | 2015-06-15 | 2017-04-04 | 472d? | 12% | [7 empty] | RT_Risk Governance & Organization | 2015-06-15 | 2017-05-02 | 492d? | 11% | TRUE | TRUE | FALSE
RG2452 |  | 1 | Risk Governance & Organization Deliverables | 2015-07-31 | 2017-04-04 | 438d? | 0% | [7 empty] | Risk Governance & Organization Deliverables | 2015-07-31 | 2017-04-04 | 438d? | 0% | TRUE | TRUE | TRUE
RG4211 | RT.B.1 | 1.1 | DELIVERABLE: Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-11-30 | 2015-11-30 | 0d | 0% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Gunn |  |  | DELIVERABLE: Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-11-30 | 2015-11-30 | 0d | 0% | TRUE | TRUE | TRUE
RG4212 | RT.B.2 | 1.2 | DELIVERABLE: Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2016-01-31 | 2016-01-31 | 0d | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization |  |  | B. Gunn |  |  | DELIVERABLE: Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2016-01-31 | 2016-01-31 | 0d | 0% | TRUE | TRUE | TRUE
RG4213 | RT.B.3 | 1.3 | DELIVERABLE: Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization | [5 empty] | DELIVERABLE: Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | TRUE | TRUE | TRUE
RG4214 | RT.B.4 | 1.4 | DELIVERABLE: Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | DELIVERABLE: Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | TRUE | TRUE | TRUE
RG4207 | RT.B.5 | 1.5 | DELIVERABLE: Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2016-01-08 | 2016-01-08 | 0d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  |  | Need further discussion to finalize |  | DELIVERABLE: Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2016-01-08 | 2016-01-08 | 0d | 0% | TRUE | TRUE | TRUE
RG4208 | RT.B.6 | 1.6 | DELIVERABLE: Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-10-02 | 2015-10-02 | 0d | 0% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | RT.Governance and Organization.Y1_181_Perform a talent review and assessment of key risk staff and develop a strategy to address gaps in hiring training leadership programs |  | B. Gunn |  |  | DELIVERABLE: Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-10-02 | 2015-10-02 | 0d | 0% | TRUE | TRUE | TRUE
RG4209 | RT.B.8 | 1.7 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model |  |  | B. Gunn |  |  | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | TRUE | TRUE | TRUE
RG4210 | RT.B.9 | 1.8 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-04-01 | 2016-04-01 | 0d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-04-01 | 2016-04-01 | 0d | 0% | TRUE | TRUE | TRUE
RG4205 | RT.B.10 | 1.9 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-09-30 | 2016-09-30 | 0d | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model |  |  | B. Gunn |  |  | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-09-30 | 2016-09-30 | 0d | 0% | TRUE | TRUE | TRUE
RG4206 | RT.B.11 | 1.1 | DELIVERABLE: Assess existing Risk Management Performance Scorecards and identify gaps | 2015-12-18 | 2015-12-18 | 0d | 100% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  | B. Gunn/C. Briongos |  |  | DELIVERABLE: Assess existing Risk Management Performance Scorecards and identify gaps | 2015-12-18 | 2015-12-18 | 0d | 100% | TRUE | TRUE | TRUE
RG4204 | RT.B.12 | 1.11 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2017-01-02 | 2017-01-02 | 0d | 0% | SHUSA | RT.Governance and Organization.Y2_44_Roll out performance assessment and compensation frameworks across the organization |  |  | B. Gunn/C. Briongos |  |  | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2017-01-02 | 2017-01-02 | 0d | 0% | TRUE | TRUE | TRUE
RG4203 | RT.B.13 | 1.12 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2017-04-04 | 2017-04-04 | 0d | 0% | SHUSA | RT.Governance and Organization.Y2_46_Develop talent management mechanisms |  |  | B. Gunn/C. Briongos |  |  | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2017-04-04 | 2017-04-04 | 0d | 0% | TRUE | TRUE | TRUE
RG2454 | RT.B.1 | 2 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | 99d | 36% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Gunn |  |  | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | 99d | 37% | TRUE | TRUE | TRUE
RG2455 | RT.B.1 | 2.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Gunn |  |  | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 2015-07-15 | 2015-07-31 | 13d | 100% | TRUE | TRUE | TRUE
RG2834 | RT.B.1 | 2.1.1 | MILESTONE: Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | [5 empty] | MILESTONE: Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals | 2015-07-15 | 2015-07-31 | 13d | 100% | TRUE | TRUE | TRUE
RG3126 | RT.B.1 | 2.1.1.1 | Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA |  |  |  |  | Documentation Required |  | Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 2015-07-15 | 2015-07-24 | 8d | 100% | TRUE | TRUE | TRUE
RG3127 | RT.B.1 | 2.1.1.2 | Syndicate with key stakeholders and get necessary approvals for the guiding principles | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA | [6 empty] | Syndicate with key stakeholders and get necessary approvals for the guiding principles | 2015-07-27 | 2015-07-31 | 5d | 100% | TRUE | TRUE | TRUE
RG2456 | RT.B.1 | 2.1.1.3 | Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA |  |  |  | John Hennessy / Edward Smith |  |  | Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals complete | 2015-07-31 | 2015-07-31 | 0d | 100% | TRUE | TRUE | TRUE
RG3295 | RT.B.1 | 2.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 2015-07-15 | 2015-08-15 | 24d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Gunn |  |  | DELIVERABLE: Define target state committee structure including Board and Management committees | 2015-07-15 | 2015-08-15 | 24d | 100% | TRUE | TRUE | TRUE
RG4106 | RT.B.1 | 2.2.1 | MILESTONE: Final landscape validated with Brian | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | [5 empty] | MILESTONE: Final landscape validated with Brian | 2015-07-15 | 2015-07-31 | 13d | 100% | TRUE | TRUE | TRUE
RG4105 | RT.B.1 | 2.2.2 | MILESTONE: Socialization with Chris Pfirrman, Jerry Plush, Scott Powell | 2015-07-31 | 2015-08-07 | 6d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | [5 empty] | MILESTONE: Socialization with Chris Pfirrman, Jerry Plush, Scott Powell | 2015-07-31 | 2015-08-07 | 6d | 100% | TRUE | TRUE | TRUE
RG2462 | RT.B.1 | 2.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-08-01 | 2015-09-30 | 44d | 56% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Gunn |  |  | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-08-01 | 2015-09-30 | 44d | 56% | TRUE | TRUE | TRUE
RG4157 | RT.B.1 | 2.3.1 | MILESTONE: Establish R&R of committees | 2015-07-15 | 2015-07-31 | 13d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | [5 empty] | MILESTONE: Establish R&R of committees | 2015-07-15 | 2015-07-31 | 13d | 100% | TRUE | TRUE | TRUE
RG4158 | RT.B.1 | 2.3.1.1 | Risk committees (draft and socialisation with Risk managers) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA | [6 empty] | Risk committees (draft and socialisation with Risk managers) | 2015-07-15 | 2015-07-24 | 8d | 100% | TRUE | TRUE | TRUE
RG4159 | RT.B.1 | 2.3.1.2 | Non-risk committees (draft) | 2015-07-15 | 2015-07-24 | 8d | 100% | SHUSA | [6 empty] | Non-risk committees (draft) | 2015-07-15 | 2015-07-24 | 8d | 100% | TRUE | TRUE | TRUE
RG4160 | RT.B.1 | 2.3.1.3 | Socialization with key stakeholders | 2015-07-24 | 2015-07-31 | 6d | 100% | SHUSA | [6 empty] | Socialization with key stakeholders | 2015-07-24 | 2015-07-31 | 6d | 100% | TRUE | TRUE | TRUE
RG4179 | RT.B.1 | 2.3.1.4 | Establish R&R of committees complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA | [6 empty] | Establish R&R of committees complete | 2015-07-31 | 2015-07-31 | 0d | 100% | TRUE | TRUE | TRUE
RG4161 | RT.B.1 | 2.3.2 | MILESTONE: Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) | 2015-07-27 | 2015-08-14 | 15d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | C. Antoine |  |  | MILESTONE: Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) | 2015-07-27 | 2015-08-14 | 15d | 100% | TRUE | TRUE | TRUE
RG4162 | RT.B.1 | 2.3.2.1 | Risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | SHUSA |  |  |  |  | High-level description |  | Risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | TRUE | TRUE | TRUE
RG4163 | RT.B.1 | 2.3.2.2 | Non-risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | SHUSA |  |  |  |  | All decentralized for SBNA and SCUSA |  | Non-risk committees | 2015-07-27 | 2015-08-07 | 10d | 100% | TRUE | TRUE | TRUE
RG4164 | RT.B.1 | 2.3.2.3 | Socialization with key stakeholders | 2015-08-03 | 2015-08-14 | 10d | 100% | SHUSA |  |  |  | C. Antoine | Aligned with TOM (Brian engaged on this in the charter work) |  | Socialization with key stakeholders | 2015-08-03 | 2015-08-14 | 10d | 100% | TRUE | TRUE | TRUE
RG4180 | RT.B.1 | 2.3.2.4 | Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) complete | 2015-08-14 | 2015-08-14 | 0d | 100% | SHUSA |  |  |  | C. Antoine |  |  | Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) complete | 2015-08-14 | 2015-08-14 | 0d | 100% | TRUE | TRUE | TRUE
RG4165 | RT.B.1 | 2.3.3 | MILESTONE: Design of charter template | 2015-07-27 | 2015-08-10 | 11d | 100% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | C. Antoine |  |  | MILESTONE: Design of charter template | 2015-07-27 | 2015-08-10 | 11d | 100% | TRUE | TRUE | TRUE
RG4166 | RT.B.1 | 2.3.3.1 | Overall structure of charter | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA |  |  |  |  | ERMC drafted, shared with Brian and Legal |  | Overall structure of charter | 2015-07-27 | 2015-07-31 | 5d | 100% | TRUE | TRUE | TRUE
RG4167 | RT.B.1 | 2.3.3.2 | Structure of the Roles and responsibilities section | 2015-07-27 | 2015-07-31 | 5d | 100% | SHUSA |  |  |  |  | Documentation Required |  | Structure of the Roles and responsibilities section | 2015-07-27 | 2015-07-31 | 5d | 100% | TRUE | TRUE | TRUE
RG4168 | RT.B.1 | 2.3.3.3 | Socialization / alignment with Brian & Chris Pfirrman | 2015-07-31 | 2015-08-07 | 6d | 100% | SHUSA |  |  |  |  | Done, Brian wants to see example of it now |  | Socialization / alignment with Brian & Chris Pfirrman | 2015-07-31 | 2015-08-07 | 6d | 100% | TRUE | TRUE | TRUE
RG4181 | RT.B.1 | 2.3.3.4 | Design of charter template complete | 2015-08-10 | 2015-08-10 | 0d | 100% | SHUSA |  |  |  | C. Antoine |  |  | Design of charter template complete | 2015-08-10 | 2015-08-10 | 0d | 100% | TRUE | TRUE | TRUE
RG4169 | RT.B.1 | 2.3.4 | MILESTONE: Design SHUSA - Group Governance Mechanisms | 2015-07-27 | 2015-08-31 | 26d | 68% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | B. Elena |  |  | MILESTONE: Design SHUSA - Group Governance Mechanisms | 2015-07-27 | 2015-08-31 | 26d | 68% | TRUE | TRUE | TRUE
RG4170 | RT.B.1 | 2.3.4.1 | Review of current documentation | 2015-07-27 | 2015-08-03 | 6d | 100% | SHUSA |  |  |  |  | Ask Olivia / Elena |  | Review of current documentation | 2015-07-27 | 2015-08-03 | 6d | 100% | TRUE | TRUE | TRUE
RG4171 | RT.B.1 | 2.3.4.2 | Benchmark / IC of FBO's practices | 2015-07-27 | 2015-08-17 | 16d | 100% | SHUSA |  |  |  |  | Ask Olivia / Elena |  | Benchmark / IC of FBO's practices | 2015-07-27 | 2015-08-17 | 16d | 100% | TRUE | TRUE | TRUE
RG4172 | RT.B.1 | 2.3.4.3 | Articulate High-level Governance Mechanisms | 2015-08-03 | 2015-08-31 | 21d | 36% | SHUSA |  |  |  | B. Elena | Ask Olivia / Elena |  | Articulate High-level Governance Mechanisms | 2015-08-03 | 2015-08-31 | 21d | 36% | TRUE | TRUE | TRUE
RG4173 | RT.B.1 | 2.3.4.3.1 | Articulation / formalization (in a ppt document) | 2015-08-03 | 2015-08-24 | 16d | 50% | SHUSA |  |  |  | B. Elena | Documentation Required; Ask Olivia / Elena |  | Articulation / formalization (in a ppt document) | 2015-08-03 | 2015-08-24 | 16d | 50% | TRUE | TRUE | TRUE
RG4174 | RT.B.1 | 2.3.4.3.2 | Socialization and Brian sign-off | 2015-08-24 | 2015-08-31 | 6d | 0% | SHUSA |  |  |  | B. Elena | Documentation Required; Ask Olivia / Elena |  | Socialization and Brian sign-off | 2015-08-24 | 2015-08-31 | 6d | 0% | TRUE | TRUE | TRUE
RG4182 | RT.B.1 | 2.3.4.4 | Design SHUSA - Group Governance Mechanisms complete | 2015-08-31 | 2015-08-31 | 0d | 20% | SHUSA |  |  |  | B. Elena |  |  | Design SHUSA - Group Governance Mechanisms complete | 2015-08-31 | 2015-08-31 | 0d | 20% | TRUE | TRUE | TRUE
RG4175 | RT.B.1 | 2.3.5 | MILESTONE: Complete Charter Drafting | 2015-07-27 | 2015-09-28 | 46d | 39% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  | C. Antoine |  |  | MILESTONE: Complete Charter Drafting | 2015-07-27 | 2015-09-28 | 46d | 39% | TRUE | TRUE | TRUE
RG4176 | RT.B.1 | 2.3.5.1 | Risk Committees charters | 2015-07-27 | 2015-09-21 | 41d | 58% | SHUSA |  |  |  | C. Antoine |  |  | Risk Committees charters | 2015-07-27 | 2015-09-21 | 41d | 58% | TRUE | TRUE | TRUE
RG4177 | RT.B.1 | 2.3.5.1.1 | ERMC charters | 2015-07-27 | 2015-08-24 | 21d | 100% | SHUSA |  |  |  |  | Documentation Required; Board Risk Committee will not be written in this round so this item is technically done (100%) |  | ERMC charters | 2015-07-27 | 2015-08-24 | 21d | 100% | TRUE | TRUE | TRUE
RG4178 | RT.B.1 | 2.3.5.1.2 | Finalize by adding the approvals from other risk committees | 2015-09-14 | 2015-09-21 | 6d | 0% | SHUSA |  |  |  | C. Antoine |  |  | Finalize by adding the approvals from other risk committees | 2015-09-14 | 2015-09-21 | 6d | 0% | TRUE | TRUE | TRUE
RG4143 | RT.B.1 | 2.3.5.1.3 | Model Risk Management | 2015-07-27 | 2015-08-17 | 16d | 100% | SHUSA | [6 empty] | Model Risk Management | 2015-07-27 | 2015-08-17 | 16d | 100% | TRUE | TRUE | TRUE
RG4144 | RT.B.1 | 2.3.5.1.4 | Credit Risk & ALLL & Executive Credit | 2015-08-10 | 2015-09-07 | 21d | 60% | SHUSA |  |  |  | C. Antoine | Documentation Required; CRC in review process, Executive Credit and ALLL drafted |  | Credit Risk & ALLL & Executive Credit | 2015-08-10 | 2015-09-07 | 21d | 60% | TRUE | TRUE | TRUE
RG4145 | RT.B.1 | 2.3.5.1.5 | New Product | 2015-08-10 | 2015-09-07 | 21d | 100% | SHUSA |  |  |  | C. Antoine | Documentation Required |  | New Product | 2015-08-10 | 2015-09-07 | 21d | 100% | TRUE | TRUE | TRUE
RG4146 | RT.B.1 | 2.3.5.1.6 | Compliance | 2015-08-24 | 2015-09-14 | 16d | 40% | SHUSA |  |  |  | C. Antoine | Documentation Required; First draft completed |  | Compliance | 2015-08-24 | 2015-09-14 | 16d | 40% | TRUE | TRUE | TRUE
RG4147 | RT.B.1 | 2.3.5.1.7 | Operational Risk | 2015-08-24 | 2015-09-14 | 16d | 0% | SHUSA |  |  |  | C. Antoine | Documentation Required |  | Operational Risk | 2015-08-24 | 2015-09-14 | 16d | 0% | TRUE | TRUE | TRUE
RG4148 | RT.B.1 | 2.3.5.1.8 | Market | 2015-08-24 | 2015-09-14 | 16d | 0% | SHUSA |  |  |  | C. Antoine | Documentation Required |  | Market | 2015-08-24 | 2015-09-14 | 16d | 0% | TRUE | TRUE | TRUE
RG4149 | RT.B.1 | 2.3.5.2 | Finance Committees charters (ALCO) | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA |  |  |  | C. Antoine |  |  | Finance Committees charters (ALCO) | 2015-09-07 | 2015-09-28 | 16d | 0% | TRUE | TRUE | TRUE
RG4150 | RT.B.1 | 2.3.5.2.1 | ALCO | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA |  |  |  | C. Antoine | Documentation Required |  | ALCO | 2015-09-07 | 2015-09-28 | 16d | 0% | TRUE | TRUE | TRUE
RG4151 | RT.B.1 | 2.3.5.2.2 | Liquidity | 2015-09-07 | 2015-09-28 | 16d | 0% | SHUSA |  |  |  | C. Antoine | Documentation Required |  | Liquidity | 2015-09-07 | 2015-09-28 | 16d | 0% | TRUE | TRUE | TRUE
RG4152 | RT.B.1 | 2.3.5.3 | Other Committees charters (Executive, HR, Comp etc.) | 2015-08-10 | 2015-09-21 | 31d | 6% | SHUSA |  |  |  | B. Elena |  |  | Other Committees charters (Executive, HR, Comp etc.) | 2015-08-10 | 2015-09-21 | 31d | 6% | TRUE | TRUE | TRUE
RG4153 | RT.B.1 | 2.3.5.3.1 | Board Committees | 2015-08-10 | 2015-08-31 | 16d | 0% | SHUSA |  |  |  | B. Elena | Documentation Required; Update will most likely be postponed |  | Board Committees | 2015-08-10 | 2015-08-31 | 16d | 0% | TRUE | TRUE | TRUE
RG4154 | RT.B.1 | 2.3.5.3.2 | Management committees | 2015-08-24 | 2015-09-21 | 21d | 10% | SHUSA |  |  |  | B. Elena | Documentation Required; Executive Management Committee charter was drafted |  | Management committees | 2015-08-24 | 2015-09-21 | 21d | 10% | TRUE | TRUE | TRUE
RG4183 | RT.B.1 | 2.3.5.4 | Charter Drafting complete | 2015-09-28 | 2015-09-28 | 0d | 0% | SHUSA |  |  |  | B. Elena |  |  | Charter Drafting complete | 2015-09-28 | 2015-09-28 | 0d | 0% | TRUE | TRUE | TRUE
RG3307 | RT.B.1 | 2.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | TRUE | TRUE | TRUE
RG3308 | RT.B.1 | 2.4.1 | MILESTONE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Elena |  |  | MILESTONE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 7% | TRUE | TRUE | TRUE
RG3983 | RT.B.1 | 2.4.1.1 | Document organization structure for SHUSA and subsidiaries, along with reporting lines | 2015-08-01 | 2015-09-30 | 44d | 10% | SHUSA |  |  |  | B. Elena | Documentation Required |  | Document organization structure for SHUSA and subsidiaries, along with reporting lines | 2015-08-01 | 2015-09-30 | 44d | 10% | TRUE | TRUE | TRUE
RG3984 | RT.B.1 | 2.4.1.2 | Define roles and responsibilities, including decision rights, escalation protocols etc. | 2015-08-01 | 2015-09-30 | 44d | 10% | SHUSA |  |  |  | B. Elena | Documentation Required |  | Define roles and responsibilities, including decision rights, escalation protocols etc. | 2015-08-01 | 2015-09-30 | 44d | 10% | TRUE | TRUE | TRUE
RG3985 | RT.B.1 | 2.4.1.3 | Define reporting lines for legal and audit | 2015-08-01 | 2015-09-30 | 44d | 0% | SHUSA | [6 empty] | Define reporting lines for legal and audit | 2015-08-01 | 2015-09-30 | 44d | 0% | TRUE | TRUE | TRUE
RG3986 | RT.B.1 | 2.4.1.4 | Document the overarching organization structure of SHUSA and its subsidiaries complete | 2015-09-30 | 2015-09-30 | 0d | 0% | SHUSA |  |  |  | B. Elena |  |  | Document the overarching organization structure of SHUSA and its subsidiaries complete | 2015-09-30 | 2015-09-30 | 0d | 0% | TRUE | TRUE | TRUE
RG3310 | RT.B.1 | 2.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  | B. Gunn |  |  | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | TRUE | TRUE | TRUE
RG3311 | RT.B.1 | 2.5.1 | MILESTONE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  | B. Elena |  |  | MILESTONE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 20% | TRUE | TRUE | TRUE
RG3987 | RT.B.1 | 2.5.1.1 | Establish overarching Policy Framework including guidelines for approval | 2015-07-15 | 2015-08-12 | 21d | 75% | SHUSA |  |  |  |  | To be discussed (part of the Governance playbook) |  | Establish overarching Policy Framework including guidelines for approval | 2015-07-15 | 2015-08-12 | 21d | 75% | TRUE | TRUE | TRUE
RG3988 | RT.B.1 | 2.5.1.2 | Establish prioritized policies and procedures across functions | 2015-07-15 | 2015-09-30 | 56d | 0% | SHUSA | [6 empty] | Establish prioritized policies and procedures across functions | 2015-07-15 | 2015-09-30 | 56d | 0% | TRUE | TRUE | TRUE
RG3989 | RT.B.1 | 2.5.1.3 | Develop policy framework, establish overall policies including guidelines for approval of policies complete | 2015-09-30 | 2015-09-30 | 0d | 0% | SHUSA |  |  |  | B. Elena |  |  | Develop policy framework, establish overall policies including guidelines for approval of policies complete | 2015-09-30 | 2015-09-30 | 0d | 0% | TRUE | TRUE | TRUE
RG3309 | RT.B.1 | 2.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  | B. Gunn |  |  | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | TRUE | TRUE | TRUE
RG3306 | RT.B.1 | 2.6.1 | MILESTONE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | [5 empty] | MILESTONE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | TRUE | TRUE | TRUE
RG3990 | RT.B.1 | 2.6.1.1 | Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA | [6 empty] | Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 2015-10-01 | 2015-10-31 | 23d | 0% | TRUE | TRUE | TRUE
RG3991 | RT.B.1 | 2.6.1.2 | Define priority reports for each function across SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | SHUSA | [6 empty] | Define priority reports for each function across SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | TRUE | TRUE | TRUE
RG3992 | RT.B.1 | 2.6.1.3 | Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries complete | 2015-10-31 | 2015-10-31 | 0d | 0% | SHUSA | [6 empty] | Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries complete | 2015-10-31 | 2015-10-31 | 0d | 0% | TRUE | TRUE | TRUE
RG3325 | RT.B.1 | 2.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  | B. Gunn |  |  | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | TRUE | TRUE | TRUE
RG3326 | RT.B.1 | 2.7.1 | MILESTONE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | [5 empty] | MILESTONE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | TRUE | TRUE | TRUE
RG3993 | RT.B.1 | 2.7.1.1 | Syndicate with subsidiaries, and refine framework document | 2015-11-01 | 2015-11-22 | 17d | 0% | SHUSA | [6 empty] | Syndicate with subsidiaries, and refine framework document | 2015-11-01 | 2015-11-22 | 17d | 0% | TRUE | TRUE | TRUE
RG4191 | RT.B.1 | 2.7.1.2 | Review for completeness of IHC EPS rules | 2015-11-01 | 2015-11-22 | 17d | 0% | SHUSA | [6 empty] | Review for completeness of IHC EPS rules | 2015-11-01 | 2015-11-22 | 17d | 0% | TRUE | TRUE | TRUE
RG3994 | RT.B.1 | 2.7.1.3 | Get approvals from SHUSA and subsidiary Boards | 2015-11-22 | 2015-11-29 | 7d | 0% | SHUSA | [6 empty] | Get approvals from SHUSA and subsidiary Boards | 2015-11-22 | 2015-11-29 | 7d | 0% | TRUE | TRUE | TRUE
RG3995 | RT.B.1 | 2.7.1.4 | Syndicate Governance and Oversight Framework document Complete | 2015-11-29 | 2015-11-29 | 0d | 0% | SHUSA | [6 empty] | Syndicate Governance and Oversight Framework document Complete | 2015-11-29 | 2015-11-29 | 0d | 0% | TRUE | TRUE | TRUE
RG3328 | RT.B.2 | 3 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | 45d | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization |  |  | B. Gunn |  |  | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | 45d | 0% | TRUE | TRUE | TRUE
RG3327 | RT.B.2 | 3.1 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2015-12-01 | 2016-01-15 | 34d | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization | [5 empty] | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2015-12-01 | 2016-01-15 | 34d | 0% | TRUE | TRUE | TRUE
RG3996 | RT.B.2 | 3.1.1 | Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 2015-12-01 | 2015-12-31 | 23d | 0% | SHUSA | [6 empty] | Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 2015-12-01 | 2015-12-31 | 23d | 0% | TRUE | TRUE | TRUE
RG3997 | RT.B.2 | 3.1.2 | Synthesize key gaps and syndicate with stakeholders | 2016-01-04 | 2016-01-15 | 10d | 0% | SHUSA | [6 empty] | Synthesize key gaps and syndicate with stakeholders | 2016-01-04 | 2016-01-15 | 10d | 0% | TRUE | TRUE | TRUE
RG3998 | RT.B.2 | 3.1.3 | Conduct gap analysis Complete | 2016-01-15 | 2016-01-15 | 1d | 0% | SHUSA | [6 empty] | Conduct gap analysis Complete | 2016-01-15 | 2016-01-15 | 1d | 0% | TRUE | TRUE | TRUE
RG3329 | RT.B.2 | 3.2 | Establish comprehensive implementation plans to address these gaps over a multi-year period | 2016-01-04 | 2016-01-31 | 21d | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization | [5 empty] | Establish comprehensive implementation plans to address these gaps over a multi-year period | 2016-01-04 | 2016-01-31 | 21d | 0% | TRUE | TRUE | TRUE
RG3330 | RT.B.3 | 4 | Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | SHUSA | RT.Governance and Organization.Y2_47_Assess risk culture across the organization | [5 empty] | Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0% | TRUE | TRUE | TRUE
RG3333 | RT.B.4 | 5 | Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-13 | 2015-07-31 | 15d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-13 | 2015-07-31 | 15d | 100% | TRUE | TRUE | TRUE
RG4020 | RT.B.4 | 5.1 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | TRUE | TRUE | TRUE
RG4024 | RT.B.4 | 5.1.1 | MILESTONE: Review meeting cadence, attendees and agenda established | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | MILESTONE: Review meeting cadence, attendees and agenda established | 2015-07-13 | 2015-07-24 | 10d | 100% | TRUE | TRUE | TRUE
RG4021 | RT.B.4 | 5.1.1.1 | Identify review meeting attendees | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA | [6 empty] | Identify review meeting attendees | 2015-07-13 | 2015-07-24 | 10d | 100% | TRUE | TRUE | TRUE
RG4022 | RT.B.4 | 5.1.1.2 | Establish review meeting calendar | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA |  |  |  |  | Documentation Required |  | Establish review meeting calendar | 2015-07-13 | 2015-07-24 | 10d | 100% | TRUE | TRUE | TRUE
RG4027 | RT.B.4 | 5.1.1.3 | Define review meeting agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | SHUSA |  |  |  |  | Documentation Required |  | Define review meeting agenda | 2015-07-13 | 2015-07-24 | 10d | 100% | TRUE | TRUE | TRUE
RG3347 | RT.B.4 | 5.2 | DELIVERABLE: Review and select existing reports for review meeting | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | DELIVERABLE: Review and select existing reports for review meeting | 2015-07-20 | 2015-07-31 | 10d | 100% | TRUE | TRUE | TRUE
RG4025 | RT.B.4 | 5.2.1 | MILESTONE: Existing reports reviewed and selected | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | MILESTONE: Existing reports reviewed and selected | 2015-07-20 | 2015-07-31 | 10d | 100% | TRUE | TRUE | TRUE
RG3344 | RT.B.4 | 5.2.1.1 | Review existing risk reports | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA | [6 empty] | Review existing risk reports | 2015-07-20 | 2015-07-31 | 10d | 100% | TRUE | TRUE | TRUE
RG4028 | RT.B.4 | 5.2.1.2 | Selecty existing reports | 2015-07-20 | 2015-07-31 | 10d | 100% | SHUSA | [6 empty] | Selecty existing reports | 2015-07-20 | 2015-07-31 | 10d | 100% | TRUE | TRUE | TRUE
RG4023 | RT.B.4 | 5.2.1.3 | Implement Routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA | [6 empty] | Implement Routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 100% | TRUE | TRUE | TRUE
RG4194 | RT.B.5 | 6 | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2015-10-05 | 2016-01-08 | 70d | 64% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  |  |  | Need further discussion to finalize |  | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2015-10-05 | 2016-01-08 | 70d | 0% | TRUE | TRUE | TRUE
RG3174 | RT.B.11 | 6.1 | Assess existing Risk Management Performance Scorecards and identify gaps | 2015-06-15 | 2015-12-18 | 135d | 64% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  | B. Gunn/C. Briongos |  |  | Assess existing Risk Management Performance Scorecards and identify gaps | 2015-06-15 | 2015-12-18 | 135d | 64% | TRUE | TRUE | TRUE
RG3144 | RT.B.11 | 6.1.1 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  | B. Gunn/C. Briongos | included from legacy CEP plan; justified / coordinated with the (round 2) enhancements below |  | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | TRUE | TRUE | TRUE
RG3145 | RT.B.11 | 6.1.1.1 | MILESTONE: Quick Win Enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  |  |  | MILESTONE: Quick Win Enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-07-31 | 35d | 100% | TRUE | TRUE | TRUE
RG3146 | RT.B.11 | 6.1.1.1.1 | Submit 1st Submission of Year to Date Figures from Data Feed Owners | 2015-06-15 | 2015-07-09 | 19d | 100% | SHUSA | [6 empty] | Submit 1st Submission of Year to Date Figures from Data Feed Owners | 2015-06-15 | 2015-07-09 | 19d | 100% | TRUE | TRUE | TRUE
RG3147 | RT.B.11 | 6.1.1.1.2 | Create Mid Year RMPS to Share with Managers | 2015-07-10 | 2015-07-31 | 16d | 100% | SHUSA |  |  |  |  | Documentation Required |  | Create Mid Year RMPS to Share with Managers | 2015-07-10 | 2015-07-31 | 16d | 100% | TRUE | TRUE | TRUE
RG3171 | RT.B.11 | 6.1.1.1.3 | Quick Win Enhancements to existing Risk Management Performance Scorecards Complete | 2015-07-31 | 2015-07-31 | 0d | 100% | SHUSA | [6 empty] | Quick Win Enhancements to existing Risk Management Performance Scorecards Complete | 2015-07-31 | 2015-07-31 | 0d | 100% | TRUE | TRUE | TRUE
RG2467 | RT.B.11 | 6.1.2 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  | B. Gunn/C. Briongos | need to justify / coordinate with the quick win enhancements above |  | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | TRUE | TRUE | TRUE
RG2837 | RT.B.11 | 6.1.2.1 | MILESTONE: Enhance Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight |  |  |  |  | MILESTONE: Enhance Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | TRUE | TRUE | TRUE
RG2468 | RT.B.11 | 6.1.2.1.1 | Perform high level assessment and remediation of performance scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | SHUSA | [6 empty] | Perform high level assessment and remediation of performance scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | TRUE | TRUE | TRUE
RG2469 | RT.B.11 | 6.1.2.1.2 | Assessment and Remediation of Performance Scorecards Complete | 2015-11-27 | 2015-11-27 | 0d | 0% | SHUSA | [6 empty] | Assessment and Remediation of Performance Scorecards Complete | 2015-11-27 | 2015-11-27 | 0d | 0% | TRUE | TRUE | TRUE
RG2478 | RT.B.6 | 7 | Design Operating Model across all risk types aligned with principles of 3 LOD, develop rollout plans and implement | 2015-06-22 | 2016-10-14 | 345d? | 13% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | RT.Governance and Organization.Y1_180_Design and approve enhanced frameworks across all risk types |  | B. Gunn | Ops Risk | Outgoing
RG4216 | RT.B.6 | 7.1 | Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | RT.Governance and Organization.Y1_181_Perform a talent review and assessment of key risk staff and develop a strategy to address gaps in hiring training leadership programs |  | B. Gunn |  |  | Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-08-03 | 2015-10-02 | 45d | 33% | TRUE | TRUE | TRUE
RG4217 | RT.B.6 | 7.1.1 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | RT.Governance and Organization.Y1_181_Perform a talent review and assessment of key risk staff and develop a strategy to address gaps in hiring training leadership programs |  | B. Gunn |  |  | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 2015-08-03 | 2015-10-02 | 45d | 33% | TRUE | TRUE | TRUE
RG4218 | RT.B.6 | 7.1.1.1 | MILESTONE: Risk organizational structure charts and subsidiary reporting schemes submitted to and approved by CRO (SHUSA) | 2015-08-03 | 2015-10-02 | 45d | 33% | SHUSA | RT.Governance and Organization.Y1_178_Strengthen Board and management oversight | RT.Governance and Organization.Y1_181_Perform a talent review and assessment of key risk staff and develop a strategy to address gaps in hiring training leadership programs |  | B. Elena | Ops Risk | Outgoing | MILESTONE: Risk organizational structure charts and subsidiary reporting schemes submitted to and approved by CRO (SHUSA) | 2015-08-03 | 2015-10-02 | 45d | 33% | TRUE | TRUE | TRUE
RG4219 | RT.B.6 | 7.1.1.1.1 | Formalize subsidiary CRO reporting lines, socialize and refine solution (SHUSA) | 2015-08-03 | 2015-08-14 | 10d | 50% | SHUSA |  |  |  | B. Elena |  |  | Formalize subsidiary CRO reporting lines, socialize and refine solution (SHUSA) | 2015-08-03 | 2015-08-14 | 10d | 50% | TRUE | TRUE | TRUE
RG4220 | RT.B.6 | 7.1.1.1.2 | Define implications of reporting lines (for Performance assessment and hiring/firing authority) (SHUSA) | 2015-08-10 | 2015-08-21 | 10d | 100% | SHUSA |  |  |  | B. Elena |  |  | Define implications of reporting lines (for Performance assessment and hiring/firing authority) (SHUSA) | 2015-08-10 | 2015-08-21 | 10d | 100% | TRUE | TRUE | TRUE
RG4221 | RT.B.6 | 7.1.1.1.3 | Design 1st LoD Risk organization leadership structure including the role of RCO (SHUSA) | 2015-08-03 | 2015-09-04 | 25d | 0% | SHUSA |  |  |  | B. Elena | Documentation Required; Uncertain. Dependent on follow up BCO meeting with Scott |  | Design 1st LoD Risk organization leadership structure including the role of RCO (SHUSA) | 2015-08-03 | 2015-09-04 | 25d | 0% | TRUE | TRUE | TRUE
RG4222 | RT.B.6 | 7.1.1.1.4 | Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 2015-10-02 | 2015-10-02 | 0d | 0% | SHUSA | [6 empty] | Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 2015-10-02 | 2015-10-02 | 0d | 0% | TRUE | TRUE | TRUE
[6 empty] | 20d | 100% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | Design Operating Model across all risk types aligned with principles of 3 LOD, develop rollout plans and implement | 2015-06-22 | 2017-05-02 | 487d | 6% | FALSE | TRUE | FALSE
RG2479 | RT.B.6 | 7.2 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 2015-06-22 | 2015-07-17 | 110d? | 31% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 2015-06-22 | 2015-07-17 | 20d | 100% | TRUE | TRUE | TRUE
RG2480 | RT.B.6 | 7.3 | DELIVERABLE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 110d? | 31% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | DELIVERABLE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 110d? | 29% | TRUE | TRUE | TRUE
RG2839 | RT.B.6 | 7.3.1 | MILESTONE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 11d | 0% | SHUSA |  |  |  | B. Gunn |  |  | MILESTONE: Design detailed operating model and implementation plans for all risk types ex. Op risk | 2015-07-13 | 2015-12-11 | 110d? | 29% | TRUE | TRUE | TRUE
RG2482 | RT.B.6 | 7.3.1.1 | Strengthening Second LOD reporting: Determine high level subsidiary CRO reporting lines | 2015-07-13 | 2015-07-27 | 6d | 0% | SHUSA |  |  |  | B. Gunn |  |  | Strengthening Second LOD reporting: Determine high level subsidiary CRO reporting lines | 2015-07-13 | 2015-07-27 | 11d | 0% | TRUE | TRUE | TRUE
RG2483 | RT.B.6 | 7.3.1.2 | Strengthening Second LOD reporting: Review and approval | 2015-07-27 | 2015-08-03 | 11d | 100% | SHUSA | [6 empty] | Strengthening Second LOD reporting: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 0% | TRUE | TRUE | TRUE
RG2484 | RT.B.6 | 7.3.1.3 | Designing the Business Control Officers: Initial high level design | 2015-07-13 | 2015-07-27 | 11d | 100% | SHUSA | [6 empty] | Designing the Business Control Officers: Initial high level design | 2015-07-13 | 2015-07-27 | 11d | 100% | TRUE | TRUE | TRUE
RG3186 | RT.B.6 | 7.3.1.4 | Designing the Business Control Officers: Detailed roles and responsibilities design | 2015-07-20 | 2015-08-03 | 6d | 100% | SHUSA | [6 empty] | Designing the Business Control Officers: Detailed roles and responsibilities design | 2015-07-20 | 2015-08-03 | 11d | 100% | TRUE | TRUE | TRUE
RG3187 | RT.B.6 | 7.3.1.5 | Designing the Business Control Officers: Review and approval | 2015-07-27 | 2015-08-03 | 11d | 100% | SHUSA | [6 empty] | Designing the Business Control Officers: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 100% | TRUE | TRUE | TRUE
RG3188 | RT.B.6 | 7.3.1.6 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 16d | 100% | SHUSA | [6 empty] | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100% | TRUE | TRUE | TRUE
RG3189 | RT.B.6 | 7.3.1.7 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 11d | 100% | SHUSA | [6 empty] | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100% | TRUE | TRUE | TRUE
RG2485 | RT.B.6 | 7.3.1.8 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 6d | 95% | SHUSA |  |  |  | M. Tony | Documentation Required; In progress, waiting for finalized stakeholder from Risk MI |  | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 11d | 100% | TRUE | TRUE | TRUE
RG2840 | RT.B.6 | 7.3.1.9 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 11d | 100% | SHUSA |  |  |  | M. Tony |  |  | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 95% | TRUE | TRUE | TRUE
RG4029 | RT.B.6 | 7.3.1.10 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 16d | 100% | SHUSA |  |  |  | M. Tony |  |  | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 100% | TRUE | TRUE | TRUE
RG4030 | RT.B.6 | 7.3.1.11 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 21d | 50% | SHUSA |  |  |  | M. Tony | ERM, compliance, and risk MI have not been reviewed |  | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 100% | TRUE | TRUE | TRUE
RG4031 | RT.B.6 | 7.3.1.12 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 16d | 25% | SHUSA |  |  |  | M. Tony | Documentation Required; ERM, compliance, and risk MI have not been reviewed |  | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 21d | 50% | TRUE | TRUE | TRUE
RG3190 | RT.B.6 | 7.3.1.13 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 21d | 75% | SHUSA |  |  |  | M. Tony |  |  | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 16d | 25% | TRUE | TRUE | TRUE
RG3191 | RT.B.6 | 7.3.1.14 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 25% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 75% | TRUE | TRUE | TRUE
RG3193 | RT.B.6 | 7.3.1.15 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 25% | TRUE | TRUE | TRUE
RG2841 | RT.B.6 | 7.3.1.16 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 31d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 21d | 0% | TRUE | TRUE | TRUE
RG2491 | RT.B.6 | 7.3.1.17 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 21d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 31d | 0% | TRUE | TRUE | TRUE
RG2492 | RT.B.6 | 7.3.1.18 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | SHUSA |  |  |  | M. Tony | Documentation Required |  | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | TRUE | TRUE | TRUE
RG3194 | RT.B.6 | 7.3.1.19 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 50d? | 0% | SHUSA | [6 empty] | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 21d | 0% | TRUE | TRUE | TRUE
RG4193 | RT.B.6 | 7.3.1.20 | Review frameworks and policies to ensure alignment to TOM design and clear articulation of 3LoD design | 2015-10-05 | 2015-12-11 | 21d | 0% | SHUSA | [6 empty] | Review frameworks and policies to ensure alignment to TOM design and clear articulation of 3LoD design | 2015-10-05 | 2015-12-11 | 50d? | 0% | TRUE | TRUE | TRUE
RG3195 | RT.B.6 | 7.3.1.21 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 16d | 0% | SHUSA | [6 empty] | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 21d | 0% | TRUE | TRUE | TRUE
RG3196 | RT.B.6 | 7.3.1.22 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 21d | 0% | SHUSA | [6 empty] | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 16d | 0% | TRUE | TRUE | TRUE
RG3197 | RT.B.6 | 7.3.1.23 | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 16d | 0% | SHUSA | [6 empty] | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 21d | 0% | TRUE | TRUE | TRUE
RG2495 | RT.B.6 | 7.3.1.24 | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 15d | 0% | SHUSA |  |  |  |  | Documentation Required |  | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 16d | 0% | TRUE | TRUE | TRUE
RG2842 | RT.B.6 | 7.3.1.25 | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 0d | 0% | SHUSA |  |  |  |  | Estimate timeline is 9 months subject to change based on final plan |  | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 15d | 0% | TRUE | TRUE | TRUE
RG2496 | RT.B.6 | 7.3.1.26 | Operating model and implementation plans for all risk types ex. Op Risk complete | 2015-12-11 | 2015-12-11 | 110d | 27% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | Operating model and implementation plans for all risk types ex. Op Risk complete | 2015-12-11 | 2015-12-11 | 0d | 0% | TRUE | TRUE | TRUE
RG2497 | RT.B.6 | 7.4 | DELIVERABLE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 110d | 27% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | DELIVERABLE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 110d | 21% | TRUE | TRUE | TRUE
RG2499 | RT.B.6 | 7.4.1 | MILESTONE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 11d | 100% | SHUSA | [6 empty] | MILESTONE: Design detailed operating model and implementation plans for Op Risk | 2015-07-13 | 2015-12-11 | 110d | 21% | TRUE | TRUE | TRUE
RG2843 | RT.B.6 | 7.4.1.1 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 16d | 100% | SHUSA | [6 empty] | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100% | TRUE | TRUE | TRUE
RG2501 | RT.B.6 | 7.4.1.2 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 9d | 100% | SHUSA |  |  |  | M. Tony |  |  | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100% | TRUE | TRUE | TRUE
RG2502 | RT.B.6 | 7.4.1.3 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 6d | 95% | SHUSA |  |  |  | M. Tony | Documentation Required; In progress, meeting on Thur. to confirm minor changes |  | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 9d | 100% | TRUE | TRUE | TRUE
RG2504 | RT.B.6 | 7.4.1.4 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 11d | 100% | SHUSA |  |  |  | M. Tony |  |  | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 95% | TRUE | TRUE | TRUE
RG3202 | RT.B.6 | 7.4.1.5 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 16d | 100% | SHUSA |  |  |  | M. Tony |  |  | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 100% | TRUE | TRUE | TRUE
RG3203 | RT.B.6 | 7.4.1.6 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 21d | 50% | SHUSA |  |  |  | M. Tony |  |  | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 100% | TRUE | TRUE | TRUE
RG3204 | RT.B.6 | 7.4.1.7 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 16d | 0% | SHUSA |  |  |  | M. Tony | Documentation Required |  | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-09-07 | 21d | 50% | TRUE | TRUE | TRUE
RG3205 | RT.B.6 | 7.4.1.8 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 21d | 0% | SHUSA |  |  |  | M. Tony |  |  | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-09-07 | 16d | 0% | TRUE | TRUE | TRUE
RG2505 | RT.B.6 | 7.4.1.9 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 50% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-08-17 | 2015-09-14 | 21d | 0% | TRUE | TRUE | TRUE
RG2506 | RT.B.6 | 7.4.1.10 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-31 | 2015-09-28 | 21d | 50% | TRUE | TRUE | TRUE
RG2509 | RT.B.6 | 7.4.1.11 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 31d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 21d | 0% | TRUE | TRUE | TRUE
RG3206 | RT.B.6 | 7.4.1.12 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 21d | 0% | SHUSA |  |  |  | M. Tony |  |  | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-14 | 2015-10-26 | 31d | 0% | TRUE | TRUE | TRUE
RG3207 | RT.B.6 | 7.4.1.13 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | SHUSA |  |  |  |  | Documentation Required |  | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-28 | 2015-10-26 | 21d | 0% | TRUE | TRUE | TRUE
RG3209 | RT.B.6 | 7.4.1.14 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 21d | 0% | SHUSA | [6 empty] | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-11-09 | 21d | 0% | TRUE | TRUE | TRUE
RG3336 | RT.B.6 | 7.4.1.15 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 16d | 0% | SHUSA | [6 empty] | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 21d | 0% | TRUE | TRUE | TRUE
RG2569 | RT.B.6 | 7.4.1.16 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 21d | 0% | SHUSA | [6 empty] | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 16d | 0% | TRUE | TRUE | TRUE
RG2845 | RT.B.6 | 7.4.1.17 | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 16d | 0% | SHUSA | [6 empty] | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 21d | 0% | TRUE | TRUE | TRUE
RG2510 | RT.B.6 | 7.4.1.18 | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 15d | 0% | SHUSA |  |  |  |  | Documentation Required |  | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 16d | 0% | TRUE | TRUE | TRUE
RG2570 | RT.B.6 | 7.4.1.19 | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 0d | 0% | SHUSA | [6 empty] | Implementation planning: Obtain approval for implementation roadmap | 2015-11-23 | 2015-12-11 | 15d | 0% | TRUE | TRUE | TRUE
RG2573 | RT.B.6 | 7.4.1.20 | Operating model and implementation plans for Op Risk complete | 2015-12-11 | 2015-12-11 | 175d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | Operating model and implementation plans for Op Risk complete | 2015-12-11 | 2015-12-11 | 0d | 0% | TRUE | TRUE | TRUE
RG2846 | RT.B.6 | 7.5 | Implement the redesigned Operating Model for all the risks | 2015-12-14 | 2016-08-12 | 175d | 0% | SHUSA | [6 empty] | Implement the redesigned Operating Model for all the risks | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4195 | RT.B.6 | 7.5.1 | Implement redesigned Operating Model for SHUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | SBNA | [6 empty] | Implement redesigned Operating Model for SHUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4196 | RT.B.6 | 7.5.2 | Implement redesigned Operating Model for SBNA | 2015-12-14 | 2016-08-12 | 175d | 0% | SCUSA | [6 empty] | Implement redesigned Operating Model for SBNA | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4197 | RT.B.6 | 7.5.3 | Implement redesigned Operating Model for SCUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | Banco Santander Puerto Rico | [6 empty] | Implement redesigned Operating Model for SCUSA | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4198 | RT.B.6 | 7.5.4 | Implement redesigned Operating Model for Puerto Rico | 2015-12-14 | 2016-08-12 | 175d | 0% | Banco Santander International (BSI Miami) | [6 empty] | Implement redesigned Operating Model for Puerto Rico | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4199 | RT.B.6 | 7.5.5 | Implement redesigned Operating Model for Miami | 2015-12-14 | 2016-08-12 | 175d | 0% | Santander Investment Securities (SIS NY) | [6 empty] | Implement redesigned Operating Model for Miami | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG4200 | RT.B.6 | 7.5.6 | Implement redesigned Operating Model for NY | 2015-12-14 | 2016-08-12 | 45d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | Implement redesigned Operating Model for NY | 2015-12-14 | 2016-08-12 | 175d | 0% | TRUE | TRUE | TRUE
RG2511 | RT.B.6 | 7.6 | DELIVERABLE: Post Implementation Review | 2016-08-15 | 2016-10-14 | 45d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | DELIVERABLE: Post Implementation Review | 2016-08-15 | 2016-10-14 | 45d | 0% | TRUE | TRUE | TRUE
RG2571 | RT.B.6 | 7.6.1 | MILESTONE: Post Implementation Review Conducted | 2016-08-15 | 2016-10-14 | 45d | 0% | SHUSA | [6 empty] | MILESTONE: Post Implementation Review Conducted | 2016-08-15 | 2016-10-14 | 45d | 0% | TRUE | TRUE | TRUE
RG2574 | RT.B.6 | 7.6.1.1 | Post Implementation Review | 2016-08-15 | 2016-10-14 | 0d | 0% | SHUSA | [6 empty] | Post Implementation Review | 2016-08-15 | 2016-10-14 | 45d | 0% | TRUE | TRUE | TRUE
RG2847 | RT.B.6 | 7.6.1.2 | MILESTONE: Post Implementation Review Conducted | 2016-10-14 | 2016-10-14 | 45d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries |  |  | B. Gunn |  |  | MILESTONE: Post Implementation Review Conducted | 2016-10-14 | 2016-10-14 | 0d | 0% | TRUE | TRUE | TRUE
RG4034 | RT.B.9 | 8 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-02-01 | 2016-04-01 | 45d | 0% | SHUSA | RT.Governance and Organization.Y1_179_Redesign and begin roll-out of the operating model for SHUSA and its subsidiaries | [5 empty] | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2016-02-01 | 2016-04-01 | 45d | 0% | TRUE | TRUE | TRUE
RG2577 | RT.B.9 | 8.1 | MILESTONE: Strong and Desired Risk Culture Defined | 2016-02-01 | 2016-04-01 | 5d | 0% | SHUSA | [6 empty] | MILESTONE: Strong and Desired Risk Culture Defined | 2016-02-01 | 2016-04-01 | 45d | 0% | TRUE | TRUE | TRUE
RG3102 | RT.B.9 | 8.1.1 | Determine the survey population and tailor survey as needed (1 week) | 2016-02-01 | 2016-02-05 | 15d | 0% | SHUSA | [6 empty] | Determine the survey population and tailor survey as needed (1 week) | 2016-02-01 | 2016-02-05 | 5d | 0% | TRUE | TRUE | TRUE
RG2515 | RT.B.9 | 8.1.2 | Deploy culture survey and collect responses (2-3 week) | 2016-02-01 | 2016-02-19 | 15d | 0% | SHUSA |  |  |  |  | Documentation Required |  | Deploy culture survey and collect responses (2-3 week) | 2016-02-01 | 2016-02-19 | 15d | 0% | TRUE | TRUE | TRUE
RG2851 | RT.B.9 | 8.1.3 | Aggregate and analyze survey results (2-3 weeks) | 2016-02-22 | 2016-03-11 | 15d | 0% | SHUSA | [6 empty] | Aggregate and analyze survey results (2-3 weeks) | 2016-02-22 | 2016-03-11 | 15d | 0% | TRUE | TRUE | TRUE
RG2517 | RT.B.9 | 8.1.4 | Conduct 3-4 targeted focus groups or workshops to refine and validate the insights (1-2 weeks) - goes in parallel with 3. | 2016-02-29 | 2016-03-18 | 10d | 0% | SHUSA | [6 empty] | Conduct 3-4 targeted focus groups or workshops to refine and validate the insights (1-2 weeks) - goes in parallel with 3. | 2016-02-29 | 2016-03-18 | 15d | 0% | TRUE | TRUE | TRUE
RG2518 | RT.B.9 | 8.1.5 | Review findings, document current state risk culture and priritize focus areas (1 week) | 2016-03-21 | 2016-04-01 | 0d | 0% | SHUSA | [6 empty] | Review findings, document current state risk culture and priritize focus areas (1 week) | 2016-03-21 | 2016-04-01 | 10d | 0% | TRUE | TRUE | TRUE
RG2519 | RT.B.9 | 8.1.6 | MILESTONE: Strong and Desired Risk Culture Defined | 2016-04-01 | 2016-04-01 | 312d | 0% | SHUSA | RT.Governance and Organization | [5 empty] | MILESTONE: Strong and Desired Risk Culture Defined | 2016-04-01 | 2016-04-01 | 0d | 0% | TRUE | TRUE | TRUE
RG2520 |  | 9 | Long Term Planning Package | 2016-01-25 | 2017-04-04 | 197d? | 0% | SHUSA | RT.Governance and Organization.Y2_44_Roll out performance assessment and compensation frameworks across the organization |  |  | B. Gunn/C. Briongos |  |  | Long Term Planning Package | 2016-01-25 | 2017-04-04 | 312d? | 0% | TRUE | TRUE | TRUE
RG2521 | RT.B.12 | 10 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2016-04-01 | 2017-01-02 | 65d | 0% | SHUSA | RT.Governance and Organization.Y2_44_Roll out performance assessment and compensation frameworks across the organization | [5 empty] | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2016-04-01 | 2017-01-02 | 197d? | 0% | TRUE | TRUE | TRUE
RG2850 | RT.B.12 | 10.1 | MILESTONE: Design risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | MILESTONE: Design risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2523 | RT.B.12 | 10.1.1 | Benchmark of risk-based compensation practices in the industry | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | Benchmark of risk-based compensation practices in the industry | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2524 | RT.B.12 | 10.1.2 | Risk-based compensation proposals and refinement with stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | Risk-based compensation proposals and refinement with stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2525 | RT.B.12 | 10.1.3 | Impact analysis of new frameworks on compensation levels | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | Impact analysis of new frameworks on compensation levels | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2526 | RT.B.12 | 10.1.4 | Formalization of new risk-based compensation framework | 2016-04-01 | 2016-06-30 | 0d | 0% | SHUSA | [6 empty] | Formalization of new risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2849 | RT.B.12 | 10.1.5 | Risk-based compensation structure formalized | 2016-06-30 | 2016-06-30 | 131d? | 0% | SHUSA | RT.Governance and Organization.Y2_44_Roll out performance assessment and compensation frameworks across the organization | [5 empty] | Risk-based compensation structure formalized | 2016-06-30 | 2016-06-30 | 0d | 0% | TRUE | TRUE | TRUE
RG2528 | RT.B.12 | 10.2 | MILESTONE: Communication and stakeholder engagement | 2016-04-01 | 2016-09-30 | 65d? | 0% | SHUSA | [6 empty] | MILESTONE: Communication and stakeholder engagement | 2016-04-01 | 2016-09-30 | 131d? | 0% | TRUE | TRUE | TRUE
RG2529 | RT.B.12 | 10.2.1 | Design of communication plan | 2016-04-01 | 2016-06-30 | 65d? | 0% | SHUSA | [6 empty] | Design of communication plan | 2016-04-01 | 2016-06-30 | 65d? | 0% | TRUE | TRUE | TRUE
RG2530 | RT.B.12 | 10.2.2 | Development of communication materials | 2016-04-01 | 2016-06-30 | 67d? | 0% | SHUSA | [6 empty] | Development of communication materials | 2016-04-01 | 2016-06-30 | 65d? | 0% | TRUE | TRUE | TRUE
RG2531 | RT.B.12 | 10.2.3 | Execution of communication plan | 2016-06-30 | 2016-09-30 | 0d | 0% | SHUSA | [6 empty] | Execution of communication plan | 2016-06-30 | 2016-09-30 | 67d? | 0% | TRUE | TRUE | TRUE
RG2532 | RT.B.12 | 10.2.4 | Stakeholder communication complete | 2016-09-30 | 2016-09-30 | 132d? | 0% | SHUSA | RT.Governance and Organization.Y2_44_Roll out performance assessment and compensation frameworks across the organization | [5 empty] | Stakeholder communication complete | 2016-09-30 | 2016-09-30 | 0d | 0% | TRUE | TRUE | TRUE
RG2854 | RT.B.12 | 10.3 | MILESTONE: Updates to performance assessment templates | 2016-07-01 | 2017-01-02 | 66d? | 0% | SHUSA | [6 empty] | MILESTONE: Updates to performance assessment templates | 2016-07-01 | 2017-01-02 | 132d? | 0% | TRUE | TRUE | TRUE
RG2534 | RT.B.12 | 10.3.1 | Inventory of performance assessment templates at SHUSA, SBNA and SCUSA | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA | [6 empty] | Inventory of performance assessment templates at SHUSA, SBNA and SCUSA | 2016-07-01 | 2016-09-30 | 66d? | 0% | TRUE | TRUE | TRUE
RG2535 | RT.B.12 | 10.3.2 | Update of template in accordance with risk-based compensation framework | 2016-07-01 | 2016-09-30 | 67d? | 0% | SHUSA | [6 empty] | Update of template in accordance with risk-based compensation framework | 2016-07-01 | 2016-09-30 | 66d? | 0% | TRUE | TRUE | TRUE
RG2536 | RT.B.12 | 10.3.3 | Socialization, training of stakeholders and roll-out of new templates | 2016-09-30 | 2017-01-02 | 0d | 0% | SHUSA | [6 empty] | Socialization, training of stakeholders and roll-out of new templates | 2016-09-30 | 2017-01-02 | 67d? | 0% | TRUE | TRUE | TRUE
RG2537 | RT.B.12 | 10.3.4 | Performance assessment templates updated | 2016-12-31 | 2016-12-31 |  | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model |  |  | B. Gunn |  |  | Performance assessment templates updated | 2016-12-31 | 2016-12-31 | 0d | 0% | TRUE | TRUE | TRUE
RG2538 | RT.B.8 | 11 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  | 65d | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model | [5 empty] | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | TRUE | TRUE | TRUE
RG2853 | RT.B.8 | 11.1 | MILESTONE: Communications to emphasize progress being made / share best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA | [6 empty] | MILESTONE: Communications to emphasize progress being made / share best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | TRUE | TRUE | TRUE
RG2540 | RT.B.8 | 11.1.1 | Assessment of progress being made & best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA | [6 empty] | Assessment of progress being made & best practices | 2016-01-25 | 2016-04-22 | 65d | 0% | TRUE | TRUE | TRUE
RG2541 | RT.B.8 | 11.1.2 | Design of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA | [6 empty] | Design of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0% | TRUE | TRUE | TRUE
RG2542 | RT.B.8 | 11.1.3 | Development of communications materials | 2016-01-25 | 2016-04-22 | 65d | 0% | SHUSA | [6 empty] | Development of communications materials | 2016-01-25 | 2016-04-22 | 65d | 0% | TRUE | TRUE | TRUE
RG2852 | RT.B.8 | 11.1.4 | Delivery of communication plan | 2016-01-25 | 2016-04-22 | 0d | 0% | SHUSA | [6 empty] | Delivery of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0% | TRUE | TRUE | TRUE
RG2544 | RT.B.8 | 11.1.5 | Progress communications delivered | 2016-04-22 | 2016-04-22 | 65d | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model | [5 empty] | Progress communications delivered | 2016-04-22 | 2016-04-22 | 0d | 0% | TRUE | TRUE | TRUE
RG2545 | RT.B.8 | 11.2 | MILESTONE: Convey organizational changes to the enterprise | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | MILESTONE: Convey organizational changes to the enterprise | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2546 | RT.B.8 | 11.2.1 | Development of materials | 2016-04-01 | 2016-06-30 | 65d | 0% | SHUSA | [6 empty] | Development of materials | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2547 | RT.B.8 | 11.2.2 | Delivery of communication to stakeholders | 2016-04-01 | 2016-06-30 | 0d | 0% | SHUSA | [6 empty] | Delivery of communication to stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0% | TRUE | TRUE | TRUE
RG2548 | RT.B.8 | 11.2.3 | Organizational changes communicated to enterprise | 2016-06-30 | 2016-06-30 | 132d | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model | [5 empty] | Organizational changes communicated to enterprise | 2016-06-30 | 2016-06-30 | 0d | 0% | TRUE | TRUE | TRUE
RG2549 | RT.B.8 | 11.3 | MILESTONE: Enterprise-wide training and development of job descriptions with explicit focus on three lines of defense | 2016-07-01 | 2017-01-02 | 66d? | 0% | SHUSA | [6 empty] | MILESTONE: Enterprise-wide training and development of job descriptions with explicit focus on three lines of defense | 2016-07-01 | 2017-01-02 | 132d | 0% | TRUE | TRUE | TRUE
RG2550 | RT.B.8 | 11.3.1 | Design of training curriculum & idenfification of key recepients as a result of post-implementation reviews | 2016-07-01 | 2016-09-30 | 66d? | 0% | SHUSA | [6 empty] | Design of training curriculum & idenfification of key recepients as a result of post-implementation reviews | 2016-07-01 | 2016-09-30 | 66d? | 0% | TRUE | TRUE | TRUE
RG2857 | RT.B.8 | 11.3.2 | Development of training materials | 2016-07-01 | 2016-09-30 | 67d? | 0% | SHUSA | [6 empty] | Development of training materials | 2016-07-01 | 2016-09-30 | 66d? | 0% | TRUE | TRUE | TRUE
RG2552 | RT.B.8 | 11.3.3 | Delivery of training to priority recipients | 2016-09-30 | 2017-01-02 | 66d? | 0% | SHUSA | [6 empty] | Delivery of training to priority recipients | 2016-09-30 | 2017-01-02 | 67d? | 0% | TRUE | TRUE | TRUE
RG2553 | RT.B.8 | 11.3.4 | Identification of key functions requiring job description updates | 2016-07-01 | 2016-09-30 | 67d? | 0% | SHUSA | [6 empty] | Identification of key functions requiring job description updates | 2016-07-01 | 2016-09-30 | 66d? | 0% | TRUE | TRUE | TRUE
RG2554 | RT.B.8 | 11.3.5 | Development of job descriptions with explicit focus on three lines of defense | 2016-09-30 | 2017-01-02 | 0d | 0% | SHUSA | [6 empty] | Development of job descriptions with explicit focus on three lines of defense | 2016-09-30 | 2017-01-02 | 67d? | 0% | TRUE | TRUE | TRUE
RG2856 | RT.B.8 | 11.3.6 | Job descriptions complete and enterprise-wide training delivered | 2016-12-31 | 2016-12-31 | 198d? | 0% | SHUSA | RT.Governance and Organization.Y2_46_Develop talent management mechanisms |  |  | B. Gunn/C. Briongos |  |  | Job descriptions complete and enterprise-wide training delivered | 2016-12-31 | 2016-12-31 | 0d | 0% | TRUE | TRUE | TRUE
RG2556 | RT.B.13 | 12 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2016-07-01 | 2017-04-04 | 66d | 0% | SHUSA | RT.Governance and Organization.Y2_46_Develop talent management mechanisms | [5 empty] | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2016-07-01 | 2017-04-04 | 198d? | 0% | TRUE | TRUE | TRUE
RG2557 | RT.B.13 | 12.1 | MILESTONE: Design recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA | [6 empty] | MILESTONE: Design recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG2558 | RT.B.13 | 12.1.1 | Diagnostic of retention challenges | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA | [6 empty] | Diagnostic of retention challenges | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG2559 | RT.B.13 | 12.1.2 | Design of new possible retention mechanisms | 2016-07-01 | 2016-09-30 | 0d | 0% | SHUSA | [6 empty] | Design of new possible retention mechanisms | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG2560 | RT.B.13 | 12.1.3 | Milestone: Design of new possible retention mechanisms complete | 2016-09-30 | 2016-09-30 | 132d? | 0% | SHUSA | RT.Governance and Organization.Y2_46_Develop talent management mechanisms | [5 empty] | Milestone: Design of new possible retention mechanisms complete | 2016-09-30 | 2016-09-30 | 0d | 0% | TRUE | TRUE | TRUE
RG2855 | RT.B.13 | 12.2 | MILESTONE: Action plans for necessary remediation efforts | 2016-10-03 | 2017-04-04 | 68d? | 0% | SHUSA | [6 empty] | MILESTONE: Action plans for necessary remediation efforts | 2016-10-03 | 2017-04-04 | 132d? | 0% | TRUE | TRUE | TRUE
RG2562 | RT.B.13 | 12.2.1 | Selection of key remediation initiatives with key stakeholders | 2016-10-03 | 2017-01-04 | 68d? | 0% | SHUSA | [6 empty] | Selection of key remediation initiatives with key stakeholders | 2016-10-03 | 2017-01-04 | 68d? | 0% | TRUE | TRUE | TRUE
RG2563 | RT.B.13 | 12.2.2 | Planning of initiatives between SHUSA and its subsidiaries | 2016-10-03 | 2017-01-04 | 68d? | 0% | SHUSA | [6 empty] | Planning of initiatives between SHUSA and its subsidiaries | 2016-10-03 | 2017-01-04 | 68d? | 0% | TRUE | TRUE | TRUE
RG2564 | RT.B.13 | 12.2.3 | Rollout of initiatives at SHUSA | 2016-10-03 | 2017-01-04 | 67d | 0% | SHUSA | [6 empty] | Rollout of initiatives at SHUSA | 2016-10-03 | 2017-01-04 | 68d? | 0% | TRUE | TRUE | TRUE
RG4185 | RT.B.13 | 12.2.4 | Rollout of initiatives at other subsidiaries | 2017-01-02 | 2017-04-04 | 0d | 0% | SHUSA | [6 empty] | Rollout of initiatives at other subsidiaries | 2017-01-02 | 2017-04-04 | 67d | 0% | TRUE | TRUE | TRUE
RG4186 | RT.B.13 | 12.2.5 | Recruitment and retention intiatives introduced throughout enterprise | 2017-04-04 | 2017-04-04 | 66d | 0% | SHUSA | RT.Governance and Organization.Y2_45_Complete roll-out of the new operating model |  |  | B. Gunn |  |  | Recruitment and retention intiatives introduced throughout enterprise | 2017-04-04 | 2017-04-04 | 0d | 0% | TRUE | TRUE | TRUE
RG4187 | RT.B.10 | 12.3 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA | [6 empty] | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG4188 | RT.B.10 | 12.3.1 | MILESTONE: Create multi-year plan that describes interventions | 2016-07-01 | 2016-09-30 | 66d | 0% | SHUSA | [6 empty] | MILESTONE: Create multi-year plan that describes interventions | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG4189 | RT.B.10 | 12.3.2 | MILESTONE: Syndicate plan with key stakeholders and get approvals | 2016-07-01 | 2016-09-30 | 0d | 0% | SHUSA | [6 empty] | MILESTONE: Syndicate plan with key stakeholders and get approvals | 2016-07-01 | 2016-09-30 | 66d | 0% | TRUE | TRUE | TRUE
RG4190 | RT.B.10 | 12.3.3 | MILESTONE: Diagnostics of risk culture; multi-year plan to achieve premier risk culture in place | 2016-09-30 | 2016-09-30 | [9 empty] | MILESTONE: Diagnostics of risk culture; multi-year plan to achieve premier risk culture in place | 2016-09-30 | 2016-09-30 | 0d | 0% | TRUE | TRUE | TRUE