## Slide 1: Index of Change
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
04/04/17
  10/02/15
  11/06/15
  10/02/15
  11/06/15
  11/09/161
  01/22/16
  01/25/171
  04/01/16
  04/04/171
  10/02/15
08/03/15
  08/03/15
  08/31/15
  08/31/15
  10/05/15
  11/09/15
  11/16/15
  01/25/16
  02/01/16
  04/04/16
  08/03/15
  Design Operating Model combining all risk types
  Focus on design phase this year
Deliverables / milestones
Finish
Sub-workstream
Start
Notes
  1 Implementation finish date may be refined during the design phase
Original
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
    Determine the prioritization of detailed operating model design and rollout by risk type / function
    Design detailed operating model and implementation plans for Risk Type / Function A & B (Most likely Credit, ERM + RAS + Strategic)
      Define detailed organizational structure and assess talent needs including target headcounts and skill sets
      Develop rollout plan
    Implement the redesigned Operating Model for Risk Type / Function A & B
    Design detailed operating model and implementation plans for Risk Type / Function C & D (Most likely Market & Liquidity, Compliance)
    Implement the redesigned Operating Model for Risk Type / Function C & D
    Design detailed operating model and implementation plans for Risk Type / Function E & F (Most likely Risk Management Information, Capital Risk)
    Implement the redesigned Operating Model for Risk Type / Function E & F
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
  Current
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
    Review of existing 1st LoD structure and capabilities (in plan, not in the slide to Fed, on CCAR side?)
    Design detailed operating model and implementation plans for all risk types ex. Op risk
    Design detailed operating model and implementation plans for Op Risk
    Implement the redesigned Operating Model for all the risks
    Post Implementation Review
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
05/02/17
  07/17/15
  11/06/15
  11/30/15
  04/04/17
  05/02/17
  04/01/16
06/22/15
  06/22/15
  07/13/15
  07/13/15
  11/09/15
  11/10/16
  02/01/16

## Slide 2: Risk Transformation project plan (1/4)
  Deliverables
    Milestones under the deliverable
    Completed
Risk Governance & Organization
  11/30/15
  07/31/15
  8/15/15
  09/30/15
  09/30/15
  09/30/15
  10/31/15
  11/30/15
  01/31/16
  01/15/16
  01/31/16
Ongoing
07/31/15
01/08/16
05/02/17
  07/17/15
  11/06/15
  11/30/15
  04/04/17
  05/02/17
  Ongoing
  04/01/16
  09/30/16
  12/18/15
  01/02/17
  04/04/17
  07/15/15
  07/15/15
  07/15/15
  08/01/15
  08/01/15
  07/15/15
  10/01/15
  11/01/15
  12/01/15
  12/01/15
  01/3/16
02/01/16
07/13/15
07/13/15
06/22/15
  06/22/15
  07/13/15
  07/13/15
  11/09/15
  11/10/16
  01/25/16
  02/01/16
  07/01/16
  06/15/16
  04/01/16
  07/01/16
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn
  Gunn/ Briongos
  Gunn/ Briongos
  Gunn/ Briongos
Deliverables / milestones
Finish
Sub-workstream
Start
Owner
  1 Implementation finish date may be refined during the design phase
  Draft overarching Governance and Oversight Framework Document for SHUSA1; syndicate and finalize
    Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company
    Define target state committee structure including Board and Management committees
    Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries
    Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines
    Develop policy framework, establish overall policies including guidelines for approval of policies
    Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries
    Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
  Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans
    Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting
    Establish comprehensive implementation plans to address these gaps over a multi-year period
Execute against multi-year plan for Risk Transformation
Implement routine Risk-Business reviews with standardized materials and reports
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD)
Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement
      Review of existing 1st LoD structure and capabilities
      Design detailed operating model and implementation plans for all risk types ex. Op risk
      Design detailed operating model and implementation plans for Op Risk
      Implement the redesigned Operating Model for all the risks
      1st/2nd/3rd Round Post Implementation Review
  Rollout communication and training for organizational changes related to 3 LOD
  Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment
  Define multiyear plan to achieve a sound target state risk culture
  Assess existing Risk Management Performance Scorecards and identify gaps
  Rollout systematic performance assessments and risk-based compensation structures
  Diagnose retention challenge and design recruitment and retention mechanisms