## Slide 1
SHUSA Risk Transformation
Leadership Team Weekly Meeting
February 16, 2016
For Discussion
DRAFT Version
Notes: 1

## Slide 2
 | Workstream | Overall | Schedule | Risk |  | Accomplishments |  | Key issues and risks | 
 | Risk Transformation | R | R | R |  | Submitted Material Risk Program action plans to Internal Audit |  | ISSUE: Governance Framework approval delays caused the Governance and Org Subsection to fall behind. The delay is causing other CART workstreams to miss deadlines due to their dependency on the completion of this framework. | 
 |  |  |  |  |  |  |  |  | 
 | Model Development | A | G | A |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | Model Risk Management | A | R | A |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | Operational Risk | R | R | G |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | Finance Transformation | A | R | A |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | Data & IT | A | R | A |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | CCAR | A | R | A |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | IHC | R | R | R |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 | Treasury / ELS | G | G | G |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
CART Workstream Dashboard

## Slide 3
Key Deliverables |  |  |  |  | Material Risks/Issues
Deliverable | Due Date | Prior | Curr. |  | ISSUE: Governance Framework approval delays caused the Governance and Org Subsection to fall behind. The delay is causing other CART workstreams to miss deadlines due to their dependency on the completion of this framework.
Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 12/11/2015 | R |  |  | 
Enhanced top of the house risk policies and 3 LOD articulation | 01/08/2016 | R |  |  | 
Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 01/31/2016 | R |  |  | 
Articulate desired risk culture (“Tone from the Top”) and conduct a risk culture assessment | 04/01/2016 | G |  |  | 
Key Accomplishments This Week |  |  |  |  | Focus For Next Week
RAS: Met with BSPR ERM to discuss RAS metrics selection; set detailed timeline for 2016 RAS exercise Risk Monitoring: Kicked-off the communication with SHUSA risk managers for the inclusion of the IHC/US entities in the MRR/CRO reports; set timeline for next steps Risk ID: Completed LoB and Entity functionality for Access database Risk ID: SHUSA Material Risk team and Risk Aggregation achieved consensus on continuous process rollout (pilot) Risk ID/RAS: Continue meetings on RAS and MRP process integration with Strategic Planning. Risk ID: Finalized and delivered Internal Audit response |  |  |  |  | Finalize and submit action plans for remaining ERM areas Update RAS development progress with other IHC entities; begin receiving feedback from risk managers regarding data availability for new Group metrics Risk Monitoring: Hold one-on-one meetings with SHUSA Risk teams to start the incorporation of the IHC/US entities in the MRR/CRO reports Risk ID: Finalize the continuous process guidance Risk ID: Develop reporting to address Internal Audit concerns Risk ID: Follow-up with Risk Managers to ensure completeness of Risk type guidance
Risk Transformation: Workstream Update
Key Message: Governance Framework & Target Operating Model approval delays continue to impact dependent Risk Transformation sub-workstreams. SHUSA MRP team and Risk Aggregation achieved consensus on continuous process rollout (pilot)
Key Contacts
Status Summary |  | 
Area | Prior | Curr.
Overall | R | 
Schedule | R | 
Risks | R | 
Scope | A | 
Resources | G | 
Financials | N/A | N/A
Accountable Exec:
Matthew Burns
Project Lead:
Greg Timmons
Senior PM:
Subayu Mandal

## Slide 4
Risk Transformation: 30 Day Look Ahead
C
Complete
G
On Target
A
At risk of missing deadlines
R
Will miss or has missed deadlines
Status | Deliver. ID | Type | Upcoming Deliverables/Milestones | Due Date | Key issues and risks
90% | RT.B.1.7 | M | Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize. | 12/11/2015 | Governance Framework: Pending SHUSA Board Approval and expected to be submitted in Q1 2016.
5% | RT.B.2.1 | M | Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting. | 01/15/2016 | 
0% | RT.B.2.2 | M | Establish comprehensive implementation plans to address these gaps over a multi-year period. | 01/31/2016 | 
90% | RT.B.5 | D | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD). | 01/08/2016 | ERM Framework: Pending SHUSA Board Approval and expected to be submitted in Q1 2016.
10% | RT.C.2.1 | M | Assess foundational Risk ID processes and ensure complete Foundational Risk Inventory is in place. | 02/26/2016 | Expected completion date to be revised as part of ongoing 2016 re-planning.
45% | RT.C.5 | D | Updated material risk inventory template and guidance for Material Risk Program. | 02/26/2016 | 
43% | RT.A.4.2 | M | Integrate RAS into Strategic Planning Process | 03/04/2016 | May need to realign date to the Strategic Planning Process calendar for 2016

## Slide 5
FOR RISK TRANSFORMATION LEADERSHIP REVIEW ONLY

## Slide 6
Risk Transformation: 60 - 90 Day Look Ahead
C
Complete
G
On Target
A
At risk of missing deadlines
R
Will miss or has missed deadlines
Status | Deliver. ID | Type | Upcoming Deliverables/Milestones | Due Date | Key issues and risks
50% | RT.D.3 | D | Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA | Thu 3/31/16 | Meeting with wholesale credit stakeholders on 2/12 to obtain updates
5% | RT.B.9 | D | Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | Fri 4/1/16 | Started definition of survey portion of risk culture assessment
0% | RT.E.6 | D | Develop and implement Wave 3 of exec. Mgmt. reporting enhancements | Fri 4/1/16 | 
6% | RT.A.4.2 | M | Integrate RAS into Material Risk Process | Fri 4/29/16 | 
6% | RT.A.4.2 | M | Integrate RAS into New Products and Business Activities Process | Fri 4/29/16 | 
25% | RT.D.1 | D | Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | Fri 4/29/16 | ELS indicates this to be on track
Risk Transformation Deliverable ID code key: RT.A.x = RAS; RT.B.x= Gov/Org; RT.C.x = Risk ID; RT.D.x = Risk Mgmt; RT.E.x = Risk Mon

## Slide 7
MRA Tracking Dashboard
Late (Past Due)
*Note: Change Log request for re-baselining of the milestone involving the above mentioned deliverables.
Deliverables | Owner | End Date | MRA / MRIA Description | IA Commitment Detail | Outstanding Milestone
Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | Matt Burns | Fri 12/11/2015 | CCAR 2014 MRA 4, CCAR 2014 MRIA 2, SAN-US Compliance Risk Management Examination 2013 MRA 1, 2014 SCUSA Retail ALLL ECM MRA 2, Credit Risk Management Target 2013 MRA 1, Credit Risk Management Target 2013 MRIA 1, Enterprise-wide Risk Management Review 2013 MRA 2, Report of Inspection 2015 MRIA 2, Report of Inspection 2015 MRA 1, SAN-US Model Risk Management Exam 2015 MRIA 1, Reporting Structure for Commercial Credit Underwriting and Account Management SBNA-2015-20 MRA 1, Report of Examination 2014 MRA 3, Enterprise Risk Management SBNA-2015-24 MRA 2, Report of Inspection 2011 MRA 1, Operational Risk Governance SOV-2013-07 MRA 1, Report of Examination 2014 MRBA 3 | None | Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | Matt Burns | Fri 01/08/2016 | Report of Inspection 2015 MRIA 1, Reporting Structure for Commercial Credit Underwriting and Account Management SBNA-2015-20 MRA 1, Enterprise Risk Management SBNA-2015-24 MRA 2, Report of Inspection 2011 MRA 1 | None | ERM Framework Approval from SHUSA Board

## Slide 8
Deliverables | Owner | End Date | MRA / MRIA Description | IA Commitment Detail | Outstanding Milestone
Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | Matt Burns | Sun 01/31/2016 | CCAR 2014 MRIA 2, 2014 SCUSA Retail ALLL ECM MRA 2, Report of Inspection 2015 MRIA 2, Report of Inspection 2015 MRIA 1, Report of Examination 2014 MRA 3, Enterprise Risk Management SBNA-2015-24 MRA 2, Report of Inspection 2011 MRA 1, Operational Risk Governance SOV-2013-07 MRA 1, Report of Examination 2014 MRBA 3 | None | Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize
MRA Tracking Dashboard
Late (Past Due)

## Slide 9
Deliverables | Owner | End Date | MRA / MRIA Description | IA Commitment Detail | Outstanding Milestone
Updated material risk inventory template and guidance for Material Risk Program | Diane Allaire | Fri 2/26/16 | CCAR 2014 MRIA 4 | None | 
MRA Tracking Dashboard
30 Day Outlook
Deliverables | Owner | End Date | MRA / MRIA Description | IA Commitment Detail | Outstanding Milestone
Develop and implement Wave 3 of exec. Mgmt. reporting enhancements | Paula Coutinho | Fri 4/1/16 | Enterprise wide Risk Management Review 2013 MRA 3,Report of Inspection 2015 MRIA 1,Report of Inspection 2015 MRIA 2 | IA.1.1.6 | Note: this will be changed in re-planning process
Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | Manuel Aya | Fri 4/29/16 | SAN US Liquidity Risk Management Examination 2012 MRIA 1,SCUSA Target 2011 MRA 9 | IA.1.2.3 | 
60-90 Day Outlook

## Slide 10
Risk Transformation– HR Process Tracker
Hiring Pipeline |  |  |  |  |  | 
# | FTE | Job Req. Posting Code | Status | FTE Name | Start Date | 
2 | Project Manager | N/A | Not Posted / Covered by FTC | N/A | N/A | 
3 | Project Manager | N/A | Not Posted / Covered by FTC | N/A | N/A | 
1. Excludes Deliverables based resources.
Actual (01/19/2016)
Diff. to Fed (01/31/2016)
Δ Fed target to plan
Resource difference to plan
Revised Target (12/31/15)
20.25
2
22.25
20.25
2
22.25
0
0
-
-
-
-
0
-
-
FTE
FTC
Total1
Status
Hiring Pipeline
1. Excludes Deliverables based resources.
Updates pending based on 2016 Staffing Target

## Slide 11
Risk Transformation Deliverable Tracking Dashboard
Deliverable Categorization
Total Deliverables: All tasks/milestones in the RT Project Plan that have been set to 100% Collected Deliverables: All tasks/milestones in the RT Project Plan that have been set to 100% and an artifact has been produced and delivered to the CMT to substantiate the completion of the deliverable Request Needed Deliverables: All tasks/milestones in the RT Project Plan that have been set to 100% and an artifact has not been produced and delivered to the CMT to substantiate the completion of the deliverable – CMT will send a reminder to deliver the artifact Requested Deliverables: All tasks/milestones in the RT Project Plan that have been set to 100% and an artifact has not been produced and delivered to the CMT to substantiate the completion of the deliverable – CMT will send a reminder to deliver the artifact within 7 days Delinquent Deliverables: All tasks/milestones in the RT Project Plan that have been set to 100% and an artifact has not been produced and delivered to the CMT to substantiate the completion of the deliverable within 7 days Upcoming Deliverables: All tasks/milestones that are due within 30 days
91.2%* of the deliverables due have been collected to date | Total Evidence of Deliverable or Milestone Completion | Collected Evidence | Evidence to be Requested | Requested Evidence | Outstancing Evidence to be Collected | Upcoming Deliverables
Risk Transformation | 68* | 62 | 0 | 0 | 6 | 1
* Data is pending final discussions with key Material Risk Program stakeholders to determine appropriate artifacts
Outstanding Deliverables to be Collected |  |  |  | 
Cover Sheet Deliverable Name | Finish Date | % Complete | Owner | Notes
Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 01/08/2016 | 90% | Matt Burns | Pending completion
Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 01/30/2016 | 0% | Matt Burns | Pending completion
Material Risk Program artifacts (loading of artifacts to SharePoint is ongoing) | 12/11/2015 | 100% | Matt Burns | Finalizing documentation
Develop and implement Wave 2 of exec Mgmt. reporting enhancements | 12/28/2015 | 100% | Matt Burns | Awaiting C. Hunley sign-off
Communicate Board-approved SHUSA (top-level), SBNA, and SCUSA RAS to enterprise | 02/24/2016 | 100% | Matt Burns | Pending A.E. Signoff
Test Strategic Plan against SHUSA (Top Level, SBNA, and SCUSA RAS | 09/18/2015 | 100% | Matt Burns | Pending A.E. Signoff
Upcoming Deliverables |  |  |  | 
Cover Sheet Deliverable Name | Finish Date | % Complete | Owner | Notes
Updated material risk inventory template and guidance for Material Risk Program | 02/26/2016 | 30% | Matt Burns | Pending completion

## Slide 12
Risk Management Internal Audit Recommendations
Unit | Recommendations | Target Date | Mgmt. Response Due | Status | Notes
ERM | 1.1. The Chairs of each Risk Committee should ensure that a majority of the members are present at each of the meetings. A quorum should be established and documented in the minutes of each meeting. 1.2. In the event of the Chair's absence, another member of the Committee must be appointed Chair for the meeting. 1.3. ERMC charter should be updated to detail the follow-up and escalation process in the event a monthly meeting cannot be held. | 06/30/2016 | 02/19/2016 | Open | Audit Review scheduled for 02/16
 | 2. Develop and implement a formal policy and procedure outlining risk change management standards | 06/30/2016 | 02/19/2016 | Open | Audit Review scheduled for 02/16
 | 3. Develop and implement elements/tools that transmit the risk culture throughout the organization | 12/30/2016 | 02/19/2016 | Open | 
RAS | 4. Finalize the SHUSA Risk Appetite Metrics Glossary to ensure a repeatable process is in place for the calculation of risk appetite metrics and limits. | 02/29/2016 | 02/12/2016 | Submitted | Completed and submitted
 | 5. Develop a formal plan by which metrics will be tested and how to execute testing at various points throughout the year to ensure all metric categories are validated on a consistent basis | 09/30/2016 | 02/12/2016 | Submitted | Audit requires development of action plan by 9/30
MRP | 6. Identify and implement additional controls (e.g. quality controls) to mitigate potential errors due to the manual nature of the risk identification and assessment process. Document both existing and new controls and incorporate into the Material Risk Program Guidance and/or additional procedural documents. | 06/30/2016 | 02/12/2016 | Submitted | 

## Slide 13
Risk Management Internal Audit Recommendations
Unit | Recommendations | Target Date | Mgmt. Response Due | Status | Notes
MRP | 7. Enhance the Material Risk Program Guidance and Business Entity Enrichment and Aggregation Guidance to require documentation of justification for significant changes to risk types and risks not carried forward throughout the process, and to define when approvals are required for deviations to Guidance. | 06/30/2016 | 02/12/2016 | Submitted | 
 | 8. Management needs to clarify the financial impact assessment approach used in the Material Risk Program and re-train all stakeholders to ensure consistent execution across all entities and lines of defense. Management also needs to ensure adjustments made by SHUSA are properly justified, reviewed, and challenged to ensure adequacy of the final assessment and transparency of the process. | 08/31/2016 | 02/12/2016 | Submitted |