## Slide 1
Risk Appetite Statement
2015 –
Accomplishments
2016 –
Key Goals
Risk ID & Assessment
Risk Gov & Org
Risk Monitoring
2017+
Key Goals
SHUSA CRO Report enhanced. SBNA/SC CRO Reports, SHUSA CRO Dashboard & Compliance Monthly Risk Reports developed and implemented
Initial CRO reporting landscape defined
Data and Business Requirements for Senior Management Reports for CUSO defined
Business Glossaries were updated based on the new reports/reports enhancements
Re-design and implement report templates for priority 2 risk type reports
Upgrade report generation process based on risk data aggregation and reporting enhanced capabilities
Define CRO report generation process and applicable governance, enhancing coordination with SBNA and SC
Assess synergies in the production of the Monthly Risk Report and RAS report and define action plan
Expand CRO report to include all CUSO entities
Update CRO reporting landscape per TOM and Gov. Framework
Re-design and implement report templates for priority 1 risk type or LOB reports
Upgrade process based on tactical solution for ERM report generation process
Enhanced the Material Risk Program and rolled out to SHUSA and IHC entities
Material Risk Program results were ERMC Challenged, CEC Approved and provided to BRC for info.
Make improvements to the Material Risk Program Guidance, produce training materials, and execute
Design and implement continuous process for material risks
Review foundational risk processes and execute remediation plans
Refine Material Risk Program Process and transition to BAU
Refine Foundational Risk ID Process
Define requirements for long term technology solution for MRP
Models developed for CRE and C&I
Validation began on CRE and C&I risk rating models
Overarching Framework approved for CRE model
Complete implementation of RR models and the related technology solution
Implement LRM Policy at the IHC entities
Establish RR Committee (Approve Charter) for on-going governance of model and usage
Revise Overarching framework to incorporate C&I Model
Training and Usage of the Model/Tool
Conduct gap analysis focusing on methodology, tools, processes, etc. as defined by the operating model & benchmark to industry practice and remediate gaps
Refine models to align to bank strategies, loss history and portfolio concentrations.
Continual training and policy revision to match model and market conditions
Risk
Management
Designed and approved target state committee structure, including Board & Management committees
Continued iterations of the Governance and Oversight Framework
Obtain approvals for Governance Framework and roll out the entities
Design Operating Model, develop plans, and begin implementation
Set “Tone from the Top” and conduct a risk culture assessment
Enhance operating model through annual update and continuous processes and transition to BAU
Develop and rollout continuous risk culture program and transition to BAU
Developed and obtained Board approval for the Risk Appetite Statements (RASs) at SHUSA, SBNA, and SCUSA
Began facilitation of integration of Risk Appetite (RA) into Key Processes
Develop RASs for IHC entities; annual RAS recalibration
Complete integration of RA into key processes (e.g. Capital, MRP, NBPA)
Begin cascading of RAS into Business Units within all entities
Finalize cascading of RAS into Business Units within all entities

## Slide 2
Risk Transformation Resources
Sub-Workstream | Risk Appetite | Risk ID & Assessment | Risk Gov & Org | Risk Monitoring | Risk Management
Could the listed roadmap initiatives be completed with the currently approved headcount? |  |  |  |  | Yes
How many additional FTE would be needed to incorporate industry best practices into the project? |  |  |  |  | 
Assumptions, qualifications and / or comments related to resource analysis. |  |  |  |  | 

## Slide 3
Risk Appetite Statement
Key Goals | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Design RAS for remaining IHC entities (SIS, Miami, Puerto Rico) and obtain approvals | SIS, Miami, and Puerto Rico board-approved RAS |  |  |  |  |  |  | 
Annual update of RAS for SHUSA, SBNA, and SC (SHUSA to incorporate all IHC entities) | Updated SHUSA, SBNA, and SC RAS |  |  |  |  |  |  | 
Integrate RAS into Key Processes |  |  |  |  |  |  |  | 
Integrate RAS into New Products and Business Activities Process | Updated NBPA process document with explicit linkages to the RAS |  |  |  |  |  |  | 
Integrate RAS into Strategic Planning Process | Updated Strategic planning process document with explicit linkages to the RAS |  |  |  |  |  |  | 
Integrate RAS into Capital Planning Process | Updated Capital Planning process document with explicit linkages to the RAS |  |  |  |  |  |  | 
Integrate RAS into Material Risk Program Process | Updated MRP process document with explicit linkages to the RAS |  |  |  |  |  |  | 
Communicate 2016 RAS throughout the enterprise, including targeted training to key stakeholders | Enterprise wide communication of RAS updates, training documentation |  |  |  |  |  |  | 
Cascade the RAS into the business units (BU) and ensure alignment with overall SHUSA risk appetite statement | Documentation regarding BU management limits which are linked to risk appetite as appropriate (to discuss) |  |  |  |  |  |  | 

## Slide 4
Risk Appetite – Dependencies & Risks
Dependency/ Risk | Description | Importance / Impact
Technology | None | N/A
Resources | There will be a need to backfill a major role in the RAS group as key stakeholders roll off the project at the end of 2Q16 | High
 | Staffing – There will be a need for additional staffing as the IHC entities develop Risk Appetite Statements. | High
 | Budget – The budget for consulting partners and increased staffing will need to be approved by Cost & Structures | High
Other Work streams | IHC – there will be a large requirement for entity involvement as it relates to rollout of the RAS at PR, Miami and NY | High

## Slide 5
Risk Appetite– MR(I)As
MRA/MRIA reference | Deficiency Title | Theme | MR(I)A Owner (Local/ Executive) | Finish date
Capital Planning Review 2013 MRA 27 | RTS Capital Adequacy Monitoring | Capital Planning | Ignacio Fuentes/Brian Gunn | Fri 9/11/15
Enterprise-wide Risk Management Review 2013 MRA 1 | Risk Tolerance Statement Metric Selection | RAS | Ignacio Fuentes/Brian Gunn | Tue 9/15/15
Report of Inspection 2015 MRIA 1 | Board and Senior Management Oversight of Consolidated Organization | Board Oversight | Michael Lipsitz | Thu 6/30/16

## Slide 6
Risk Identification & Assessment (1/2)
Key Goal | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Review foundational Risk ID processes and build multi-year enhancement objectives | Foundation Risk ID Multi-year Objectives document |  | * |  |  |  |  | 
Execute remediation plan for foundational Risk ID processes | Plan execution artifacts |  |  |  |  | * |  | 
Complete Lessons Learned for 2015 Material Risk Program | Lessons Learned Results Documentation |  |  |  |  |  |  | 
Updated material risk inventory template and guidance for Material Risk Program |  |  |  |  |  |  |  | 
Update "top-down" guidance | “Top-Down” Guidance document |  |  |  |  |  |  | 
Update “bottoms-up“ guidance | “Bottoms-up” Guidance document |  |  |  |  |  |  | 
Update “continuous“ guidance | “Continuous” Guidance document |  |  |  |  |  |  | 
Enhance Material Risk Program toolset | Enhanced MRP toolset document |  |  |  |  |  |  | 
Develop training materials for Material Risk Program and execute training |  |  |  |  |  |  |  | 
Develop Training materials | Training materials |  |  |  |  |  |  | 
Execute Training | Training attendee list |  |  |  |  |  |  | 
Develop executive communication for Material Risk Program | Executive communication documentation |  |  |  |  |  |  | 
Implement “Top-Down” Material Risk Program Process | Implementation artifacts for Top-Down process |  |  |  |  |  |  | 
* Date has not been finalized

## Slide 7
Risk Identification & Assessment (2/2)
Key Goal | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Implement Execution of "bottoms up process" for MRP for all seven (7) entities |  |  |  |  |  |  |  | 
Execute 1st LoD Material Risk Program by LoB for each entity | Approved Entity LoB Material Risk Inventory |  |  |  |  |  |  | 
Execute Aggregation & Enrichment process for each entity | Approved Entity Risk Type Inventory |  |  |  |  |  |  | 
Execute SHUSA Aggregation & Enrichment process for all risk types | Approved SHUSA Material Risk Inventory |  |  |  |  |  |  | 
Implement “Continuous” Material Risk Program | Execution artifacts for “Continuous” Material Risk Program |  | * |  |  |  |  | 
Develop and implement guidance for Mid-Cycle run | Mid-Cycle Run Guidance Document and implementation artifacts | * |  |  |  |  |  | 
* Date has not been finalized

## Slide 8
Risk Identification & Assessment – Dependencies & Risks
Dependency/ Risk | Description | Importance / Impact
Technology | There will need to be an updated toolset developed, or leveraged, as the Material Risk Program continues to increase in maturity. | Medium
Resources | Staffing – Foundational Risk ID and the Material Risk Program will both require additional staffing in order to facilitate the implementation and execution of new processes i.e. continuous process and mid-cycle run. | Medium
 | Budget – The budget for consulting partners and increased staffing will need to be approved by Cost & Structures. | Medium
Other Workstreams | Operational Risk – The Foundational Risk ID processes are heavily reliant on the Operational Risk Workstream for their identification programs e.g., RCSA, Vendor Risk Assessments, etc. | High
 | Other Risk Types – Foundational Risk ID Assessment will need to be completed by other workstreams, besides Operational Risk, to illustrate the concerns from various other Risk Identification processes. | 
 | IHC – There will be a large requirement for entity involvement as it relates to the bottoms up process for the Material Risk Program. | High

## Slide 9
Risk Identification & Assessment – MR(I)As
MRA/MRIA reference | Deficiency Title | Theme | MR(I)A Owner (Local/ Executive) | Finish date
CCAR 2014 MRIA 4 | Risk Identification Process | Risk Identification | Diane Allaire / Matt Burns / Brian Gunn | Wed 5/31/17
Report of Inspection 2015 MRIA 2 | Enterprise-wide Risk Management Program | ERM | Brian Gunn / Brian Gunn | Wed 5/31/17
Information Security SOV-2013-09 MRA 2 | Risk Measurement Methodology and Risk Assessment Process | Information Security | Mike Lima / Marcelo Brutti | Fri 5/27/16
Wholesale Credit Risk Management SBNA-2014-15 MRA 3 | Credit exposure aggregation needs to be appropriate per correlation of risk among various industries | Credit Risk | James Driscoll / Marcelo Brutti | Fri 1/15/16
Wholesale Credit Risk Management SBNA-2014-15 MRA 2 | Improvement of management of credit concentrations | Risk Appetite | James Driscoll / Marcelo Brutti | Fri 1/15/16
Enterprise Risk Management SBNA-2015-24 MRA 2 | Reputational and Strategic Risk Management | ERM | Mike Carbone / Marcelo Brutti | Fri 1/15/16
Operational Risk Governance SOV-2013-07 MRA 3 | Operational Risk Assessment Process | Operational Risk | Mike Lima / Marcelo Brutti | Fri 5/27/16

## Slide 10
Risk Gov & Org (1/2)
Key Goals | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Design Operating Model across all risk types aligned with principles of 3 LOD, develop rollout plans and implement |  |  |  |  |  |  |  | 
Complete Operating Model | SHUSA Operating Model |  |  |  |  |  |  | 
Obtain approval on Operating Model | Approval evidence |  |  |  |  |  |  | 
Gap assessment against current state | Gap Assessment document |  |  |  |  |  |  | 
Develop rollout plans | Rollout Plans for each entity |  |  |  |  |  |  | 
Implementation of Operating Model | Implementation artifacts |  |  |  |  |  |  | 
Finalize Development of Governance Framework & Obtain Board Approval (incorporate all key ERM elements e.g. MRP, RAS etc.) | Governance Framework |  |  |  |  |  |  | 
Rollout communication and training on risk governance changes resulting from Operating Model and Governance Framework |  |  |  |  |  |  |  | 
Develop SHUSA and entities communications strategy | Communications Strategy |  |  |  |  |  |  | 
Communications and Training rollout for Operating Model | Implementation artifacts |  |  |  |  |  |  | 
Communications and Training rollout for Governance Framework | Implementation artifacts |  |  |  |  |  |  | 
Conduct gap analysis against the overarching Governance Framework document, identify gaps, develop and implement multi-year execution plans |  |  |  |  |  |  |  | 
Conduct GAP Assessment | GAP Analysis document |  |  |  |  |  |  | 
Develop multi-year execution plans | Multi-year Execution Plans |  |  |  |  |  |  | 
Implement multi-year executions plans | Implementation artifacts |  |  |  |  |  |  | 

## Slide 11
Risk Gov & Org (2/2)
Key Goals | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment |  |  |  |  |  |  |  | 
Develop Risk Culture Framework with executive buy-in | Risk Culture Framework document |  |  |  |  |  |  | 
Conduct Risk Culture Assessment | Risk Culture Assessment document |  |  |  |  |  |  | 
Develop plans for achieving desired risk culture | Implementation plans |  |  |  |  |  |  | 
Implement plans for achieving desired risk culture | Implementation artifacts |  |  |  |  |  |  | 
Enhance top of the house risk policies to include risk areas not originally included in CART (e.g., Compliance, Credit Risk) | Updated top of house risk policies documents |  |  |  |  |  |  | 
Develop risk perspective on program follow-thru and develop verification process/program for implementation items | Implementation documents from verification process/program |  |  |  |  |  |  | 
Human Resources Initiatives (content to be revisited with appropriate HR stakeholders) |  |  |  |  |  |  |  | 
Rollout systematic performance assessments and compensation structures | Performance Assessments and Compensation Structures |  |  |  |  |  |  | 
Develop and Enhance scorecards for all IHC Entities | Enhanced Scorecards |  |  |  |  |  |  | 
Diagnose retention challenge and design recruitment and retention mechanisms | Timeline and artifact TBD (to be determined with Lisa VanRoekel and Heightened Standards Team) |  |  |  |  |  |  | 

## Slide 12
Risk Governance & Organization – Dependencies & Risks
Dependency/ Risk | Description | Importance / Impact
Resources | Staffing – Governance and Organization will require additional staffing in order to facilitate the gap assessments and remediation plans for the Operating Model and Governance framework. | High
 | Budget – The budget for consulting partners and increased staffing will need to be approved by Cost & Structures. | High
Other Workstreams | There are a number of dependencies from other workstreams on this SWS, mainly as it relates to the TOM and Governance Framework. | High
 | IHC – There will be a large requirement for entity involvement as it relates to the gap assessments and rollout of numerous documents, including the Target Operating Model and the Governance Framework. | High

## Slide 13
Gov & Org – MR(I)As
MRA/MRIA reference | Deficiency Title | Theme | MR(I)A Owner (Local/ Executive) | Finish date
CCAR 2014 MRA 4 | Capital Policy and Capital Contingency Plan | Capital Policy | Juan Carlos Alvarez/Jerry Plush | Mon 11/30/15
CCAR 2014 MRIA 2 | Governance Structure | Governance | Jerry Plush | Sun 1/31/16
CCAR 2014 MRIA 4 | Risk Identification Process | Risk Identification | Diane Allaire/Brian Gunn | Fri 10/14/16
SAN-US Compliance Risk Management Examination 2013 MRA 1 | Compliance Risk Management Framework | Compliance | Michael Wilcox/Carol Hunley | Fri 10/14/16
2014 SCUSA Retail ALLL ECM MRA 2 | ALLL Governance Structure | ALLL | Peter Moenickheim/Jason Kulas | ongoing
Credit Risk Management Target 2013 MRA 1 | Expansion of the Credit Risk Reporting Packages | Credit Risk | Peter Moenickheim/Jason Kulas | Mon 11/30/15
Credit Risk Management Target 2013 MRIA 1 | Implementation of an Effective Credit Risk Management Framework | Credit Risk | Peter Moenickheim/Jason Kulas | Fri 10/14/16
Enterprise-wide Risk Management Review 2013 MRA 2 | EWRMG Issue Discovery and Resolution | ERM | Brian Gunn | Mon 1/2/17
Report of Inspection 2015 MRA 1 | Improve policies, procedures, and practices surrounding new business initiatives | New Business Initiatives | Michael Lipsitz | Mon 11/30/15
SAN-US Model Risk Management Exam 2015 MRIA 1 | SAN-US MRM Governance and Oversight | Model Risk Management | Rafic Fahs/Brian Gunn | Mon 11/30/15
SAN-US Model Risk Management Exam 2015 MRA 1 | SCUSA Pricing Model Governance | Model Risk Management | Lana Johnson/Jason Grubb | Thu 12/31/15
Vendor Risk Management SBNA-2013-21 MRA 1 | Governance Framework Requires Strengthening | Vendor Risk | Michael Lima/Marcelo Brutti | Fri 10/14/16
Vendor Risk Management SBNA-2013-21 MRA 4 | Quality Assurance Processes are Lacking and Need to Be Developed | Vendor Risk | Michael Lima/Marcelo Brutti | Fri 10/14/16
Reporting Structure for Commercial Credit Underwriting and Account Management SBNA-2015-20 MRA 1 | Credit Risk Management Independence | Governance | David Spector | ongoing
Report of Examination 2014 MRA 3 | Credit Risk Governance | Governance | Manuel Rodriguez/Francisco de Lera | ongoing
Enterprise Risk Management SBNA-2015-24 MRA 2 | Reputational and Strategic Risk Management | ERM | Mike Carbone/Marcelo Brutti | ongoing
Report of Inspection 2011 MRA 1 | SBC Enterprise Wide Risk Management Program | ERM | Angel Vares/Fredy Molfino | ongoing
Operational Risk Governance SOV-2013-07 MRA 1 | Organizational Structure | Operational Risk | Michael Lima/Marcelo Brutti | ongoing
Operational Risk Management SBNA-2014-31 | Integration of Operational Risk Management in the Lines of Business | Operational Risk | Michael Lima/Marcelo Brutti | Fri 10/14/16
Report of Examination 2014 MRBA 3 | Composition of the Audit Committee | Internal Audit | Rafael Bonilla/Fredy Molfino | ongoing

## Slide 14
Risk Monitoring (1/2)
Key Goals | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Define CRO report generation process and applicable governance, enhancing coordination with SBNA and SC | CRO Report Generation Process and Governance defined |  |  |  |  |  |  | 
Assess synergies in the production of the Monthly Risk Report and RAS report and define action plan | Findings of the assessment and action plan |  |  |  |  |  |  | 
Expand SHUSA MRR and CRO Report for IHC/CUSO |  |  |  |  |  |  |  | 
Adapt SHUSA MRR Report to new corporate template and update report generation procedures after implementation | Updated SHUSA MRR and SHUSA MRR Handbook |  |  |  |  |  |  | 
Develop corporate view of MRR report Identify metrics with corporate versus local view Adapt processes to create additional slides with corporate view Create SHUSA MRR with corporate view | Documented differences between corporate vs. local metrics. New SHUSA MRR with corporate view. |  |  |  |  |  |  | 
Implement IHC/CUSO view of MRR report Conduct a gap assessment of SHUSA MRR metrics amongst all US entities Define approach to present IHC/CUSO CRO repot to the BRC and Board and implementation timeline. Expand data collection templates and report generation process to include all IHC/CUSO metrics. Draft IHC/CUSO MRR Gather senior management feedback Incorporate feedback Revised report distributed to senior management. | IHC/CUSO MRR and CRO Reports |   |      |  |  |  |  | 
Automation process to be mapped depending on TBD tactical and strategic reporting solutions

## Slide 15
Risk Monitoring (2/2)
Key Goals | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Define target risk reporting program for the IHC and CUSO |  |  |  |  |  |  |  | 
This should include the definition of risk reporting landscape for the core risk reports linked to Board level report, key content and frequency of each risk report and escalation process | Target reporting landscape for the core risk reports |  |  |  |  |  |  | 
Gap assessment versus current reports | Identified Gaps in Risk Reporting from current state to target state |  |  |  |  |  |  | 
Design of report templates for new reports or enhancements of existing reports and define implementation timeline based on risk type (or business line) priority-1 reports | Updated report templates |  |  |  |  |  |  | 
New reports or enhanced existing reports for the IHC and CUSO (manual inputs if access to golden sources are not available) as per defined implementation plan | Updated IHC Risk Reports |  |  |  |  |  |  | 
Documentation of data requirements for report automation process | Updated SHUSA Glossary (data requirements & marked-up report template) |  |  |  |  |  |  | 
Design of report templates for new reports or enhancements of existing reports and define implementation timeline based on risk type (or business line) priority-1 reports | Updated report templates |  |  |  |  |  |  | 
New reports or enhanced existing reports for the IHC and CUSO (manual inputs if access to golden sources are not available) as per defined implementation plan | Updated IHC Risk Reports |  |  |  |  |  |  | 
Documentation of data requirements for report automation process | Updated SHUSA Glossary (data requirements & marked-up report template) |  |  |  |  |  |  | 

## Slide 16
Risk Monitoring & Reporting – Dependencies & Risks
Dependency/ Risk | Description | Importance / Impact
Technology | 2016: Definition of tactical and long term risk data aggregation and reporting technical solution; Implementation of tactical solution for ERM reports. | High
 | 2017+: Implementation of long term solution risk data aggregation and reporting solution, including solution for ERM and Risk Area specific reports for IHC/CUSO. | High
Resources | Staffing – Risk Consolidation will need an increased number of staff to deliver on the implementation of the CRO Reports and other deliverables of the program. Currently Risk Consolidation is staffed with two (2) fewer resources than initially approved. | Medium
 | Budget – Risk Consolidation may need to confirm approval on budgeting for this increased staffing as well as any consulting partners. | High
Other Workstreams | Data / IT – The RDA program needs to be expanded to include all IHC/CUSO entities to meet local regulatory and management requirements | High
 | IHC – The entities will need to be involved as part of the expansion of the scope of the CRO Monthly Risk Reports to include all entities. | High

## Slide 17
Risk Monitoring & Reporting – MR(I)As
MRA/MRIA reference | Deficiency Title | Theme | MR(I)A Owner (Local/ Executive) | Finish date
Report of Inspection 2015 MRIA 2 (sub-item d) | Enterprise-wide Risk Management Program | ERM | Brian Gunn / Brian Gunn | Fri 4/1/16
Credit Risk Management Target 2013 MRA 1 | Expansion of the Credit Risk Reporting Packages | Credit Risk | Peter Moenickheim / Jason Kulas | Mon 11/9/15
Enterprise-wide Risk Management Review 2013 MRA 3 | EWRMG Access to Data and Systems | ERM | Arif Arain / Brian Gunn | Fri 4/1/16
Report of Inspection 2015 MRIA 1 | Board and Senior Management Oversight of Consolidated Organization | Board Oversight | Michael Lipsitz / Michael Lipsitz | Fri 4/1/16
Enterprise Risk Management SBNA-2015-24 MRA 2 | Reputational and Strategic Risk Management | ERM | Mike Carbone / Marcelo Brutti | Mon 9/7/15

## Slide 18
Risk Management – Roadmap
Key Goal | Deliverable/Artifact | 2016 |  |  |  | 2017 |  | 2018+
 |  | 1Q | 2Q | 3Q | 4Q | 1H | 2H | 
Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA | Revised wholesale credit process documentation |  |  |  |  |  |  | 
Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | Updated LRM Policies at IHC entities |  |  |  |  |  |  | 
Rollout Commercial Risk Ratings |  |  |  |  |  |  |  | 
Finalize CRE Model | Validated CRE Model |  |  |  |  |  |  | 
Finalize C&I Model | Validated C&I Model |  |  |  |  |  |  | 
CRE Implementation (Phase 1 solution) | CRE Model Solution implemented |  |  |  |  |  |  | 
C&I Implementation (Phase 1 solution) | C&I Model Solution implemented |  |  |  |  |  |  | 
Create requirement definitions for Phase II technology solution for CRE and C&I model implementation | BRD for Phase 2 technology solution |  |  |  |  |  |  | 
Conduct gap analyses across risk types focusing on methodology, tools, processes, and expectations as defined by the operating model and benchmark to industry practice | Gap analyses across Risk Types |  |  |  |  |  |  | 
Create remediation plans to address gaps and initiate remediation actions | Remediation plans to align with industry best practice |  |  |  |  |  |  | 
Establish Risk Rating Committee and Charter for on-going governance | Charter and Committee schedule |  |  |  |  |  |  | 
Revise Overarching framework to incorporate C&I Rating | Overarching framework document |  |  |  |  |  |  | 
Training and Usage of Model | Training Classes, Procedure and Policy Documentation |  |  |  |  |  |  | 

## Slide 19
Risk Management – Dependencies & Risks
Dependency/ Risk | Description | Importance / Impact
Technology | T&O will be required to implement both the short and long term solution for the Risk Rating Tool. | High
Resources | The Head of Credit Risk Rating position will need to be filled prior to completion of the Risk Rating Initiative. | Medium
 | Staffing – Management will not need any new hires. | N/A
 | Budget – We will not need to obtain approval on budgeting for this initiative due to the lack of requirements for increased staffing. | N/A
Other Workstreams | ELS – There are a number of Liquidity initiatives in the Risk Management plan, which will require their execution. | High
 | Model – Development and Validation of Risk Rating models will need to occur along with completion of BRD as technology updates and enhancements are made. | High
 | Wholesale Credit - Wholesale credit will be needed to opine on pertinent sections of the plan. | Medium

## Slide 20
Risk Management – MR(I)As
MRA/MRIA reference | Deficiency Title | Theme | MR(I)A Owner (Local/ Executive) | Finish date
Enterprise Risk Management SBNA-2015-24 MRA 2 | Reputational & Strategic Risk Management | ERM | Mike Carbone/ Marcelo Brutti | Fri 12/2/16
Wholesale Credit Risk Management SBNA-2014-15 MRA 2 | Improvement of management of credit concentrations | RAS | James Driscoll/ Marcelo Brutti | Thu 3/31/16
Middle Market C&I Lending SBNA-2014-24 MRA 2 | Risk Rating Methodology | Credit Risk | Bill Latham / David Spector | Fri 7/29/16
Wholesale Credit Risk Management SBNA-2014-15 MRA 3 | Credit exposure aggregation needs to be appropriate per correlation of risk among various industries | Credit Risk | James Driscoll/ Marcelo Brutti | Thu 3/31/16
SAN-US Liquidity Risk Management Examination 2012 MRIA 1 | Liquidity Risk Management Practices | Liquidity Stress Testing | Manolo Lasso / Brian Gunn | Thu 12/31/15
SAN-US Liquidity Risk Management Examination 2011 MRA 1 | Formalization of the Liquidity Stress Test Assumption Review Process | Liquidity Stress Testing | Manolo Lasso / Brian Gunn | Thu 12/31/15
SCUSA Target 2011 MRA 9 | SCUSA Liquidity Limits | Liquidity Policies | Jennifer Davis/ Jason Kulas | Mon 11/30/15
CCAR 2015 MRIA 1 | Loss Estimation Methodologies--Wholesale Credit Risk | Loss estimation | TBD / TBD | Fri 7/29/16