## Slide 1: Risk Governance ‘Top Three’ update:
Three most significant items of Progress last week
  Charter template design
  Target committee structure finalized with CRO & handed over high-level R&R
  Section 2 draft socialized and Section 3 and 4 of the Governance playbook outlined
Three most significant Execution items for the next week
Three most significant
Key risks/ Issues/ roadblocks and resource requirements
Weekly update (07/27– 07/31)
  Socialization of the charter template and kick-off drafting of Risk committee charter
  Draft new membership and roles and responsibilities for ERMC and MRM committees
  Share feedback on Board Risk committee with CRO
  CRO feedback on Committee high-level R&R before end of the week / socialization with key stakeholders
  Access to org charts for both SHUSA and the subsidiaries
  Meeting scheduling with appropriate stakeholders to socialize template
Overall Sub-workstream Status
Current Status
Previous Status
Upcoming
G
G
G