## Slide 1: Risk Organization ‘Top Three’ update:
Three most significant items of Progress last week
  Reviewed roles and responsibilities draft with risk type leaders
  Detailed draft of Business Control Officer roles and responsibilities
  Drafted of BCO current state and implementation plan
Three most significant Execution items for the next week
Three most significant
Key risks/ Issues/ roadblocks and resource requirements
Weekly update (07/27 – 07/31)
  Finalize review and compilation of roles and responsibilities
  Determine org chart design principles
  Begin drafting functional org charts
  Have not received current state documentation from Brian
  Operational risk leadership has not been engaged
  Certain risk types may be bottlenecked by delayed stakeholder feedback
Overall Sub-workstream Status
Current Status
Previous Status
G
G
Upcoming
G