## Sheet1 (hidden)
Outline Level | WBS | Task Name | % Complete | Duration | Start | Finish | Contact | Notes | Updated Notes
0 | 0 | Risk Transformation | 1% | 492d? | 2015-06-15 | 2017-05-02
1 | 1 | Risk Governance & Organization | 1% | 492d? | 2015-06-15 | 2017-05-02
2 | 1.1 | Risk Governance & Organization Deliverables | 0% | 467d | 2015-07-17 | 2017-05-02
3 | 1.1.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 0% | 0d | 2015-07-31 | 2015-07-31
3 | 1.1.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 0% | 0d | 2015-08-15 | 2015-08-15
3 | 1.1.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 0% | 0d | 2015-09-30 | 2015-09-30
3 | 1.1.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 0% | 0d | 2015-09-30 | 2015-09-30
3 | 1.1.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 0% | 0d | 2015-09-30 | 2015-09-30
3 | 1.1.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 0% | 0d | 2015-10-30 | 2015-10-30
3 | 1.1.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 0% | 0d | 2015-11-30 | 2015-11-30
3 | 1.1.8 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 0% | 0d | 2016-01-26 | 2016-01-26
3 | 1.1.9 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 0% | 0d | 2015-07-24 | 2015-07-24
3 | 1.1.10 | DELIVERABLE: Review and select existing reports for review meeting | 0% | 0d | 2015-07-31 | 2015-07-31
3 | 1.1.11 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 0% | 0d | 2015-07-31 | 2015-07-31
3 | 1.1.12 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 0% | 0d | 2015-11-27 | 2015-11-27
3 | 1.1.13 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 0% | 0d | 2015-10-02 | 2015-10-02
3 | 1.1.14 | DELIVERABLE: Determine the prioritization of operating model design and rollout by risk type / function | 0% | 0d | 2015-09-25 | 2015-09-25
3 | 1.1.15 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 0% | 0d | 2015-07-17 | 2015-07-17
3 | 1.1.16 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function A (Most likely Credit) | 0% | 0d | 2016-11-09 | 2016-11-09
3 | 1.1.17 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function B (Most likely ERM + RAS + Strategic) | 0% | 0d | 2016-11-09 | 2016-11-09
3 | 1.1.18 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function C (Most likely Market & Liquidity) | 0% | 0d | 2017-01-25 | 2017-01-25
3 | 1.1.19 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function D (Most likely Compliance) | 0% | 0d | 2017-01-25 | 2017-01-25
3 | 1.1.20 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function E (Most likely Risk Management Information) | 0% | 0d | 2017-04-04 | 2017-04-04
3 | 1.1.21 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function F (Most likely Capital Risk) | 0% | 0d | 2017-04-04 | 2017-04-04
3 | 1.1.22 | DELIVERABLE: 1st Round Post Implementation Review | 0% | 0d | 2016-12-07 | 2016-12-07
3 | 1.1.23 | DELIVERABLE: 2nd Round Post Implementation Review | 0% | 0d | 2017-02-22 | 2017-02-22
3 | 1.1.24 | DELIVERABLE: 3rd Round Post Implementation Review | 0% | 0d | 2017-05-02 | 2017-05-02
3 | 1.1.25 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 0% | 0d | 2015-10-02 | 2015-10-02
3 | 1.1.26 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 0% | 0d | 2017-01-03 | 2017-01-03
3 | 1.1.27 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 0% | 0d | 2017-01-02 | 2017-01-02
3 | 1.1.28 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 0% | 0d | 2017-04-04 | 2017-04-04
3 | 1.1.29 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 0% | 0d | 2016-09-30 | 2016-09-30
2 | 1.2 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 4% | 99d | 2015-07-15 | 2015-11-30 | B. Gunn
3 | 1.2.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 62% | 13d | 2015-07-15 | 2015-07-31 | B. Gunn
4 | 1.2.1.1 | MILESTONE: Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals | 62% | 13d | 2015-07-15 | 2015-07-31
5 | 1.2.1.1.1 | Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 100% | 8d | 2015-07-15 | 2015-07-24 |  | Collect Documentation
5 | 1.2.1.1.2 | Syndicate with key stakeholders and get necessary approvals for the guiding principles | 0% | 5d | 2015-07-27 | 2015-07-31
5 | 1.2.1.1.3 | Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals complete | 0% | 0d | 2015-07-31 | 2015-07-31 | John Hennessy / Edward Smith | whether to add task for "Diagnostic of Risk Mgmt. Committee effectiveness"
3 | 1.2.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 0% | 24d | 2015-07-15 | 2015-08-15 | B. Gunn | Added according to Mck changes in the PPT and need detailed tasks
4 | 1.2.2.1 | MILESTONE: Final landscape validated with Brian | 0% | 13d | 2015-07-15 | 2015-07-31
4 | 1.2.2.2 | MILESTONE: Socialization with Chris Pfirrman, Jerry Plush, Scott Powell | 0% | 6d | 2015-07-31 | 2015-08-07
3 | 1.2.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 5% | 44d | 2015-08-01 | 2015-09-30 | B. Gunn | Chg from verb to noun; chg "determine scheme of coordination…" to "review of governance mechanism…"
4 | 1.2.3.1 | MILESTONE: Establish R&R of committees | 73% | 13d | 2015-07-15 | 2015-07-31
5 | 1.2.3.1.1 | Risk committees (draft and socialisation with Risk managers) | 100% | 8d | 2015-07-15 | 2015-07-24
5 | 1.2.3.1.2 | Non-risk committees (draft) | 100% | 8d | 2015-07-15 | 2015-07-24
5 | 1.2.3.1.3 | Socialization with key stakeholders | 0% | 6d | 2015-07-24 | 2015-07-31
5 | 1.2.3.1.4 | Establish R&R of committees complete | 0% | 0d | 2015-07-31 | 2015-07-31
4 | 1.2.3.2 | MILESTONE: Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) | 0% | 15d | 2015-07-27 | 2015-08-14
5 | 1.2.3.2.1 | Risk committees | 0% | 10d | 2015-07-27 | 2015-08-07
5 | 1.2.3.2.2 | Non-risk committees | 0% | 10d | 2015-07-27 | 2015-08-07
5 | 1.2.3.2.3 | Socialization with key stakeholders | 0% | 10d | 2015-08-03 | 2015-08-14
5 | 1.2.3.2.4 | Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) complete | 0% | 0d | 2015-08-14 | 2015-08-14
4 | 1.2.3.3 | MILESTONE: Design of charter template | 0% | 11d | 2015-07-27 | 2015-08-10
5 | 1.2.3.3.1 | Overall structure of charter | 0% | 5d | 2015-07-27 | 2015-07-31 |  | Collect Documentation
5 | 1.2.3.3.2 | Structure of the Roles and responsibilities section | 0% | 5d | 2015-07-27 | 2015-07-31 |  | Collect Documentation
5 | 1.2.3.3.3 | Socialization / alignment with Brian & Chris Pfirrman | 0% | 6d | 2015-07-31 | 2015-08-07
5 | 1.2.3.3.4 | Design of charter template complete | 0% | 0d | 2015-08-10 | 2015-08-10
4 | 1.2.3.4 | MILESTONE: Design SHUSA - Group Governance Mechanisms | 0% | 26d | 2015-07-27 | 2015-08-31
5 | 1.2.3.4.1 | Review of current documentation | 0% | 6d | 2015-07-27 | 2015-08-03
5 | 1.2.3.4.2 | Benchmark / IC of FBO's practices | 0% | 16d | 2015-07-27 | 2015-08-17
5 | 1.2.3.4.3 | Articulate High-level Governance Mechanisms | 0% | 21d | 2015-08-03 | 2015-08-31
6 | 1.2.3.4.3.1 | Articulation / formalization (in a ppt document) | 0% | 16d | 2015-08-03 | 2015-08-24
6 | 1.2.3.4.3.2 | Socialization and Brian sign-off | 0% | 6d | 2015-08-24 | 2015-08-31
5 | 1.2.3.4.4 | Design SHUSA - Group Governance Mechanisms complete | 0% | 0d | 2015-08-31 | 2015-08-31
4 | 1.2.3.5 | MILESTONE: Complete Charter Drafting | 0% | 46d | 2015-07-27 | 2015-09-28
5 | 1.2.3.5.1 | Risk Committees charters | 0% | 41d | 2015-07-27 | 2015-09-21
6 | 1.2.3.5.1.1 | Board Risk Committee and ERMC charters | 0% | 21d | 2015-07-27 | 2015-08-24
6 | 1.2.3.5.1.2 | Finalize by adding the approvals from other risk committees | 0% | 6d | 2015-09-14 | 2015-09-21
6 | 1.2.3.5.1.3 | Model Risk Management | 0% | 16d | 2015-07-27 | 2015-08-17
6 | 1.2.3.5.1.4 | Credit Risk & ALLL & Executive Credit | 0% | 21d | 2015-08-10 | 2015-09-07
6 | 1.2.3.5.1.5 | New Product | 0% | 21d | 2015-08-10 | 2015-09-07
6 | 1.2.3.5.1.6 | Compliance | 0% | 16d | 2015-08-24 | 2015-09-14
6 | 1.2.3.5.1.7 | Operational Risk | 0% | 16d | 2015-08-24 | 2015-09-14
6 | 1.2.3.5.1.8 | Market | 0% | 16d | 2015-08-24 | 2015-09-14
5 | 1.2.3.5.2 | Finance Committees charters (ALCO) | 0% | 16d | 2015-09-07 | 2015-09-28
6 | 1.2.3.5.2.1 | ALCO | 0% | 16d | 2015-09-07 | 2015-09-28
6 | 1.2.3.5.2.2 | Liquidity | 0% | 16d | 2015-09-07 | 2015-09-28
5 | 1.2.3.5.3 | Other Committees charters (Executive, HR, Comp etc.) | 0% | 31d | 2015-08-10 | 2015-09-21
6 | 1.2.3.5.3.1 | Board Committees | 0% | 16d | 2015-08-10 | 2015-08-31
6 | 1.2.3.5.3.2 | Management committees | 0% | 21d | 2015-08-24 | 2015-09-21
5 | 1.2.3.5.4 | Charter Drafting complete | 0% | 0d | 2015-09-28 | 2015-09-28
3 | 1.2.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 0% | 44d | 2015-08-01 | 2015-09-30 | B. Gunn
4 | 1.2.4.1 | MILESTONE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 0% | 44d | 2015-08-01 | 2015-09-30
5 | 1.2.4.1.1 | Document organization structure for SHUSA and subsidiaries, along with reporting lines | 0% | 44d | 2015-08-01 | 2015-09-30
5 | 1.2.4.1.2 | Define roles and responsibilities, including decision rights, escalation protocols etc. | 0% | 44d | 2015-08-01 | 2015-09-30
5 | 1.2.4.1.3 | Define reporting lines for legal and audit | 0%
5 | 1.2.4.1.4 | Document the overarching organization structure of SHUSA and its subsidiaries complete | 0% | 0d | 2015-09-30 | 2015-09-30
3 | 1.2.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 0% | 56d | 2015-07-15 | 2015-09-30 | B. Gunn
4 | 1.2.5.1 | MILESTONE: Develop policy framework, establish overall policies including guidelines for approval of policies | 0% | 56d | 2015-07-15 | 2015-09-30
5 | 1.2.5.1.1 | Establish overarching Policy Framework including guidelines for approval | 0% | 21d | 2015-07-15 | 2015-08-12
5 | 1.2.5.1.2 | Establish prioritized policies and procedures across functions | 0% | 56d | 2015-07-15 | 2015-09-30
5 | 1.2.5.1.3 | Develop policy framework, establish overall policies including guidelines for approval of policies complete | 0% | 0d | 2015-09-30 | 2015-09-30
3 | 1.2.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 0% | 23d | 2015-10-01 | 2015-10-31 | B. Gunn
4 | 1.2.6.1 | MILESTONE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 0% | 23d | 2015-10-01 | 2015-10-31
5 | 1.2.6.1.1 | Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 0% | 23d | 2015-10-01 | 2015-10-31
5 | 1.2.6.1.2 | Define priority reports for each function across SHUSA and its subsidiaries | 0% | 23d | 2015-10-01 | 2015-10-31
5 | 1.2.6.1.3 | Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries complete | 0% | 0d | 2015-10-31 | 2015-10-31
3 | 1.2.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 0% | 22d | 2015-11-01 | 2015-11-30 | B. Gunn
4 | 1.2.7.1 | MILESTONE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 0% | 22d | 2015-11-01 | 2015-11-30
5 | 1.2.7.1.1 | Syndicate with subsidiaries, and refine framework document | 0% | 17d | 2015-11-01 | 2015-11-22
5 | 1.2.7.1.2 | Get approvals from SHUSA and subsidiary Boards | 0% | 7d | 2015-11-22 | 2015-11-29
5 | 1.2.7.1.3 | Syndicate Governance and Oversight Framework document Complete | 0% | 0d | 2015-11-29 | 2015-11-29
2 | 1.3 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 0% | 45d | 2015-12-01 | 2016-01-31 | B. Gunn
3 | 1.3.1 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 0% | 41d | 2015-12-01 | 2016-01-26
4 | 1.3.1.1 | Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 0% | 31d | 2015-12-01 | 2016-01-12
4 | 1.3.1.2 | Synthesize key gaps and syndicate with stakeholders | 0% | 11d | 2016-01-12 | 2016-01-26
4 | 1.3.1.3 | Conduct gap analysis Complete | 0% | 0d | 2016-01-26 | 2016-01-26
3 | 1.3.2 | Establish comprehensive implementation plans to address these gaps over a multi-year period | 0% | 21d | 2016-01-04 | 2016-01-31
2 | 1.4 | Execute against multi-year plan for Risk Transformation | 0% |  | 2016-02-01
2 | 1.5 | Implement routine Risk-Business reviews with standardized materials and reports | 50% | 15d | 2015-07-13 | 2015-07-31
3 | 1.5.1 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 83% | 10d | 2015-07-13 | 2015-07-24 | B. Gunn
4 | 1.5.1.1 | MILESTONE: Review meeting cadence, attendees and agenda established | 83% | 10d | 2015-07-13 | 2015-07-24
5 | 1.5.1.1.1 | Identify review meeting attendees | 100% | 10d | 2015-07-13 | 2015-07-24
5 | 1.5.1.1.2 | Establish review meeting calendar | 100% | 10d | 2015-07-13 | 2015-07-24 |  | Collect Documentation
5 | 1.5.1.1.3 | Define review meeting agenda | 50% | 10d | 2015-07-13 | 2015-07-24 |  | Collect Documentation
3 | 1.5.2 | DELIVERABLE: Review and select existing reports for review meeting | 0% | 10d | 2015-07-20 | 2015-07-31 | B. Gunn
4 | 1.5.2.1 | MILESTONE: Existing reports reviewed and selected | 0% | 10d | 2015-07-20 | 2015-07-31
5 | 1.5.2.1.1 | Review existing risk reports | 0% | 10d | 2015-07-20 | 2015-07-31
5 | 1.5.2.1.2 | Selecty existing reports | 0% | 10d | 2015-07-20 | 2015-07-31
5 | 1.5.2.1.3 | Implement Routine Risk-Business reviews with standardized materials and reports | 0% | 0d | 2015-07-31 | 2015-07-31
2 | 1.6 | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 0% | 130d | 2015-07-13 | 2016-01-08 |  | Need further discussion to finalize
2 | 1.7 | Assessment and Enhancement to Existing Risk Management Performance Scorecards | 0% | 135d | 2015-06-15 | 2015-12-18 | B. Gunn/C. Briongos | Separated from "Strengthen Board and Management Committee Oversight"
3 | 1.7.1 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 0% | 35d | 2015-06-15 | 2015-08-03 | B. Gunn/C. Briongos | included from legacy CEP plan; need to justify / coordinate with the (round 2) enhancements below
4 | 1.7.1.1 | MILESTONE: Quick Win Enhancements to existing Risk Management Performance Scorecards | 0% | 35d | 2015-06-15 | 2015-08-03
5 | 1.7.1.1.1 | Submit 1st Submission of Year to Date Figures from Data Feed Owners | 0% | 19d | 2015-06-15 | 2015-07-09
5 | 1.7.1.1.2 | Create Mid Year RMPS to Share with Managers | 0% | 16d | 2015-07-10 | 2015-07-31 |  | Collect Documentation
5 | 1.7.1.1.3 | Quick Win Enhancements to existing Risk Management Performance Scorecards Complete | 0% | 0d | 2015-08-03 | 2015-08-03
3 | 1.7.2 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 0% | 20d | 2015-11-02 | 2015-11-27 | B. Gunn/C. Briongos | need to justify / coordinate with the quick win enhancements above
4 | 1.7.2.1 | MILESTONE: Enhance Performance Scorecards | 0% | 20d | 2015-11-02 | 2015-11-27
5 | 1.7.2.1.1 | Perform high level assessment and remediation of performance scorecards | 0% | 20d | 2015-11-02 | 2015-11-27
5 | 1.7.2.1.2 | Assessment and Remediation of Performance Scorecards Complete | 0% | 0d | 2015-11-27 | 2015-11-27
2 | 1.8 | Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 0% | 45d | 2015-08-03 | 2015-10-02 | B. Gunn
3 | 1.8.1 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 0% | 45d | 2015-08-03 | 2015-10-02 | B. Gunn | Chg verb to noun; deleted "submitted to CRO for approval", chg to "CRO-approved Risk org charts…"
4 | 1.8.1.1 | MILESTONE: Risk organizational structure charts and subsidiary reporting schemes submitted to and approved by CRO (SHUSA) | 0% | 45d | 2015-08-03 | 2015-10-02 |  | Ops Risk
5 | 1.8.1.1.1 | Formalize subsidiary CRO reporting lines, socialize and refine solution (SHUSA) | 0% | 10d | 2015-08-03 | 2015-08-14
5 | 1.8.1.1.2 | Define implications of reporting lines (for Performance assessment and hiring/firing authority) (SHUSA) | 0% | 10d | 2015-08-10 | 2015-08-21
5 | 1.8.1.1.3 | Design 1st LoD Risk organization leadership structure including the role of RCO (SHUSA) | 0% | 25d | 2015-08-03 | 2015-09-04
5 | 1.8.1.1.4 | Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 0% | 0d | 2015-10-02 | 2015-10-02
2 | 1.9 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 0% | 487d | 2015-06-22 | 2017-05-02 | B. Gunn | Ops Risk
3 | 1.9.1 | DELIVERABLE: Determine the prioritization of operating model design and rollout by risk type / function | 0% | 45d | 2015-08-03 | 2015-10-02 | B. Gunn | Should this take 1 month?
4 | 1.9.1.1 | Confirm Risk type / function A & B | 0% | 1d | 2015-08-03 | 2015-08-03
4 | 1.9.1.2 | Confirm Risk type / function C, D, E, & F | 0% | 1d | 2015-09-25 | 2015-09-25
4 | 1.9.1.3 | TOM Design Determined by risk type/function | 0% | 0d | 2015-09-25 | 2015-09-25
3 | 1.9.2 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 75% | 20d | 2015-06-22 | 2015-07-17
3 | 1.9.3 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function A (Most likely Credit) | 0% | 313d | 2015-08-31 | 2016-11-09 | B. Gunn
4 | 1.9.3.1 | MILESTONE: Design detailed operating model and implementation plans for Risk type / function A (Most likely Credit) | 0% | 313d | 2015-08-31 | 2016-11-09
5 | 1.9.3.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 25d | 2015-08-31 | 2015-10-02 |  | Chg: "org. structure with aligned talent assessment and development" to "…org structure, perform talent assessment and identify development needs."
5 | 1.9.3.1.2 | Develop rollout plan | 0% | 25d | 2015-10-05 | 2015-11-06
5 | 1.9.3.1.3 | MILESTONE | 0% | 0d | 2015-11-06 | 2015-11-06
5 | 1.9.3.1.4 | Implement Risk Type A/Function (Most likely Credit) Framework at SHUSA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.3.1.5 | Implement Risk Type A/Function (Most likely Credit) Framework at SBNA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.3.1.6 | Implement Risk Type A/Function (Most likely Credit) Framework at SCUSA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.3.1.7 | Risk Type A/Function (Most likely Credit) Framework Implemented at SHUSA, SBNA, and SCUSA | 0% | 0d | 2016-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.4 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function B (Most likely ERM + RAS + Strategic) | 0% | 313d | 2015-08-31 | 2016-11-09 | B. Gunn
4 | 1.9.4.1 | MILESTONE: Risk type / function B (Most likely ERM + RAS + Strategic) | 0% | 313d | 2015-08-31 | 2016-11-09
5 | 1.9.4.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 25d | 2015-08-31 | 2015-10-02 |  | Chg: "org. structure with aligned talent assessment and development" to "…org structure, perform talent assessment and identify development needs."
5 | 1.9.4.1.2 | Develop rollout plan | 0% | 25d | 2015-10-05 | 2015-11-06
5 | 1.9.4.1.3 | MILESTONE | 0% | 0d | 2015-11-06 | 2015-11-06
5 | 1.9.4.1.4 | Implement Risk Type B/Function (Most likely ERM + RAS + Strategic)) Framework at SHUSA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.4.1.5 | Implement Risk Type B/Function (Most likely ERM + RAS + Strategic) Framework at SBNA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.4.1.6 | Implement Risk Type B/Function (Most likely ERM + RAS + Strategic) Framework at SCUSA | 0% | 263d | 2015-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.4.1.7 | Risk Type B/Function (Most likely ERM + RAS + Strategic) Framework Implemented at SHUSA, SBNA, and SCUSA | 0% | 0d | 2016-11-09 | 2016-11-09 |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.5 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function C (Most likely Market & Liquidity) | 0% | 313d | 2015-11-16 | 2017-01-25 | B. Gunn
4 | 1.9.5.1 | MILESTONE: Risk type / function C (Most likely Market & Liquidity) | 0% | 313d | 2015-11-16 | 2017-01-25
5 | 1.9.5.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 25d | 2015-11-16 | 2015-12-18
5 | 1.9.5.1.2 | Develop rollout plan | 0% | 25d | 2015-12-21 | 2016-01-22 |  | Chg: "org. structure with aligned talent assessment and development" to "…org structure, perform talent assessment and identify development needs."
5 | 1.9.5.1.3 | MILESTONE | 0% | 0d | 2016-01-22 | 2016-01-22
5 | 1.9.5.1.4 | Implement Risk Type C (Most likely Market & Liquidity)/Function Framework at SHUSA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.5.1.5 | Implement Risk Type C (Most likely Market & Liquidity)/Function Framework at SBNA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.5.1.6 | Implement Risk Type C (Most likely Market & Liquidity)/Function Framework at SCUSA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.5.1.7 | Risk Type C (Most Likely Market & Liquidity)/Function at SHUSA, SBNA, SCUSA Implemented | 0% | 0d | 2017-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.6 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function D (Most likely Compliance) | 0% | 313d | 2015-11-16 | 2017-01-25 | B. Gunn
4 | 1.9.6.1 | MILESTONE: Risk type / function D (Most likely Compliance) | 0% | 313d | 2015-11-16 | 2017-01-25
5 | 1.9.6.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 25d | 2015-11-16 | 2015-12-18
5 | 1.9.6.1.2 | Develop rollout plan | 0% | 25d | 2015-12-21 | 2016-01-22
5 | 1.9.6.1.3 | MILESTONE | 0% | 0d | 2016-01-22 | 2016-01-22
5 | 1.9.6.1.4 | Implement Risk Type D (Most likely Compliance)/Function Framework at SHUSA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.6.1.5 | Implement Risk Type D (Most likely Compliance)/Function Framework at SBNA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.6.1.6 | Implement Risk Type D (Most likely Compliance)/Function Framework at SCUSA | 0% | 263d | 2016-01-25 | 2017-01-25 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.6.1.7 | Risk Type D (Most Likely Compliance)/Function at SHUSA, SBNA, SCUSA Implemented | 0% | 0d | 2017-01-25 | 2017-01-25
3 | 1.9.7 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function E (Most likely Risk Management Information) | 0% | 307d | 2016-02-01 | 2017-04-04 | B. Gunn
4 | 1.9.7.1 | MILESTONE: Risk type / function E (Most likely Risk Management Information) | 0% | 307d | 2016-02-01 | 2017-04-04
5 | 1.9.7.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 22d | 2016-02-01 | 2016-03-01
5 | 1.9.7.1.2 | Develop rollout plan | 0% | 23d | 2016-03-02 | 2016-04-01
5 | 1.9.7.1.3 | MILESTONE | 0% | 0d | 2016-04-01 | 2016-04-01
5 | 1.9.7.1.4 | Implement Risk Type E (Most likely Risk Management Information)/Function Framework at SHUSA, SBNA, and SCUSA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.7.1.5 | Implement Risk Type E (Most likely Risk Management Information)/Function Framework at SHUSA, SBNA, and SCUSA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.7.1.6 | Implement Risk Type E (Most likely Risk Management Information)/Function Framework at SHUSA, SBNA, and SCUSA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.7.1.7 | Risk Type E (Most likely Risk Management Information)/Function Framework at SHUSA, SBNA, and SCUSA Implemented | 0% | 0d | 2017-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.8 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function F (Most likely Capital Risk) | 0% | 307d | 2016-02-01 | 2017-04-04 | B. Gunn
4 | 1.9.8.1 | MILESTONE: Risk type / function F (Most likely Capital Risk) | 0% | 307d | 2016-02-01 | 2017-04-04
5 | 1.9.8.1.1 | Define detailed organizational structure and assess talent needs including target headcounts and skill sets | 0% | 22d | 2016-02-01 | 2016-03-01
5 | 1.9.8.1.2 | Develop rollout plan | 0% | 23d | 2016-03-02 | 2016-04-01
5 | 1.9.8.1.3 | MILESTONE | 0% | 0d | 2016-04-01 | 2016-04-01
5 | 1.9.8.1.4 | Implement Risk Type F (Most likely Capital Risk)/Function Framework at SHUSA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.8.1.5 | Implement Risk Type F (Most likely Capital Risk)/Function Framework at SBNA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.8.1.6 | Implement Risk Type F (Most likely Capital Risk)/Function Framework at SCUSA | 0% | 262d | 2016-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
5 | 1.9.8.1.7 | Risk Type F (Most likely Capital Risk)/Function Framework at SHUSA, SBNA, and SCUSA Implemented | 0% | 0d | 2017-04-04 | 2017-04-04 |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.9 | Implement the redesigned Operating Model for each Risk Type/Function | 0% | 367d | 2015-11-09 | 2017-04-04 | B. Gunn
3 | 1.9.10 | DELIVERABLE: 1st Round Post Implementation Review | 0% | 20d | 2016-11-10 | 2016-12-07 | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.10.1 | MILESTONE: 1st Round Post Implementation Review Conducted | 0% | 20d | 2016-11-10 | 2016-12-07
5 | 1.9.10.1.1 | Post Implementation Review (First Round) | 0% | 20d | 2016-11-10 | 2016-12-07
5 | 1.9.10.1.2 | MILESTONE: 1st Round Post Implementation Review Conducted | 0% | 0d | 2016-12-07 | 2016-12-07
3 | 1.9.11 | DELIVERABLE: 2nd Round Post Implementation Review | 0% | 20d | 2017-01-26 | 2017-02-22 | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.11.1 | MILESTONE: 2nd Round Post Implementation Review Conducted | 0% | 20d | 2017-01-26 | 2017-02-22
5 | 1.9.11.1.1 | Post Implementation Review (Second Round) | 0% | 20d | 2017-01-26 | 2017-02-22
5 | 1.9.11.1.2 | MILESTONE: 2nd Round Post Implementation Review Conducted | 0% | 0d | 2017-02-22 | 2017-02-22 |  | Corrected dates
3 | 1.9.12 | DELIVERABLE: 3rd Round Post Implementation Review | 0% | 20d | 2017-04-05 | 2017-05-02 | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.12.1 | MILESTONE: 3rd Round Post Implementation Review Conducted | 0% | 20d | 2017-04-05 | 2017-05-02
5 | 1.9.12.1.1 | Post Implementation Review (Third Round) | 0% | 20d | 2017-04-05 | 2017-05-02
5 | 1.9.12.1.2 | MILESTONE: 3rd Round Post Implementation Review Conducted | 0% | 0d | 2017-05-02 | 2017-05-02
3 | 1.9.13 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 0% | 45d | 2015-08-03 | 2015-10-02 | B. Gunn | Chg verb to noun
4 | 1.9.13.1 | MILESTONE: Strong and Desired Risk Culture Defined | 0% | 45d | 2015-08-03 | 2015-10-02
5 | 1.9.13.1.1 | Determine the survey population and tailor survey as needed (1 week) | 0% | 5d | 2015-08-03 | 2015-08-07
5 | 1.9.13.1.2 | Deploy culture survey and collect responses (2-3 week) | 0% | 15d | 2015-08-03 | 2015-08-21
5 | 1.9.13.1.3 | Aggregate and analyze survey results (2-3 weeks) | 0% | 15d | 2015-08-24 | 2015-09-11
5 | 1.9.13.1.4 | Conduct 3-4 targeted focus groups or workshops to refine and validate the insights (1-2 weeks) - goes in parallel with 3. | 0% | 15d | 2015-08-31 | 2015-09-18
5 | 1.9.13.1.5 | Review findings, document current state risk culture and priritize focus areas (1 week) | 0% | 10d | 2015-09-21 | 2015-10-02
5 | 1.9.13.1.6 | MILESTONE: Strong and Desired Risk Culture Defined | 0% | 0d | 2016-10-02 | 2016-10-02 |  | Chg "Instilled" to "Defined"
2 | 1.1 | Long Term Planning Package | 0% | 312d? | 2016-01-25 | 2017-04-04
3 | 1.10.1 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 0% | 197d? | 2016-04-01 | 2017-01-02 | B. Gunn/C. Briongos | Chg verb to noun; Chg "rollout…" to "Introduction of…"
4 | 1.10.1.1 | MILESTONE: Design risk-based compensation framework | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.1.1.1 | Benchmark of risk-based compensation practices in the industry | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.1.1.2 | Risk-based compensation proposals and refinement with stakeholders | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.1.1.3 | Impact analysis of new frameworks on compensation levels | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.1.1.4 | Formalization of new risk-based compensation framework | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.1.1.5 | Risk-based compensation structure formalized | 0% | 0d | 2016-06-30 | 2016-06-30 |  | Chg "complete" to "formalized"; do not want to reflect that structure is complete
4 | 1.10.1.2 | MILESTONE: Communication and stakeholder engagement | 0% | 131d? | 2016-04-01 | 2016-09-30
5 | 1.10.1.2.1 | Design of communication plan | 0% | 65d? | 2016-04-01 | 2016-06-30
5 | 1.10.1.2.2 | Development of communication materials | 0% | 65d? | 2016-04-01 | 2016-06-30 |  | Chg "writing" to "development"
5 | 1.10.1.2.3 | Execution of communication plan | 0% | 67d? | 2016-06-30 | 2016-09-30
5 | 1.10.1.2.4 | Stakeholder communication complete | 0% | 0d | 2016-09-30 | 2016-09-30
4 | 1.10.1.3 | MILESTONE: Updates to performance assessment templates | 0% | 132d? | 2016-07-01 | 2017-01-02
5 | 1.10.1.3.1 | Inventory of performance assessment templates at SHUSA, SBNA and SCUSA | 0% | 66d? | 2016-07-01 | 2016-09-30
5 | 1.10.1.3.2 | Update of template in accordance with risk-based compensation framework | 0% | 66d? | 2016-07-01 | 2016-09-30
5 | 1.10.1.3.3 | Socialization, training of stakeholders and roll-out of new templates | 0% | 67d? | 2016-09-30 | 2017-01-02 |  | Chg "training to" to "training of"
5 | 1.10.1.3.4 | Performance assessment templates updated | 0% | 0d | 2016-12-31 | 2016-12-31
3 | 1.10.2 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 0% |  | 2016-01-25 |  | B. Gunn
4 | 1.10.2.1 | MILESTONE: Communications to emphasize progress being made / share best practices | 0% | 65d | 2016-01-25 | 2016-04-22
5 | 1.10.2.1.1 | Assessment of progress being made & best practices | 0% | 65d | 2016-01-25 | 2016-04-22
5 | 1.10.2.1.2 | Design of communication plan | 0% | 65d | 2016-01-25 | 2016-04-22
5 | 1.10.2.1.3 | Development of communications materials | 0% | 65d | 2016-01-25 | 2016-04-22
5 | 1.10.2.1.4 | Delivery of communication plan | 0% | 65d | 2016-01-25 | 2016-04-22
5 | 1.10.2.1.5 | Progress communications delivered | 0% | 0d | 2016-03-31 | 2016-03-31
4 | 1.10.2.2 | MILESTONE: Convey organizational changes to the enterprise | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.2.2.1 | Development of materials | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.2.2.2 | Delivery of communication to stakeholders | 0% | 65d | 2016-04-01 | 2016-06-30
5 | 1.10.2.2.3 | Organizational changes communicated to enterprise | 0% | 0d | 2016-06-30 | 2016-06-30
4 | 1.10.2.3 | MILESTONE: Enterprise-wide training and development of job descriptions with explicit focus on three lines of defense | 0% | 132d? | 2016-07-01 | 2017-01-02
5 | 1.10.2.3.1 | Design of training curriculum & idenfification of key recepients as a result of post-implementation reviews | 0% | 66d? | 2016-07-01 | 2016-09-30
5 | 1.10.2.3.2 | Development of training materials | 0% | 66d? | 2016-07-01 | 2016-09-30
5 | 1.10.2.3.3 | Delivery of training to priority recipients | 0% | 67d? | 2016-09-30 | 2017-01-02
5 | 1.10.2.3.4 | Identification of key functions requiring job description updates | 0% | 66d? | 2016-07-01 | 2016-09-30
5 | 1.10.2.3.5 | Development of job descriptions with explicit focus on three lines of defense | 0% | 67d? | 2016-09-30 | 2017-01-02
5 | 1.10.2.3.6 | Job descriptions complete and enterprise-wide training delivered | 0% | 0d | 2016-12-31 | 2016-12-31
3 | 1.10.3 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 0% | 198d? | 2016-07-01 | 2017-04-04 | B. Gunn/C. Briongos | Chg verb to noun
4 | 1.10.3.1 | MILESTONE: Design recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 0% | 66d | 2016-07-01 | 2016-09-30 |  | Chg noun to verb
5 | 1.10.3.1.1 | Diagnostic of retention challenges | 0% | 66d | 2016-07-01 | 2016-09-30
5 | 1.10.3.1.2 | Design of new possible retention mechanisms | 0% | 66d | 2016-07-01 | 2016-09-30
5 | 1.10.3.1.3 | Milestone: Design of new possible retention mechanisms complete | 0% | 0d | 2016-09-30 | 2016-09-30 |  | Added "possible"
4 | 1.10.3.2 | MILESTONE: Action plans for necessary remediation efforts | 0% | 132d? | 2016-10-03 | 2017-04-04
5 | 1.10.3.2.1 | Selection of key remediation initiatives with key stakeholders | 0% | 68d? | 2016-10-03 | 2017-01-04
5 | 1.10.3.2.2 | Planning of initiatives between SHUSA and its subsidiaries | 0% | 68d? | 2016-10-03 | 2017-01-04
5 | 1.10.3.2.3 | Rollout of initiatives at SHUSA | 0% | 68d? | 2016-10-03 | 2017-01-04
5 | 1.10.3.2.4 | Rollout of initiatives at other subsidiaries | 0% | 67d | 2017-01-02 | 2017-04-04
5 | 1.10.3.2.5 | Recruitment and retention intiatives introduced throughout enterprise | 0% | 0d | 2017-03-31 | 2017-03-31
3 | 1.10.4 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 0% | 66d | 2016-07-01 | 2016-09-30 | B. Gunn | Chg verb to noun
4 | 1.10.4.1 | MILESTONE: Create multi-year plan that describes interventions | 0% | 66d | 2016-07-01 | 2016-09-30
4 | 1.10.4.2 | MILESTONE: Syndicate plan with key stakeholders and get approvals | 0% | 66d | 2016-07-01 | 2016-09-30
4 | 1.10.4.3 | MILESTONE: Diagnostics of risk culture; multi-year plan to achieve premier risk culture in place | 0% | 0d | 2016-09-30 | 2016-09-30 |  | Chg "Ongoing diagnostics" to "Diagnostics"; "development of multi-year plan" to "multi-year plan"; intent was to remove indefinite terminology from a milestone

## New
Outline Level | WBS | Task Name | Start | Finish | Duration | % Complete | Contact | Notes | Updated Notes
0 | 0 | Risk Transformation | 2015-06-15 | 2017-05-02 | 492d? | 2%
1 | 1 | Risk Governance & Organization | 2015-06-15 | 2017-05-02 | 492d? | 2%
2 | 1.1 | Risk Governance & Organization Deliverables | 2015-07-17 | 2017-05-02 | 467d | 0%
3 | 1.1.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 2015-07-31 | 2015-07-31 | 0d | 0%
3 | 1.1.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 2015-08-15 | 2015-08-15 | 0d | 0%
3 | 1.1.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-09-30 | 2015-09-30 | 0d | 0%
3 | 1.1.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-09-30 | 2015-09-30 | 0d | 0%
3 | 1.1.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-09-30 | 2015-09-30 | 0d | 0%
3 | 1.1.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-30 | 2015-10-30 | 0d | 0%
3 | 1.1.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-30 | 2015-11-30 | 0d | 0%
3 | 1.1.8 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2016-01-26 | 2016-01-26 | 0d | 0%
3 | 1.1.9 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 2015-07-24 | 2015-07-24 | 0d | 0%
3 | 1.1.10 | DELIVERABLE: Review and select existing reports for review meeting | 2015-07-31 | 2015-07-31 | 0d | 0%
3 | 1.1.11 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 2015-07-31 | 2015-07-31 | 0d | 0%
3 | 1.1.12 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 2015-11-27 | 2015-11-27 | 0d | 0%
3 | 1.1.13 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 2015-10-02 | 2015-10-02 | 0d | 0%
3 | 1.1.14 | DELIVERABLE: Determine the prioritization of operating model design and rollout by risk type / function | 2015-09-25 | 2015-09-25 | 0d | 0%
3 | 1.1.15 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 2015-07-17 | 2015-07-17 | 0d | 0%
3 | 1.1.16 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function A (Most likely Credit) | 2016-11-09 | 2016-11-09 | 0d | 0%
3 | 1.1.17 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function B (Most likely ERM + RAS + Strategic) | 2016-11-09 | 2016-11-09 | 0d | 0%
3 | 1.1.18 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function C (Most likely Market & Liquidity) | 2017-01-25 | 2017-01-25 | 0d | 0%
3 | 1.1.19 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function D (Most likely Compliance) | 2017-01-25 | 2017-01-25 | 0d | 0%
3 | 1.1.20 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function E (Most likely Risk Management Information) | 2017-04-04 | 2017-04-04 | 0d | 0%
3 | 1.1.21 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function F (Most likely Capital Risk) | 2017-04-04 | 2017-04-04 | 0d | 0%
3 | 1.1.22 | DELIVERABLE: 1st Round Post Implementation Review | 2016-12-07 | 2016-12-07 | 0d | 0%
3 | 1.1.23 | DELIVERABLE: 2nd Round Post Implementation Review | 2017-02-22 | 2017-02-22 | 0d | 0%
3 | 1.1.24 | DELIVERABLE: 3rd Round Post Implementation Review | 2017-05-02 | 2017-05-02 | 0d | 0%
3 | 1.1.25 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2015-10-02 | 2015-10-02 | 0d | 0%
3 | 1.1.26 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2017-01-03 | 2017-01-03 | 0d | 0%
3 | 1.1.27 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2017-01-02 | 2017-01-02 | 0d | 0%
3 | 1.1.28 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2017-04-04 | 2017-04-04 | 0d | 0%
3 | 1.1.29 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-09-30 | 2016-09-30 | 0d | 0%
2 | 1.2 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | 99d | 4% | B. Gunn
3 | 1.2.1 | DELIVERABLE: Establish core principles for governance and oversight of SHUSA and its subsidiaries, including role of and interactions with the holding company | 2015-07-15 | 2015-07-31 | 13d | 62% | B. Gunn
4 | 1.2.1.1 | MILESTONE: Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals | 2015-07-15 | 2015-07-31 | 13d | 62%
5 | 1.2.1.1.1 | Document guiding principles and foundational elements (e.g., business ownership of risks, lines of defense, shared services, RAS, Board and management respective R&R etc.) | 2015-07-15 | 2015-07-24 | 8d | 100% |  | Collect Documentation
5 | 1.2.1.1.2 | Syndicate with key stakeholders and get necessary approvals for the guiding principles | 2015-07-27 | 2015-07-31 | 5d | 0%
5 | 1.2.1.1.3 | Establish core principles for governance and oversight of SHUSA and its subsidiaries and obtain approvals complete | 2015-07-31 | 2015-07-31 | 0d | 0% | John Hennessy / Edward Smith | whether to add task for "Diagnostic of Risk Mgmt. Committee effectiveness"
3 | 1.2.2 | DELIVERABLE: Define target state committee structure including Board and Management committees | 2015-07-15 | 2015-08-15 | 24d | 0% | B. Gunn | Added according to Mck changes in the PPT and need detailed tasks
4 | 1.2.2.1 | MILESTONE: Final landscape validated with Brian | 2015-07-15 | 2015-07-31 | 13d | 0%
4 | 1.2.2.2 | MILESTONE: Socialization with Chris Pfirrman, Jerry Plush, Scott Powell | 2015-07-31 | 2015-08-07 | 6d | 0%
3 | 1.2.3 | DELIVERABLE: Articulate committee compositions, roles, decision rights, delegation of authority and distribution of responsibilities between the Group, SHUSA and its subsidiaries | 2015-08-01 | 2015-09-30 | 44d | 5% | B. Gunn | Chg from verb to noun; chg "determine scheme of coordination…" to "review of governance mechanism…"
4 | 1.2.3.1 | MILESTONE: Establish R&R of committees | 2015-07-15 | 2015-07-31 | 13d | 73%
5 | 1.2.3.1.1 | Risk committees (draft and socialisation with Risk managers) | 2015-07-15 | 2015-07-24 | 8d | 100%
5 | 1.2.3.1.2 | Non-risk committees (draft) | 2015-07-15 | 2015-07-24 | 8d | 100%
5 | 1.2.3.1.3 | Socialization with key stakeholders | 2015-07-24 | 2015-07-31 | 6d | 0%
5 | 1.2.3.1.4 | Establish R&R of committees complete | 2015-07-31 | 2015-07-31 | 0d | 0%
4 | 1.2.3.2 | MILESTONE: Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) | 2015-07-27 | 2015-08-14 | 15d | 0%
5 | 1.2.3.2.1 | Risk committees | 2015-07-27 | 2015-08-07 | 10d | 0%
5 | 1.2.3.2.2 | Non-risk committees | 2015-07-27 | 2015-08-07 | 10d | 0%
5 | 1.2.3.2.3 | Socialization with key stakeholders | 2015-08-03 | 2015-08-14 | 10d | 0%
5 | 1.2.3.2.4 | Establish High-level R&R of SHUSA committees vs. subsidiaries Committees (linked to TOM) complete | 2015-08-14 | 2015-08-14 | 0d | 0%
4 | 1.2.3.3 | MILESTONE: Design of charter template | 2015-07-27 | 2015-08-10 | 11d | 0%
5 | 1.2.3.3.1 | Overall structure of charter | 2015-07-27 | 2015-07-31 | 5d | 0% |  | Collect Documentation
5 | 1.2.3.3.2 | Structure of the Roles and responsibilities section | 2015-07-27 | 2015-07-31 | 5d | 0% |  | Collect Documentation
5 | 1.2.3.3.3 | Socialization / alignment with Brian & Chris Pfirrman | 2015-07-31 | 2015-08-07 | 6d | 0%
5 | 1.2.3.3.4 | Design of charter template complete | 2015-08-10 | 2015-08-10 | 0d | 0%
4 | 1.2.3.4 | MILESTONE: Design SHUSA - Group Governance Mechanisms | 2015-07-27 | 2015-08-31 | 26d | 0%
5 | 1.2.3.4.1 | Review of current documentation | 2015-07-27 | 2015-08-03 | 6d | 0%
5 | 1.2.3.4.2 | Benchmark / IC of FBO's practices | 2015-07-27 | 2015-08-17 | 16d | 0%
5 | 1.2.3.4.3 | Articulate High-level Governance Mechanisms | 2015-08-03 | 2015-08-31 | 21d | 0%
6 | 1.2.3.4.3.1 | Articulation / formalization (in a ppt document) | 2015-08-03 | 2015-08-24 | 16d | 0%
6 | 1.2.3.4.3.2 | Socialization and Brian sign-off | 2015-08-24 | 2015-08-31 | 6d | 0%
5 | 1.2.3.4.4 | Design SHUSA - Group Governance Mechanisms complete | 2015-08-31 | 2015-08-31 | 0d | 0%
4 | 1.2.3.5 | MILESTONE: Complete Charter Drafting | 2015-07-27 | 2015-09-28 | 46d | 0%
5 | 1.2.3.5.1 | Risk Committees charters | 2015-07-27 | 2015-09-21 | 41d | 0%
6 | 1.2.3.5.1.1 | Board Risk Committee and ERMC charters | 2015-07-27 | 2015-08-24 | 21d | 0%
6 | 1.2.3.5.1.2 | Finalize by adding the approvals from other risk committees | 2015-09-14 | 2015-09-21 | 6d | 0%
6 | 1.2.3.5.1.3 | Model Risk Management | 2015-07-27 | 2015-08-17 | 16d | 0%
6 | 1.2.3.5.1.4 | Credit Risk & ALLL & Executive Credit | 2015-08-10 | 2015-09-07 | 21d | 0%
6 | 1.2.3.5.1.5 | New Product | 2015-08-10 | 2015-09-07 | 21d | 0%
6 | 1.2.3.5.1.6 | Compliance | 2015-08-24 | 2015-09-14 | 16d | 0%
6 | 1.2.3.5.1.7 | Operational Risk | 2015-08-24 | 2015-09-14 | 16d | 0%
6 | 1.2.3.5.1.8 | Market | 2015-08-24 | 2015-09-14 | 16d | 0%
5 | 1.2.3.5.2 | Finance Committees charters (ALCO) | 2015-09-07 | 2015-09-28 | 16d | 0%
6 | 1.2.3.5.2.1 | ALCO | 2015-09-07 | 2015-09-28 | 16d | 0%
6 | 1.2.3.5.2.2 | Liquidity | 2015-09-07 | 2015-09-28 | 16d | 0%
5 | 1.2.3.5.3 | Other Committees charters (Executive, HR, Comp etc.) | 2015-08-10 | 2015-09-21 | 31d | 0%
6 | 1.2.3.5.3.1 | Board Committees | 2015-08-10 | 2015-08-31 | 16d | 0%
6 | 1.2.3.5.3.2 | Management committees | 2015-08-24 | 2015-09-21 | 21d | 0%
5 | 1.2.3.5.4 | Charter Drafting complete | 2015-09-28 | 2015-09-28 | 0d | 0%
3 | 1.2.4 | DELIVERABLE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 0% | B. Gunn
4 | 1.2.4.1 | MILESTONE: Document the overarching organization structure of SHUSA and its subsidiaries including reporting lines | 2015-08-01 | 2015-09-30 | 44d | 0%
5 | 1.2.4.1.1 | Document organization structure for SHUSA and subsidiaries, along with reporting lines | 2015-08-01 | 2015-09-30 | 44d | 0%
5 | 1.2.4.1.2 | Define roles and responsibilities, including decision rights, escalation protocols etc. | 2015-08-01 | 2015-09-30 | 44d | 0%
5 | 1.2.4.1.3 | Define reporting lines for legal and audit |  |  |  | 0%
5 | 1.2.4.1.4 | Document the overarching organization structure of SHUSA and its subsidiaries complete | 2015-09-30 | 2015-09-30 | 0d | 0%
3 | 1.2.5 | DELIVERABLE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 0% | B. Gunn
4 | 1.2.5.1 | MILESTONE: Develop policy framework, establish overall policies including guidelines for approval of policies | 2015-07-15 | 2015-09-30 | 56d | 0%
5 | 1.2.5.1.1 | Establish overarching Policy Framework including guidelines for approval | 2015-07-15 | 2015-08-12 | 21d | 0%
5 | 1.2.5.1.2 | Establish prioritized policies and procedures across functions | 2015-07-15 | 2015-09-30 | 56d | 0%
5 | 1.2.5.1.3 | Develop policy framework, establish overall policies including guidelines for approval of policies complete | 2015-09-30 | 2015-09-30 | 0d | 0%
3 | 1.2.6 | DELIVERABLE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0% | B. Gunn
4 | 1.2.6.1 | MILESTONE: Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0%
5 | 1.2.6.1.1 | Create the overall reporting framework - core principles, cadence and rhythm of reporting, broad definition of report types (production reports vs. custom reports) | 2015-10-01 | 2015-10-31 | 23d | 0%
5 | 1.2.6.1.2 | Define priority reports for each function across SHUSA and its subsidiaries | 2015-10-01 | 2015-10-31 | 23d | 0%
5 | 1.2.6.1.3 | Create overarching reporting framework for the Board and Management for SHUSA and its subsidiaries complete | 2015-10-31 | 2015-10-31 | 0d | 0%
3 | 1.2.7 | DELIVERABLE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0% | B. Gunn
4 | 1.2.7.1 | MILESTONE: Syndicate Governance and Oversight Framework document with key stakeholders across SHUSA, the legal entities and the Corporation, incorporate refinements and finalize | 2015-11-01 | 2015-11-30 | 22d | 0%
5 | 1.2.7.1.1 | Syndicate with subsidiaries, and refine framework document | 2015-11-01 | 2015-11-22 | 17d | 0%
5 | 1.2.7.1.2 | Get approvals from SHUSA and subsidiary Boards | 2015-11-22 | 2015-11-29 | 7d | 0%
5 | 1.2.7.1.3 | Syndicate Governance and Oversight Framework document Complete | 2015-11-29 | 2015-11-29 | 0d | 0%
2 | 1.3 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | 45d | 0% | B. Gunn
3 | 1.3.1 | DELIVERABLE: Conduct gap analysis against the target state governance and committee structure, organization and roles, decision rights, delegation of responsibilities, policy framework and reporting | 2015-12-01 | 2016-01-26 | 41d | 0%
4 | 1.3.1.1 | Conduct gap assessment for SHUSA and subsidiaries against Framework Document | 2015-12-01 | 2016-01-12 | 31d | 0%
4 | 1.3.1.2 | Synthesize key gaps and syndicate with stakeholders | 2016-01-12 | 2016-01-26 | 11d | 0%
4 | 1.3.1.3 | Conduct gap analysis Complete | 2016-01-26 | 2016-01-26 | 0d | 0%
3 | 1.3.2 | Establish comprehensive implementation plans to address these gaps over a multi-year period | 2016-01-04 | 2016-01-31 | 21d | 0%
2 | 1.4 | Execute against multi-year plan for Risk Transformation | 2016-02-01 |  |  | 0%
2 | 1.5 | Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-13 | 2015-07-31 | 15d | 50%
3 | 1.5.1 | DELIVERABLE: Establish review meeting cadence, attendees and agenda | 2015-07-13 | 2015-07-24 | 10d | 83% | B. Gunn
4 | 1.5.1.1 | MILESTONE: Review meeting cadence, attendees and agenda established | 2015-07-13 | 2015-07-24 | 10d | 83%
5 | 1.5.1.1.1 | Identify review meeting attendees | 2015-07-13 | 2015-07-24 | 10d | 100%
5 | 1.5.1.1.2 | Establish review meeting calendar | 2015-07-13 | 2015-07-24 | 10d | 100% |  | Collect Documentation
5 | 1.5.1.1.3 | Define review meeting agenda | 2015-07-13 | 2015-07-24 | 10d | 50% |  | Collect Documentation
3 | 1.5.2 | DELIVERABLE: Review and select existing reports for review meeting | 2015-07-20 | 2015-07-31 | 10d | 0% | B. Gunn
4 | 1.5.2.1 | MILESTONE: Existing reports reviewed and selected | 2015-07-20 | 2015-07-31 | 10d | 0%
5 | 1.5.2.1.1 | Review existing risk reports | 2015-07-20 | 2015-07-31 | 10d | 0%
5 | 1.5.2.1.2 | Selecty existing reports | 2015-07-20 | 2015-07-31 | 10d | 0%
5 | 1.5.2.1.3 | Implement Routine Risk-Business reviews with standardized materials and reports | 2015-07-31 | 2015-07-31 | 0d | 0%
2 | 1.6 | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2015-07-13 | 2016-01-08 | 130d | 0% |  | Need further discussion to finalize
2 | 1.7 | Assessment and Enhancement to Existing Risk Management Performance Scorecards | 2015-06-15 | 2015-12-18 | 135d | 0% | B. Gunn/C. Briongos | Separated from "Strengthen Board and Management Committee Oversight"
3 | 1.7.1 | DELIVERABLE: Assessment and quick win enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-08-03 | 35d | 0% | B. Gunn/C. Briongos | included from legacy CEP plan; need to justify / coordinate with the (round 2) enhancements below
4 | 1.7.1.1 | MILESTONE: Quick Win Enhancements to existing Risk Management Performance Scorecards | 2015-06-15 | 2015-08-03 | 35d | 0%
5 | 1.7.1.1.1 | Submit 1st Submission of Year to Date Figures from Data Feed Owners | 2015-06-15 | 2015-07-09 | 19d | 0%
5 | 1.7.1.1.2 | Create Mid Year RMPS to Share with Managers | 2015-07-10 | 2015-07-31 | 16d | 0% |  | Collect Documentation
5 | 1.7.1.1.3 | Quick Win Enhancements to existing Risk Management Performance Scorecards Complete | 2015-08-03 | 2015-08-03 | 0d | 0%
3 | 1.7.2 | DELIVERABLE: Assessment of "Round 2" Enhancements to existing Risk Management Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0% | B. Gunn/C. Briongos | need to justify / coordinate with the quick win enhancements above
4 | 1.7.2.1 | MILESTONE: Enhance Performance Scorecards | 2015-11-02 | 2015-11-27 | 20d | 0%
5 | 1.7.2.1.1 | Perform high level assessment and remediation of performance scorecards | 2015-11-02 | 2015-11-27 | 20d | 0%
5 | 1.7.2.1.2 | Assessment and Remediation of Performance Scorecards Complete | 2015-11-27 | 2015-11-27 | 0d | 0%
2 | 1.8 | Identify and implement near term changes to the risk organization and reporting lines across SHUSA | 2015-08-03 | 2015-10-02 | 45d | 0% | B. Gunn
3 | 1.8.1 | DELIVERABLE: CRO-approved Risk organizational structure charts and subsidiary reporting schemes | 2015-08-03 | 2015-10-02 | 45d | 0% | B. Gunn | Chg verb to noun; deleted "submitted to CRO for approval", chg to "CRO-approved Risk org charts…"
4 | 1.8.1.1 | MILESTONE: Risk organizational structure charts and subsidiary reporting schemes submitted to and approved by CRO (SHUSA) | 2015-08-03 | 2015-10-02 | 45d | 0% |  | Ops Risk
5 | 1.8.1.1.1 | Formalize subsidiary CRO reporting lines, socialize and refine solution (SHUSA) | 2015-08-03 | 2015-08-14 | 10d | 0%
5 | 1.8.1.1.2 | Define implications of reporting lines (for Performance assessment and hiring/firing authority) (SHUSA) | 2015-08-10 | 2015-08-21 | 10d | 0%
5 | 1.8.1.1.3 | Design 1st LoD Risk organization leadership structure including the role of RCO (SHUSA) | 2015-08-03 | 2015-09-04 | 25d | 0%
5 | 1.8.1.1.4 | Risk organizational structure charts and subsidiary reporting schemes submitted to CRO for approval (SHUSA) | 2015-10-02 | 2015-10-02 | 0d | 0%
2 | 1.9 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | 487d | 1% | B. Gunn | Ops Risk
3 | 1.9.1 | DELIVERABLE: Determine the prioritization of operating model design and rollout by risk type / function | 2015-08-03 | 2015-10-02 | 45d | 0% | B. Gunn | Should this take 1 month? | N/A
4 | 1.9.1.1 | Confirm Risk type / function A & B | 2015-08-03 | 2015-08-03 | 1d | 0% |  |  | N/A
4 | 1.9.1.2 | Confirm Risk type / function C, D, E, & F | 2015-09-25 | 2015-09-25 | 1d | 0% |  |  | N/A
4 | 1.9.1.3 | TOM Design Determined by risk type/function | 2015-09-25 | 2015-09-25 | 0d | 0% |  |  | N/A
3 | 1.9.2 | DELIVERABLE: Review of existing 1st LoD structure and capabilities | 2015-06-22 | 2015-07-17 | 20d | 75%
3 | 1.9.3 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function A (All risk types ex. Op risk) | 2015-07-13 | 2016-11-09 | 347d | 0% | B. Gunn
4 | 1.9.3.1 | MILESTONE: Design detailed operating model and implementation plans for Risk type / function A (All risk types ex. Op risk) | 2015-07-13 | 2016-11-09 | 347d | 0%
5 | 1.9.3.1.1 | Strengthening Second LOD reporting: Determine high level subsidiary CRO reporting lines | 2015-07-13 | 2015-07-27 | 11d | 0% |  |  | Brian has taken over
5 | 1.9.3.1.2 | Strengthening Second LOD reporting: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 0% |  |  | Brian has taken over
5 | 1.9.3.1.3 | Designing the Business Control Officers: Initial high level design | 2015-07-13 | 2015-07-27 | 11d | 100%
5 | 1.9.3.1.4 | Designing the Business Control Officers: Detailed roles and responsibilities design | 2015-07-20 | 2015-08-03 | 11d | 100%
5 | 1.9.3.1.5 | Designing the Business Control Officers: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 75%
5 | 1.9.3.1.6 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100%
5 | 1.9.3.1.7 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100%
5 | 1.9.3.1.8 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 16d | 75%
5 | 1.9.3.1.9 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 25%
5 | 1.9.3.1.10 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 25%
5 | 1.9.3.1.11 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 0%
5 | 1.9.3.1.12 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-08-31 | 16d | 0%
5 | 1.9.3.1.13 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-08-31 | 11d | 0%
5 | 1.9.3.1.14 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-07-27 | 2015-08-17 | 16d | 0%
5 | 1.9.3.1.15 | Identify resource requirements and gap assessment: Obtain industry benchmarks | 2015-08-10 | 2015-08-31 | 16d | 0%
5 | 1.9.3.1.16 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-10 | 2015-09-07 | 21d | 0%
5 | 1.9.3.1.17 | Identify resource requirements and gap assessment: Conduct FTE analysis | 2015-08-31 | 2015-09-21 | 16d | 0%
5 | 1.9.3.1.18 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-08-31 | 2015-09-21 | 16d | 0%
5 | 1.9.3.1.19 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-08-24 | 2015-09-21 | 21d | 0%
5 | 1.9.3.1.20 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-09-07 | 2015-09-28 | 16d | 0%
5 | 1.9.3.1.21 | Identify resource requirements and gap assessment: Review budget and obtain approval | 2015-09-14 | 2015-10-05 | 16d | 0%
5 | 1.9.3.1.22 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-09-14 | 2015-10-05 | 16d | 0%
5 | 1.9.3.1.23 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-05 | 2015-11-02 | 21d | 0%
5 | 1.9.3.1.24 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-10-19 | 2015-11-09 | 16d | 0%
5 | 1.9.3.1.25 | Implementation planning: Draft roadmap for implementation | 2015-10-19 | 2015-11-09 | 16d | 0%
5 | 1.9.3.1.26 | Implementation planning: Review roadmap with key stakeholders | 2015-10-19 | 2015-11-09 | 16d | 0%
5 | 1.9.3.1.27 | Implementation planning: Obtain approval for implementation roadmap | 2015-10-26 | 2015-11-09 | 11d | 0%
5 | 1.9.3.1.28 | Operating model and implementation plans for all risk types/function ex. Op Risk complete | 2016-11-09 | 2016-11-09 | 0d | 0% |  | Estimate timeline is 3 months subject to change based on final plan
3 | 1.9.4 | DELIVERABLE: Design detailed operating model and implementation plans for Risk type / function B (Op Risk) | 2015-07-13 | 2015-11-30 | 101d | 0% | B. Gunn
4 | 1.9.4.1 | MILESTONE: Risk type / function B (Op Risk) | 2015-07-13 | 2015-11-30 | 101d | 0%
5 | 1.9.4.1.1 | Strengthening Second LOD reporting: Determine high level subsidiary CRO reporting lines | 2015-07-13 | 2015-07-27 | 11d | 0% |  |  | Delete, N/A
5 | 1.9.4.1.2 | Strengthening Second LOD reporting: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 0% |  |  | Delete, N/A
5 | 1.9.4.1.3 | Designing the Business Control Officers: Initial high level design | 2015-07-13 | 2015-07-27 | 11d | 0% |  |  | Delete, N/A
5 | 1.9.4.1.4 | Designing the Business Control Officers: Detailed roles and responsibilities design | 2015-07-20 | 2015-08-03 | 11d | 0% |  |  | Delete, N/A
5 | 1.9.4.1.5 | Designing the Business Control Officers: Review and approval | 2015-07-27 | 2015-08-03 | 6d | 0% |  |  | Delete, N/A
5 | 1.9.4.1.6 | Roles and responsibilities drafting: High-level division of tasks between SHUSA vs. Subs and 1st LOD vs. 2nd LOD | 2015-07-13 | 2015-07-27 | 11d | 100%
5 | 1.9.4.1.7 | Roles and responsibilities drafting: Detailed drafts of roles and responsiblities for all risk types | 2015-07-13 | 2015-08-03 | 16d | 100%
5 | 1.9.4.1.8 | Roles and responsibilities drafting: Review drafts with key stakeholders in each risk type | 2015-07-20 | 2015-08-10 | 16d | 25%
5 | 1.9.4.1.9 | Roles and responsibilities drafting: Finalize and compile roles and responsibilities, and obtain approval | 2015-08-03 | 2015-08-10 | 6d | 0%
5 | 1.9.4.1.10 | Functional organizational chart building: Incorporation of reporting line decisions into org chart principles | 2015-07-27 | 2015-08-10 | 11d | 25%
5 | 1.9.4.1.11 | Functional organizational chart building: Drafts of functional org chart for all risk types | 2015-08-03 | 2015-08-24 | 16d | 0%
5 | 1.9.4.1.12 | Functional organizational chart building: Review drafts with key stakeholders in each risk type | 2015-08-10 | 2015-08-31 | 16d | 0%
5 | 1.9.4.1.13 | Functional organizational chart building: Finalize and compile functional org charts, and obtain approval | 2015-08-17 | 2015-08-31 | 11d | 0%
5 | 1.9.4.1.14 | Identify resource requirements and gap assessment: Map current state resources in the organization | 2015-07-27 | 2015-08-24 | 21d | 0%
5 | 1.9.4.1.15 | Identify resource requirements and gap assessment: Obtain industry benchmarks | 2015-08-10 | 2015-08-31 | 16d | 0%
5 | 1.9.4.1.16 | Identify resource requirements and gap assessment: Determine required skills and headcount using the functional org charts | 2015-08-17 | 2015-09-28 | 31d | 0%
5 | 1.9.4.1.17 | Identify resource requirements and gap assessment: Conduct FTE analysis | 2015-09-07 | 2015-10-05 | 21d | 0%
5 | 1.9.4.1.18 | Identify resource requirements and gap assessment: Review skill and headcount requirments with stakeholders in each risk type | 2015-09-14 | 2015-10-12 | 21d | 0%
5 | 1.9.4.1.19 | Identify resource requirements and gap assessment: Determine gap between availability and requirement | 2015-09-07 | 2015-10-19 | 31d | 0%
5 | 1.9.4.1.20 | Identify resource requirements and gap assessment: Review gap assessment with stakeholders in each risk type | 2015-10-05 | 2015-11-02 | 21d | 0%
5 | 1.9.4.1.21 | Identify resource requirements and gap assessment: Review budget and obtain approval | 2015-09-28 | 2015-10-19 | 16d | 0%
5 | 1.9.4.1.22 | Identify resource requirements and gap assessment: Finalized and compile resource requirements and gap assessment | 2015-10-12 | 2015-10-26 | 11d | 0%
5 | 1.9.4.1.23 | Implementation planning: Design stepwise implementation from present state to target state, with interim states | 2015-10-12 | 2015-11-02 | 16d | 0%
5 | 1.9.4.1.24 | Implementation planning: Socialize interim states with key stakeholders to assess appropriateness and feasibility | 2015-11-09 | 2015-11-30 | 16d | 0%
5 | 1.9.4.1.25 | Implementation planning: Draft roadmap for implementation | 2015-10-26 | 2015-11-23 | 21d | 0%
5 | 1.9.4.1.26 | Implementation planning: Review roadmap with key stakeholders | 2015-11-09 | 2015-11-30 | 16d | 0%
5 | 1.9.4.1.27 | Implementation planning: Obtain approval for implementation roadmap | 2015-11-01 | 2015-11-09 | 7d | 0%
5 | 1.9.4.1.28 | Operating model and implementation plans for Op Risk complete | 2015-11-09 | 2015-11-09 | 0d | 0%
3 | 1.9.5 | Implement the redesigned Operating Model for each Risk Type/Function | 2015-11-09 | 2017-04-04 | 367d | 0% | B. Gunn
3 | 1.9.6 | DELIVERABLE: 1st Round Post Implementation Review | 2016-11-10 | 2016-12-07 | 20d | 0% | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.6.1 | MILESTONE: 1st Round Post Implementation Review Conducted | 2016-11-10 | 2016-12-07 | 20d | 0%
5 | 1.9.6.1.1 | Post Implementation Review (First Round) | 2016-11-10 | 2016-12-07 | 20d | 0%
5 | 1.9.6.1.2 | MILESTONE: 1st Round Post Implementation Review Conducted | 2016-12-07 | 2016-12-07 | 0d | 0%
3 | 1.9.7 | DELIVERABLE: 2nd Round Post Implementation Review | 2017-01-26 | 2017-02-22 | 20d | 0% | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.7.1 | MILESTONE: 2nd Round Post Implementation Review Conducted | 2017-01-26 | 2017-02-22 | 20d | 0%
5 | 1.9.7.1.1 | Post Implementation Review (Second Round) | 2017-01-26 | 2017-02-22 | 20d | 0%
5 | 1.9.7.1.2 | MILESTONE: 2nd Round Post Implementation Review Conducted | 2017-02-22 | 2017-02-22 | 0d | 0% |  | Corrected dates
3 | 1.9.8 | DELIVERABLE: 3rd Round Post Implementation Review | 2017-04-05 | 2017-05-02 | 20d | 0% | B. Gunn | Chg verb to noun; omitted "conducted"
4 | 1.9.8.1 | MILESTONE: 3rd Round Post Implementation Review Conducted | 2017-04-05 | 2017-05-02 | 20d | 0%
5 | 1.9.8.1.1 | Post Implementation Review (Third Round) | 2017-04-05 | 2017-05-02 | 20d | 0%
5 | 1.9.8.1.2 | MILESTONE: 3rd Round Post Implementation Review Conducted | 2017-05-02 | 2017-05-02 | 0d | 0%
3 | 1.9.9 | DELIVERABLE: Articulate desired risk culture by setting the “Tone from the Top” and conducting a risk culture assessment | 2015-08-03 | 2015-10-02 | 45d | 0% | B. Gunn | Chg verb to noun
4 | 1.9.9.1 | MILESTONE: Strong and Desired Risk Culture Defined | 2015-08-03 | 2015-10-02 | 45d | 0%
5 | 1.9.9.1.1 | Determine the survey population and tailor survey as needed (1 week) | 2015-08-03 | 2015-08-07 | 5d | 0%
5 | 1.9.9.1.2 | Deploy culture survey and collect responses (2-3 week) | 2015-08-03 | 2015-08-21 | 15d | 0%
5 | 1.9.9.1.3 | Aggregate and analyze survey results (2-3 weeks) | 2015-08-24 | 2015-09-11 | 15d | 0%
5 | 1.9.9.1.4 | Conduct 3-4 targeted focus groups or workshops to refine and validate the insights (1-2 weeks) - goes in parallel with 3. | 2015-08-31 | 2015-09-18 | 15d | 0%
5 | 1.9.9.1.5 | Review findings, document current state risk culture and priritize focus areas (1 week) | 2015-09-21 | 2015-10-02 | 10d | 0%
5 | 1.9.9.1.6 | MILESTONE: Strong and Desired Risk Culture Defined | 2016-10-02 | 2016-10-02 | 0d | 0% |  | Chg "Instilled" to "Defined"
2 | 1.1 | Long Term Planning Package | 2016-01-25 | 2017-04-04 | 312d? | 0%
3 | 1.10.1 | DELIVERABLE: Rollout systematic performance assessments and compensation structures | 2016-04-01 | 2017-01-02 | 197d? | 0% | B. Gunn/C. Briongos | Chg verb to noun; Chg "rollout…" to "Introduction of…"
4 | 1.10.1.1 | MILESTONE: Design risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.1.1.1 | Benchmark of risk-based compensation practices in the industry | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.1.1.2 | Risk-based compensation proposals and refinement with stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.1.1.3 | Impact analysis of new frameworks on compensation levels | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.1.1.4 | Formalization of new risk-based compensation framework | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.1.1.5 | Risk-based compensation structure formalized | 2016-06-30 | 2016-06-30 | 0d | 0% |  | Chg "complete" to "formalized"; do not want to reflect that structure is complete
4 | 1.10.1.2 | MILESTONE: Communication and stakeholder engagement | 2016-04-01 | 2016-09-30 | 131d? | 0%
5 | 1.10.1.2.1 | Design of communication plan | 2016-04-01 | 2016-06-30 | 65d? | 0%
5 | 1.10.1.2.2 | Development of communication materials | 2016-04-01 | 2016-06-30 | 65d? | 0% |  | Chg "writing" to "development"
5 | 1.10.1.2.3 | Execution of communication plan | 2016-06-30 | 2016-09-30 | 67d? | 0%
5 | 1.10.1.2.4 | Stakeholder communication complete | 2016-09-30 | 2016-09-30 | 0d | 0%
4 | 1.10.1.3 | MILESTONE: Updates to performance assessment templates | 2016-07-01 | 2017-01-02 | 132d? | 0%
5 | 1.10.1.3.1 | Inventory of performance assessment templates at SHUSA, SBNA and SCUSA | 2016-07-01 | 2016-09-30 | 66d? | 0%
5 | 1.10.1.3.2 | Update of template in accordance with risk-based compensation framework | 2016-07-01 | 2016-09-30 | 66d? | 0%
5 | 1.10.1.3.3 | Socialization, training of stakeholders and roll-out of new templates | 2016-09-30 | 2017-01-02 | 67d? | 0% |  | Chg "training to" to "training of"
5 | 1.10.1.3.4 | Performance assessment templates updated | 2016-12-31 | 2016-12-31 | 0d | 0%
3 | 1.10.2 | DELIVERABLE: Rollout communication and training for organizational changes related to 3 LOD | 2016-01-25 |  |  | 0% | B. Gunn
4 | 1.10.2.1 | MILESTONE: Communications to emphasize progress being made / share best practices | 2016-01-25 | 2016-04-22 | 65d | 0%
5 | 1.10.2.1.1 | Assessment of progress being made & best practices | 2016-01-25 | 2016-04-22 | 65d | 0%
5 | 1.10.2.1.2 | Design of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0%
5 | 1.10.2.1.3 | Development of communications materials | 2016-01-25 | 2016-04-22 | 65d | 0%
5 | 1.10.2.1.4 | Delivery of communication plan | 2016-01-25 | 2016-04-22 | 65d | 0%
5 | 1.10.2.1.5 | Progress communications delivered | 2016-03-31 | 2016-03-31 | 0d | 0%
4 | 1.10.2.2 | MILESTONE: Convey organizational changes to the enterprise | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.2.2.1 | Development of materials | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.2.2.2 | Delivery of communication to stakeholders | 2016-04-01 | 2016-06-30 | 65d | 0%
5 | 1.10.2.2.3 | Organizational changes communicated to enterprise | 2016-06-30 | 2016-06-30 | 0d | 0%
4 | 1.10.2.3 | MILESTONE: Enterprise-wide training and development of job descriptions with explicit focus on three lines of defense | 2016-07-01 | 2017-01-02 | 132d? | 0%
5 | 1.10.2.3.1 | Design of training curriculum & idenfification of key recepients as a result of post-implementation reviews | 2016-07-01 | 2016-09-30 | 66d? | 0%
5 | 1.10.2.3.2 | Development of training materials | 2016-07-01 | 2016-09-30 | 66d? | 0%
5 | 1.10.2.3.3 | Delivery of training to priority recipients | 2016-09-30 | 2017-01-02 | 67d? | 0%
5 | 1.10.2.3.4 | Identification of key functions requiring job description updates | 2016-07-01 | 2016-09-30 | 66d? | 0%
5 | 1.10.2.3.5 | Development of job descriptions with explicit focus on three lines of defense | 2016-09-30 | 2017-01-02 | 67d? | 0%
5 | 1.10.2.3.6 | Job descriptions complete and enterprise-wide training delivered | 2016-12-31 | 2016-12-31 | 0d | 0%
3 | 1.10.3 | DELIVERABLE: Diagnose retention challenge and design recruitment and retention mechanisms | 2016-07-01 | 2017-04-04 | 198d? | 0% | B. Gunn/C. Briongos | Chg verb to noun
4 | 1.10.3.1 | MILESTONE: Design recruitment and retention mechanisms (e.g. Professional development and job rotation programs, job satisfaction assessments, and compensation structure) | 2016-07-01 | 2016-09-30 | 66d | 0% |  | Chg noun to verb
5 | 1.10.3.1.1 | Diagnostic of retention challenges | 2016-07-01 | 2016-09-30 | 66d | 0%
5 | 1.10.3.1.2 | Design of new possible retention mechanisms | 2016-07-01 | 2016-09-30 | 66d | 0%
5 | 1.10.3.1.3 | Milestone: Design of new possible retention mechanisms complete | 2016-09-30 | 2016-09-30 | 0d | 0% |  | Added "possible"
4 | 1.10.3.2 | MILESTONE: Action plans for necessary remediation efforts | 2016-10-03 | 2017-04-04 | 132d? | 0%
5 | 1.10.3.2.1 | Selection of key remediation initiatives with key stakeholders | 2016-10-03 | 2017-01-04 | 68d? | 0%
5 | 1.10.3.2.2 | Planning of initiatives between SHUSA and its subsidiaries | 2016-10-03 | 2017-01-04 | 68d? | 0%
5 | 1.10.3.2.3 | Rollout of initiatives at SHUSA | 2016-10-03 | 2017-01-04 | 68d? | 0%
5 | 1.10.3.2.4 | Rollout of initiatives at other subsidiaries | 2017-01-02 | 2017-04-04 | 67d | 0%
5 | 1.10.3.2.5 | Recruitment and retention intiatives introduced throughout enterprise | 2017-03-31 | 2017-03-31 | 0d | 0%
3 | 1.10.4 | DELIVERABLE: Define multiyear plan to achieve a sound target state risk culture | 2016-07-01 | 2016-09-30 | 66d | 0% | B. Gunn | Chg verb to noun
4 | 1.10.4.1 | MILESTONE: Create multi-year plan that describes interventions | 2016-07-01 | 2016-09-30 | 66d | 0%
4 | 1.10.4.2 | MILESTONE: Syndicate plan with key stakeholders and get approvals | 2016-07-01 | 2016-09-30 | 66d | 0%
4 | 1.10.4.3 | MILESTONE: Diagnostics of risk culture; multi-year plan to achieve premier risk culture in place | 2016-09-30 | 2016-09-30 | 0d | 0% |  | Chg "Ongoing diagnostics" to "Diagnostics"; "development of multi-year plan" to "multi-year plan"; intent was to remove indefinite terminology from a milestone