## Traceability matrix
Status of remediation of deliverable by …
Row # | Deficiency ID | MRA / MRIA | Deficiency title | Deficiency Citation: Corrective Action | CCAR 2016 (0 = not started, 4 completed) | CCAR 2017 (0 = not started, 4 completed) | Comments | Mapping ID | Deliverable name | Deliverable start date | Deliverable finish date | Workstreaw owning deliverable | Sub-workstream owning deliverable | Review approval from workstream (Yes/No)
1 | SANUS.FED.2011.07.19.MRA.01 | SAN-US Liquidity Risk Management Examination MRA 1 | Formalization of the Liquidity Stress Test Assumption Review Process | Within 60 days management should develop and implement procedures for ensuring that the rationale of all major assumptions, within the liquidity risk stress tests, be supported by well documented and robust documentation. |  |  |  | d20263 | Documentation standards and templates for each category to ensure consistent inclusion of relevant information defined | 2015-09-15 | 2015-09-15 | CCAR
1 | SANUS.FED.2011.07.19.MRA.01 | [6 empty] | d886 | Independent Review of LRM adequacy and effectiveness completed | 2015-09-25 | 2016-05-27 | ELS
1 | SANUS.FED.2011.07.19.MRA.01 | [6 empty] | D10994 | Design Liquidity Stress Test Challenge Process Framework and get approvals | 2015-06-01 | 2015-12-31 | Risk Transformation | Risk Management
1 | SANUS.FED.2011.07.19.MRA.01 | [6 empty] | d10995 | Liquidity Stress Test Challenge Process Framework | 2015-06-01 | 2015-12-31 | Risk Transformation
2 | SANUS.FED.2012.10.11.MRIA.01 | SAN-US Liquidity Risk Management Examination MRIA 1 | Liquidity Risk Management Practices | Senior management must improve liquidity risk management practices related to liquidity stress testing, management of the liquidity buffer, and the liquidity limit management processes. More specifically, senior management must: • Ensure that the reporting to senior management on liquidity stress test results includes more detailed information on the impact of stress on the firm's liquidity position; • Ensure the reporting on the liquidity buffer includes the composition of the buffer and whether an excess or deficiency exists; • Use liquidity limits as a proactive risk management tool. Where appropriate, senior management must recalibrate operating limits to fit within their risk appetite. In addition, senior management must ensure that early warning indicators are applied to operating limits. Lastly, senior management must review key liquidity metrics at the US ALCO as required by internal policy; and • Clarify reporting of limits in ALCO that use both percentage and absolute dollar measurements. |  |  |  | D999 | Policies Review | 2015-03-31 | 2015-12-31 | ELS
2 | SANUS.FED.2012.10.11.MRIA.01 | [6 empty] | D1011 | Liquidity Risk Management Control reporting framework Program | 2015-06-30 | 2015-12-31 | ELS
2 | SANUS.FED.2012.10.11.MRIA.01 | [6 empty] | D10826 | Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | 2014-11-03 | 2015-11-30 | Risk Transformation
2 | SANUS.FED.2012.10.11.MRIA.01 | [6 empty] | D10995 | Liquidity Stress Test Challenge Process Framework | 2015-06-01 | 2015-12-31 | Risk Transformation
5 | SANUS.FED.2013.01.30.MRA.01 | Enterprise-wide Risk Management Review MRA 1 | Risk Tolerance Statement Metric Selection | Management should develop and document a standardized methodology for Risk Tolerance Statement metric selection and tolerance level and limit setting that ensures that metrics and limits are appropriate in relation to established risk appetites, and are based on risk assessments, current business activities, and business development and operations strategies. |  |  |  | D11952 | Implement prioritized set of operational risk metrics for Risk Appetite (SHUSA / SBNA / SCUSA) | 2015-06-15 | 2016-12-31 | Operational Risk | Risk Appetite
5 | SANUS.FED.2013.01.30.MRA.01 | [6 empty] | D11498 | Design SHUSA (top-level), SBNA, and SCUSA RAS | 2015-06-08 | 2015-09-11 | Risk Transformation | Risk Appetite
5 | SANUS.FED.2013.01.30.MRA.01 | [6 empty] | D11557 | Establish related processes and documentation for ongoing management of RAS (e.g. breach escalation and remediation process – including consequences) | 2015-07-06 | 2015-09-15 | Risk Transformation | Risk Appetite
5 | SANUS.FED.2013.01.30.MRA.01 | [6 empty] | D11565 | Articulate SHUSA (top-level), SBNA, and SCUSA RAS approval process, and train the Board on the approach and their role | 2015-08-31 | 2015-11-30 | Risk Transformation | Risk Appetite
5 | SANUS.FED.2013.01.30.MRA.01 | [6 empty] | D11605 | RAS for remainder of subsidiaries and select Bus (SIS NY, Puerto Rico, Miami) | 2016-02-01 | 2016-06-30 | Risk Transformation | Risk Appetite
4 | SANUS.FED.2013.01.30.MRA.02 | Enterprise-wide Risk Management Review MRA 2 | EWRMG Issue Discovery and Resolution | Management should develop a formal process for EWRMG management and staff to document and track issues raised and management's timely resolution of those issues. |  |  |  | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
4 | SANUS.FED.2013.01.30.MRA.02 | [6 empty] | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
3 | SANUS.FED.2013.01.30.MRA.03 | Enterprise-wide Risk Management Review MRA 3 | EWRMG Access to Data and Systems | As part of the SHUSA and SAN-US EWRM program development plan, management should assess requirements for EWRMG unit access to risk and accounting data systems, and initiate IT development projects to select, build, or leverage existing data analysis tools to support EWRMG's independent and cross-entity risk monitoring and aggregation needs. |  |  |  | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Management
7 | SANUS.FED.2013.12.24.MRA.01 | SAN-US Compliance Risk Management Examination MRA 1 | Compliance Risk Management Framework | Within 60 days of this report, the SAN-US Executive Management Committee must establish a detailed action plan to develop a SAN-US compliance risk management framework which clearly defines the scope and coverage of compliance oversight at the SAN-US level and articulates expectations for compliance risk management at the US legal entities. The framework should clearly articulate the roles and responsibilities of various committees, functions, and staff and the standards and processes to be followed in order to ensure effective compliance risk management across the US operations. |  |  |  | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
7 | SANUS.FED.2013.12.24.MRA.01 | [6 empty] | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
24 | SANUS.FED.2015.01.23.MRIA.01 | SAN-US Model Risk Management Exam MRIA 1 | SAN-US MRM Governance and Oversight | The boards of directors are required to immediately develop a formal SAN-US model risk management governance and oversight structure that includes committee, managerial, and policy structures that are aligned between SAN-US and the business units. Accountability for model risk management program oversight and management should be clearly and consistently communicated through committee charters, managerial reporting lines, and individual job descriptions that include roles and responsibilities. |  |  |  | D13153 | Enhance MRM Framework, Policy / Procedures / Standards / Templates | 2017-03-31 | 2017-03-31 | Model Risk Management | MRM Framework
24 | SANUS.FED.2015.01.23.MRIA.01 | [6 empty] | D12615 | Strengthen oversight of the MRM framework by the Board and senior management | 2015-07-13 | 2017-05-08 | Model Risk Management | Governance and Reporting
25 | SANUS.FED.2015.01.23.MRIA.02 | SAN-US Model Risk Management Exam MRIA 2 | SAN-US MRM Framework Plan | The boards of directors are required to immediately develop a comprehensive plan to implement an effective model risk management framework. This plan must contain a thorough gap analysis against SR 11 -7 and action steps to remediate identified gaps and deficiencies, including those contained in this report. The project plan must be administered by experienced project managers who can oversee project plan milestones and granular tasks as well as interim completion dates. |  |  |  | D12968 | Address Legacy Model Validation Backlog | 2015-06-19 | 2016-07-15 | Model Risk Management
25 | SANUS.FED.2015.01.23.MRIA.02 | [6 empty] | D12613 | Program Management practice | 2017-03-24 | 2017-03-24 | Model Risk Management | MRM Framework
25 | SANUS.FED.2015.01.23.MRIA.02 | [6 empty] | D13153 | Enhance MRM Framework, Policy / Procedures / Standards / Templates | 2017-03-31 | 2017-03-31 | Model Risk Management | MRM Framework
25 | SANUS.FED.2015.01.23.MRIA.02 | [6 empty] | D12611 | Strengthen oversight of the MRM framework by the Board and senior management | 2017-05-08 | 2017-05-08 | Model Risk Management | Governance and Reporting
26 | SANUS.FED.2015.01.23.MRIA.03 | SAN-US Model Risk Management Exam MRIA 3 | SAN-US MRM Leadership Strengthening | The boards of directors are required to immediately strengthen model risk management leadership as well as the quantity and quality of staff. A comprehensive skills and staffing assessment and hiring strategy must be developed for implementation of an effective model risk management framework. The assessment and strategy should address resource needs for model risk management oversight, model development, and the model validation functions taking into account current backlogs and excessive workloads as well as the required project plan. |  |  |  | D13493 | 90% of the hiring plan complete | 2014-09-19 | 2014-09-19 | Model Development
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13489 | Engage external recruiting resources (if needed) | 2014-09-19 | 2014-09-19 | Model Development
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13459 | Develop and Approve Organizational chart | 2015-07-31 | 2015-07-31 | Model Development
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13486 | Identify hiring plan gaps and establish hiring standards | 2015-08-17 | 2015-08-17 | Model Development
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13488 | Transition existing staff to new organizational structure | 2015-09-28 | 2015-09-28 | Model Development
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13378 | Hire immediate-term for known staffing requirements based on volume of validation required | 2015-05-15 | 2015-12-31 | Model Risk Management | MRM Leadership and Staffing
26 | SANUS.FED.2015.01.23.MRIA.03 | [6 empty] | D13397 | Long term staffing solution | 2015-08-31 | 2017-01-19 | Model Risk Management
10 | SCUSA.FED.2011.07.19.MRA.09 | SCUSA Target MRA 9 | SCUSA Liquidity Limits | It is expected that management will formalize the Self-Funding Ratio guideline into a liquidity risk limit. It was further conveyed to management that one risk limit and one risk guideline is not sufficient to properly identify, measure, monitor, and control liquidity risk of a entity the size and magnitude of SCUSA. It is expected that management will formulate additional liquidity risk metrics, which will subsequently be approved by the ALCO and the board of directors. This action would enhance the overall quality of liquidity risk management. In addition, it is expected that management will formulate a liquidity dashboard that includes additional risk metrics and early warning triggers that would give management ample time and opportunity to revise balance sheet strategies and growth rates to prevent possible liquidity events. It is further expected that such a liquidity dashboard will be updated no less than quarterly and in many cases; some components of the liquidity dashboard will be updated and reported to the ALCO and Board of Directors monthly. |  |  |  | d1274 | Update & Implement Liquidity Funding Plan (LFP) | 2014-11-03 | 2014-12-12 | ELS | Risk Monitoring / Reporting
9 | SCUSA.FED.2011.07.19.MRA.09 | [6 empty] | D10826 | Analyze and remediate gaps in liquidity risk management (“LRM”) against IHC requirements | 2014-11-03 | 2015-11-30 | Risk Transformation
8 | SCUSA.FED.2011.07.19.MRA.11 | SCUSA Target MRA 11 | SCUSA Funding Policy | SCUSA does not have any deposits and is very dependent upon internal lines of credit from the parent company and related entities, and third party lines of credit arranged by management for funding purposes. Management's efforts to increase funding sources are noted. However, management indicated that SCUSA does not have a diversified funding policy. It is expected that management will formulate a diversified funding policy and will continue to strive to further increase funding sources. In addition, it is expected that management will develop an inter-bank funding policy that enact limits and guidance to parent company and related entities funding especially if there is potential SOSA rating downgrade that would enact limitations on parent company inter-bank funding. The Treasury Department and Senior Financial Management should formulate a diversified funding policy and an inter-bank funding policy within 90 days of the date of this letter. |  |  |  | Gap | Gap (Possibly out of scope) | #N/A | #N/A | ELS
10 | SCUSA.FED.2013.12.09.MRA.01 | Credit Risk Management Target MRA 1 | Expansion of the Credit Risk Reporting Packages | Within 120 days, SCUSA's board of directors is required to expand the credit risk reporting packages provided to senior management, the board of directors, and committees thereof. At a minimum, reporting should include analyses of the level and trend of portfolio asset quality and aggregate risks, performance against an expanded set of meaningful limits, as well as assessments of loss mitigation efforts by product type. |  |  |  | d10731 | Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols | 2015-06-15 | 2015-08-17 | Risk Transformation | Risk Monitoring / Reporting
10 | SCUSA.FED.2013.12.09.MRA.01 | [6 empty] | d10748 | Define target exec. Mgmt risk reporting landscape and scope of remediation (link to committee structure) | 2015-07-27 | 2015-09-07 | Risk Transformation | Risk Monitoring / Reporting
10 | SCUSA.FED.2013.12.09.MRA.01 | [6 empty] | d10759 | Develop and implement Wave 1 of exec. Mgmt. reporting enhancements | 2015-08-31 | 2015-11-09 | Risk Transformation | Risk Monitoring / Reporting
10 | SCUSA.FED.2013.12.09.MRA.01 | [6 empty] | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
15 | SCUSA.FED.2013.12.09.MRIA.01 | Credit Risk Management Target MRIA 1 | Implementation of an Effective Credit Risk Management Framework | Within 60 days, SCUSA's board of directors is required to immediately develop a detailed plan for the implementation of an effective credit risk management framework that provides sound oversight and challenge across all of its retail and commercial lending activities. The plan must address existing gaps in the independent risk management infrastructure and define the function's mission. Risk management roles and responsibilities must be clearly defined for key individuals with sufficient authority, accountability, and independence from the business. The plan must also address skill gaps, particularly in commercial lending, to ensure there is sufficient leadership and quantity of staff with requisite skill sets to provide effective oversight and challenge. The plan should list specific action steps, deliverables, individuals responsible for action steps, and clear deadlines for completion. |  |  |  | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
15 | SCUSA.FED.2013.12.09.MRIA.01 | [6 empty] | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
20 | SCUSA.FED.2014.11.24.MRA.01 | 2014 SCUSA Retail ALLL ECM MRA 1 | ALLL Methodology | Within 120 days, SCUSA's board of directors is required to develop and implement an acceptable plan to materially strengthen the ALLL methodology and bring it in conformance with regulatory guidance. This plan must include a budget, milestones, tasks, and specific timeframes for completion. The plan must be administered by an experienced project manager to ensure appropriate monitoring and reporting of progress and escalation of issues. |  |  |  | D8765 | Develop forecasting methodologies for Balance Sheet, PPNR, Losses and ALLL (Milestone 2) | 2015-08-17 | 2015-12-31 | Finance transformation | Capital management
20 | SCUSA.FED.2014.11.24.MRA.01 | [6 empty] | POTENTIAL GAP | #N/A | #N/A | #N/A | Finance transformation
21 | SCUSA.FED.2014.11.24.MRA.02 | 2014 SCUSA Retail ALLL ECM MRA 2 | ALLL Governance Structure | Within 120 days, SCUSA's board of directors is required to develop an appropriate ALLL governance structure that clearly articulates roles and responsibility for the management and oversight of the provisioning process. |  |  |  | D11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
21 | SCUSA.FED.2014.11.24.MRA.02 | [6 empty] | D11770 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | Risk Transformation | Risk Governance & Org
21 | SCUSA.FED.2014.11.24.MRA.02 | [6 empty] | D11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
23 | SCUSA.FED.2015.01.23.MRA.01 | SAN-US Model Risk Management Exam MRA 1 | SCUSA Pricing Model Governance | SCUSA's board of directors and senior management are required to develop and implement a sound pricing governance process. This governance should include policies, procedures, and limits, and ensure that pricing changes are subject to oversight from model risk management and the appropriate management and board committees. Applicable committee charters should be updated to define authority and oversight over the pricing process. |  |  |  | D12614 | SCUSA Pricing Governance and Oversight | 2015-12-31 | 2015-12-31 | Model Risk Management | Governance and Reporting
27 | SHUSA.FED.2013.06.04.MRA.01 | Capital Planning Review MRA 1 | Identifying Capital Plan Weaknesses | Management is required to develop a systematic, comprehensive, and repeatable process to identify weaknesses and deficiencies with the capital planning process. Using a granular bottoms-up approach, the process should capture model, process, and data-level weaknesses, plus any other weaknesses. |  |  |  | D20332 | Weakness Identification Policy, Procedures & Inventory | 2015-11-30 | 2015-11-30 | CCAR | Governance
32 | SHUSA.FED.2013.06.04.MRA.02 | Capital Planning Review MRA 2 | Capital Planning Process Weaknesses | Management is required to develop a credible, transparent, and repeatable process to measure the uncertainty resulting from capital planning process weaknesses. Where possible, the quantification of uncertainty should be done at the model or process level. In instances where this is not possible, management is required to ensure that estimates of uncertainty done at a higher level or based on proxy methodologies are fully justified and supported. The methodologies used to quantify the uncertainty, including potential immateriality, should be well supported and documented and subject to independent validation. In addition, more formalized procedures, processes, and controls for management overlays and conservative adjustments should be developed. |  |  |  | D20496 | Approved procedure to measure the uncertainty from Model, Data & Process Weaknesses | 2015-09-30 | 2015-09-30 | CCAR | Capital assessment
32 | SHUSA.FED.2013.06.04.MRA.02 | [6 empty] | D20497 | Develop process to ensure appropriate analysis and documentation supporting rationale of uncertainty add-ons related to process weaknesses | 2016-06-30 | 2016-06-30 | CCAR | Capital assessment
40 | SHUSA.FED.2013.06.04.MRA.03 | Capital Planning Review MRA 3 | Uncertainty in Scenario Planning | Management is required to develop a process that formally accounts for the uncertainty in the planning horizon of each scenario either through an impact to the estimates (e.g. losses, PPNR, etc.), the stress capital targets used in the scenarios, or a combination of both, and is sensitive to the scenarios. |  |  |  | D20496 | Approved procedure to measure the uncertainty from Model, Data & Process Weaknesses | 2015-09-30 | 2015-09-30 | CCAR | Capital assessment
40 | SHUSA.FED.2013.06.04.MRA.03 | [6 empty] | D20497 | Develop process to ensure appropriate analysis and documentation supporting rationale of uncertainty add-ons related to process weaknesses | 2016-06-30 | 2016-06-30 | CCAR | Capital assessment
45 | SHUSA.FED.2013.06.04.MRA.09 | Capital Planning Review MRA 9 | Internal Operational Loss Forecasting | Management is required to evaluate the quality, quantity, and relevance of its internal operational loss data for use in forecasting operational losses. If necessary, management is required to expand the operational data used to forecast operational losses beyond just internal loss data in order to capture the full operational risk profile of the firm. |  |  |  | D12470 | Implement Operational Risk Loss Forecasting for CCAR and document | 2015-08-01 | 2016-03-31 | Operational Risk | Risk ID & Measurement
45 | SHUSA.FED.2013.06.04.MRA.09 | [6 empty] | D12287 | Initiate Issue ID and Loss Data Capture | 2015-08-01 | 2017-12-31 | Operational Risk | Risk ID & Measurement
28 | SHUSA.FED.2013.06.04.MRA.10 | Capital Planning Review MRA 10 | Operational Risk Profile and Estimates | Management is required to develop a credible, transparent, and repeatable methodology to estimate the operational losses. This methodology should capture the firm's exposure to idiosyncratic stressful operational risk events that occur during a severe downturn. In addition, management is required to investigate the relationship of operational losses and the economic environment. Management is required to ensure the methodology captures the firm's full operational risk profile, including exposure to legal risk. Finally, the methodology should be fully documented and independently validated. |  |  |  | POTENTIAL GAP | #N/A | #N/A | #N/A | Model Risk Management | Model Validation
28 | SHUSA.FED.2013.06.04.MRA.10 | [6 empty] | D12470 | Implement Operational Risk Loss Forecasting for CCAR and document | 2015-08-01 | 2016-03-31 | Operational Risk | Risk ID & Measurement
28 | SHUSA.FED.2013.06.04.MRA.10 | [6 empty] | D12347 | Roll out Scenario Analysis | 2015-08-01 | 2016-12-31 | Operational Risk | Risk ID & Measurement
29 | SHUSA.FED.2013.06.04.MRA.13 | Capital Planning Review MRA 13 | Consistency of Scenario Risk Drivers | Management is required to ensure that the set of scenario risk drivers used for forecasting the supervisory scenarios are consistent with the risk drivers provided by the Federal Reserve and are internally consistent. The scenarios and the development of additional scenario risk drivers should be independently validated. |  |  |  | D20434 | Policies & procedures for the scenario design and scenario selection process | 2015-09-30 | 2015-09-30 | CCAR | Scenario Generation
29 | SHUSA.FED.2013.06.04.MRA.13 | [6 empty] | D20435 | Scenario Generation Process Enhancements | 2015-12-31 | 2015-12-31 | CCAR | Scenario Generation
30 | SHUSA.FED.2013.06.04.MRA.17 | Capital Planning Review MRA 17 | Forecasting Tools | Management is required to add to its project plan the review of forecasting tools, such as spreadsheets, to ensure they are well designed and that appropriate controls, such as edits checks, are in place. |  |  |  | D19999 | Inventory of spreadsheets & other similar calculation tools used in the CCAR process | 2015-09-28 | 2015-09-28 | CCAR | End-to-end internal controls
30 | SHUSA.FED.2013.06.04.MRA.17 | [6 empty] | D20000 | Change management process to oversee the end-to-end process to identify and document changes and required internal controls | 2015-12-31 | 2015-12-31 | CCAR | Governance
30 | SHUSA.FED.2013.06.04.MRA.17 | [6 empty] | D7436 | Enhance CCAR/DFAST Internal Control framework and methodology | 2015-06-01 | 2016-08-30 | Finance transformation | Internal Controls
31 | SHUSA.FED.2013.06.04.MRA.18 | Capital Planning Review MRA 18 | Definition of Available Capital | Management is required to determine and document in the capital plan a definition of available capital for SHUSA. In addition, management is required to demonstrate the capacity of each component of its chosen definition of available capital beyond common equity to absorb losses during times of stress. |  |  |  | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR | Governance
31 | SHUSA.FED.2013.06.04.MRA.18 | [6 empty] | D8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital management
31 | SHUSA.FED.2013.06.04.MRA.18 | [6 empty] | D9320 | Phased build out of strategic enhancements to the capital planning for 2016 – 2018 (Deliverable 6) | 2016-06-01 | 2018-09-01 | Finance transformation | Capital management
33 | SHUSA.FED.2013.06.04.MRA.20 | Capital Planning Review MRA 20 | Forward-Looking Analysis in BHC Stress Scenario | Management is required to expand the forward-looking analysis in the BHC stress-scenario and idiosyncratic scenarios to rigorously capture and analyze the impact of the stress on the firm and its strategic direction. |  |  |  | D20039 | Centralized oversight and execution of CCAR cycle run process | 2015-08-31 | 2015-08-31 | CCAR | Scenario Generation
33 | SHUSA.FED.2013.06.04.MRA.20 | [6 empty] | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR | End to end process
33 | SHUSA.FED.2013.06.04.MRA.20 | [6 empty] | D20334 | Education sessions for the Board & Sr. Management to improve their ability to more effectively challenge outputs of the CCAR process designed & Rolled out | 2015-12-10 | 2015-12-10 | CCAR | End to end process
33 | SHUSA.FED.2013.06.04.MRA.20 | [6 empty] | D20435 | Scenario Generation Process Enhancements | 2015-12-31 | 2015-12-31 | CCAR | Capital assessment
33 | SHUSA.FED.2013.06.04.MRA.20 | [6 empty] | D20040 | E2E Process Documentation | 2015-12-31 | 2015-12-31 | CCAR | Scenario Generation
33 | SHUSA.FED.2013.06.04.MRA.20 | [6 empty] | D20333 | Updated SHUSA-wide Review & Challenge Framework | 2016-02-15 | 2016-02-15 | CCAR | End to end process
34 | SHUSA.FED.2013.06.04.MRA.21 | Capital Planning Review MRA 21 | Capital Ratio Sensitivity Analysis | Management is required to conduct thorough sensitivity analysis at a granular model level as well as the level of the key inputs to the forecasted capital ratios. This analysis should evaluate the uncertainty around the firm's estimates, including the potential margin of error and the sensitivity of the estimates to changes in inputs and key assumptions. In addition, sensitivity analysis should be conducted in order to understand and analyze the range of possible outcomes associated with the execution of the firm's business strategy and for communication with the board of directors. |  |  |  | d20501 | Approved procedure to measure the uncertainty from Model, Data & Process Weaknesses | 2015-08-03 | 2015-09-30 | CCAR | Capital Assessment
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D20517 | Develop process to ensure approprate analysis and documentation supporting rationale of uncertainty add-ons related to process weaknesses | 2015-06-08 | 2016-01-15 | CCAR | Capital Assessment
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D20542 | Develop repeatable approach to sensitivity analysis that covers end-to-end capital planning process | 2016-01-04 | 2016-06-30 | CCAR | Capital Assessment
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13615 | CRE Risk Rating - Wholesale | 2015-08-17 | 2015-08-17 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13617 | Unsecured Loss Estimation (PD and LGD) | 2015-10-15 | 2015-10-15 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13616 | C&I Risk Rating | 2015-10-30 | 2015-10-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13618 | Auto Lending Loss Estimation (PD and LGD) | 2015-10-30 | 2015-10-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13619 | Auto Lending PPNR (Origination and Pricing) | 2015-10-30 | 2015-10-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13620 | Deposit PPNR (Balance and Pricing) | 2016-02-29 | 2016-02-29 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13622 | CRE PPNR (Origination and Pricing) | 2016-04-29 | 2016-04-29 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13623 | CRE PPNR (Utilization and Prepay) | 2016-06-30 | 2016-06-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13625 | C&I PPNR (Origination, Utilization, Prepay and Pricing) | 2016-07-28 | 2016-07-28 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13626 | OTTI (new vendor) | 2016-07-29 | 2016-07-29 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13627 | Residential RE Loss Estimation (Mortgage and HELOC - PD and LGD) | 2016-09-22 | 2016-09-22 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13628 | Residential RE PPNR (Origination, Utilization and Pricing) | 2016-09-30 | 2016-09-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13629 | Residential RE Loss Estimation (HELOAN - PD and LGD) | 2017-05-30 | 2017-05-30 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13630 | Residential RE PPNR (HELOAN - Origination and Pricing) | 2017-06-06 | 2017-06-06 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13621 | CRE Loss Estimation (PD, LGD and EAD) | 2017-09-29 | 2017-09-29 | Model development
34 | SHUSA.FED.2013.06.04.MRA.21 | [6 empty] | D13624 | C&I Loss Estimation (PD,LGD,EAD) | 2017-09-29 | 2017-09-29 | Model development
35 | SHUSA.FED.2013.06.04.MRA.23 | Capital Planning Review MRA 23 | Firmwide Consistency of Scenarios | Management is required to add to its project plan the development of a process to ensure that scenarios are applied consistently throughout the firm, over time, and across portfolios and that forecasts are internally consistent. The project delivery dates should reflect the complexity of these processes. |  |  |  | D20434 | Policies & procedures for the scenario design and scenario selection process | 2015-09-30 | 2015-09-30 | CCAR | Scenario generation
35 | SHUSA.FED.2013.06.04.MRA.23 | [6 empty] | D20435 | Scenario Generation Process Enhancements | 2015-12-31 | 2015-12-31 | CCAR | Scenario generation
36 | SHUSA.FED.2013.06.04.MRA.26 | Capital Planning Review MRA 26 | Aggregate Capital Impact from Stressful Conditions | Management is required to add to its project plan the formalization of a rigorous process, beyond enterprise-wide scenario analysis, to assess the aggregate impact on capital from stressful conditions. Further, management is required to develop a process to incorporate additional measures of the impact on capital from stressful conditions into the capital adequacy assessment process. The project delivery dates should reflect the complexity of these processes. |  |  |  | PARTIAL GAP (economic capital) | #REF! | #REF! | #REF! | Finance transformation | Capital management
37 | SHUSA.FED.2013.06.04.MRA.27 | Capital Planning Review MRA 27 | RTS Capital Adequacy Monitoring | Management is required to add to its project plan an update of the RTS with additional capital ratios in order to formalize the monitoring of capital adequacy. |  |  |  | Awaiting response George | #REF! | #REF! | #REF! | Finance transformation | Capital management
38 | SHUSA.FED.2013.06.04.MRA.28 | Capital Planning Review MRA 28 | Early Warning Indicators | Management is required to add to its project plan the development of a process to forecast relevant early warning indicators over the planning horizon for the stress scenarios and consider potential responses to the indicators in different stress scenarios. |  |  |  | D8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital management
39 | SHUSA.FED.2013.06.04.MRA.29 | Capital Planning Review MRA 29 | Non-linearities in Forecasting Process | Management is required to evaluate potential non-linearities that may arise in the measurement and forecasting process for the supervisory and BHC scenarios. Where relevant, these effects should be captured within the forward-looking analysis over the planning horizon where possible or accounted for through measures of uncertainty or management overlays. |  |  |  | D20501 | Approved procedure to measure the uncertainty from Model, Data & Process Weaknesses | 2015-08-03 | 2015-09-30 | CCAR | Capital Assessment
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D20517 | Develop process to ensure approprate analysis and documentation supporting rationale of uncertainty add-ons related to process weaknesses | 2015-06-08 | 2016-01-15 | CCAR | Capital Assessment
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D20542 | Develop repeatable approach to sensitivity analysis that covers end-to-end capital planning process | 2016-01-04 | 2016-06-30 | CCAR
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13674 | Unsecured Loss Estimation (PD and LGD) | 2015-06-09 | 2015-10-15 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13724 | Auto Lending PPNR (Origination and Pricing) | 2015-06-15 | 2015-10-30 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13699 | Auto Lending Loss Estimation (PD and LGD) | 2015-06-09 | 2015-10-30 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13753 | Deposit PPNR (Balance and Pricing) | 2015-11-13 | 2016-02-29 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13815 | CRE PPNR (Origination and Pricing) | 2015-12-07 | 2016-04-29 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13840 | CRE PPNR (Utilization and Prepay) | 2015-12-07 | 2016-06-30 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13902 | C&I PPNR (Origination, Utilization, Prepay and Pricing) | 2016-01-04 | 2016-07-28 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13951 | OTTI (new vendor) | 2016-03-01 | 2016-07-29 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13963 | Residential RE Loss Estimation (Mortgage and HELOC - PD and LGD) | 2016-05-16 | 2016-09-22 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D14012 | Residential RE PPNR (Origination, Utilization and Pricing) | 2016-05-16 | 2016-09-30 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D14049 | Residential RE Loss Estimation (HELOAN - PD and LGD) | 2017-01-20 | 2017-05-30 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D14074 | Residential RE PPNR (HELOAN - Origination and Pricing) | 2017-01-20 | 2017-06-06 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13865 | C&I Loss Estimation (PD,LGD,EAD) | 2017-04-06 | 2017-09-29 | Model Development
39 | SHUSA.FED.2013.06.04.MRA.29 | [6 empty] | D13778 | CRE Loss Estimation (PD, LGD and EAD) | 2017-04-06 | 2017-09-29 | Model Development
41 | SHUSA.FED.2013.06.04.MRA.30 | Capital Planning Review MRA 30 | Capital and Liquidity Exposure to Subsidiaries | Management is required to add to its project plan the evaluation of the possibility that capital and liquidity could become trapped at subsidiaries and potential responses. |  |  |  | D1285 | Update and Implement Contingency Funding Plan | 2015-01-05 | 2015-05-29 | ELS
41 | SHUSA.FED.2013.06.04.MRA.30 | [6 empty] | d9195 | Enhanced and strengthened forecast and aggregation process (Deliverable 4) | 2015-05-04 | 2015-12-31 | Finance transformation | Capital Management
41 | SHUSA.FED.2013.06.04.MRA.30 | [6 empty] | d8715 | Integration of MIA-BSI, NY-SIS and PR entities into the SHUSA forecasting process for CCAR 2016 (Deliverable 2) | 2015-07-13 | 2016-03-11 | Finance transformation | Capital Management
41 | SHUSA.FED.2013.06.04.MRA.30 | [6 empty] | d8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital Management
41 | SHUSA.FED.2013.06.04.MRA.30 | [6 empty] | d9320 | Phased build out of strategic enhancements to the capital planning for 2016 – 2018 (Deliverable 6) | 2016-06-01 | 2018-09-01 | Finance transformation | Capital Management
42 | SHUSA.FED.2013.06.04.MRA.34 | Capital Planning Review MRA 34 | Dividend Policy Criteria for Adverse Financial Events | Management is required to update the dividend policy to include more quantitative and qualitative criteria for promptly reconsidering capital distributions in the event of a deteriorating operating environment or economic outlook. At a minimum, consideration should be given to additional triggers such as an adverse financial event that causes a material decline in earnings, significant anticipated balance sheet growth, and deterioration in leading economic indicators that are material to SHUSA's operations. |  |  |  | D8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital management
43 | SHUSA.FED.2013.06.04.MRA.35 | Capital Planning Review MRA 35 | Capital Action Decision Criteria | Management is required to update the capital plan to include specific criteria for making decisions related to all capital actions. |  |  |  | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR
43 | SHUSA.FED.2013.06.04.MRA.35 | [6 empty] | D8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital management
44 | SHUSA.FED.2013.06.04.MRA.37 | Capital Planning Review MRA 37 | Board of Director Engagement in Capital Planning | The board of directors is required to engage in the capital planning process on a periodic basis by receiving ongoing training, evaluating and approving relevant parts of the capital plan throughout the planning process, and ensuring it is well prepared to approve the annual capital plan. The board's meetings, activities, and deliberations related to capital planning should be well documented in relevant materials and meeting minutes. |  |  |  | D20334 | Education sessions for the Board & Sr. Management to improve their ability to more effectively challenge outputs of the CCAR process designed & Rolled out | 2015-12-10 | 2015-12-10 | CCAR | Governance
44 | SHUSA.FED.2013.06.04.MRA.37 | [6 empty] | D20370 | Updated SHUSA-wide Review & Challenge Framework | 2015-06-29 | 2016-02-15 | CCAR | Governance
46 | SHUSA.FED.2014.04.22.MRA.01 | CCAR 2014 MRA 1 | IT Infrastructure / Data Management Systems | The board of directors is required to perform a gap analysis of the firm's IT infrastructure and data management systems that support the end-to-end capital planning process. A project plan should be developed to address any identified gaps within a timeframe that reflects the complexity of the remediation efforts. |  |  |  | D25171 | Execute SCUSA data management Pilot waves 1-3 (Without formal tooling) | 2014-08-29 | 2015-05-25 | Data / IT | Technology and capabilities gap assesment
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D24543 | Execute SBNA data management wave 1 (based on priority) | 2014-03-31 | 2015-08-30 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D20781 | Conduct a comprehensive gap assessment in IT infrastructure and data management systems to cover CCAR and SBNA and SCUSA | 2015-06-01 | 2015-12-31 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D24921 | Execute SBNA data management wave 2 (based on priority) | 2015-05-11 | 2015-12-31 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D20832 | Expand the gap assessment to include additional legal entities and IHC | 2015-10-01 | 2016-06-30 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D21093 | Establish IT architecture practices | 2015-01-01 | 2016-06-30 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D21245 | Design detailed target state IT architecture to deliver CART program | 2015-06-01 | 2016-06-30 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D25138 | Execute SBNA data management wave 3 (based on priority) | 2016-01-01 | 2016-09-30 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D25211 | Execute SCUSA data management wave 1 (With tools) | 2014-10-27 | 2016-12-31 | Data / IT | Technology and capabilities gap assesment
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D24291 | Execute SHUSA data management wave 1 (Priority data domains required for CCAR - ~150+ KDEs) | 2015-06-22 | 2017-03-15 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D25159 | Execute SBNA data management wave 4 (based on priority) | 2016-11-01 | 2017-03-31 | Data / IT | Target-state IT architecture infrastructure and tools
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D24490 | Execute SHUSA data management wave 2 (based on priority) | 2016-08-15 | 2017-08-15 | Data / IT | Effective data governance and data quality program
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D25405 | Expand scope of data management to remaining legal entities (PR, Miami, SIS) | 2016-04-01 | 2017-12-31 | Data / IT | Technology and capabilities gap assesment
46 | SHUSA.FED.2014.04.22.MRA.01 | [6 empty] | D24521 | Execute SHUSA data management wave 3 (based on priority) | 2017-09-30 | 2018-09-30 | Data / IT | Effective data governance and data quality program
47 | SHUSA.FED.2014.04.22.MRA.04 | CCAR 2014 MRA 4 | Capital Policy and Capital Contingency Plan | The board of directors is required to ensure that SHUSA has a comprehensive capital policy that addresses the major components of SHUSA's capital planning processes and links to, and is supported by, other policies; provides details on how the board and senior management manage, monitor, and make decisions regarding all aspects of capital planning; and lays out expectations for the information to be included in SHUSA's capital plan. |  |  |  | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR
47 | SHUSA.FED.2014.04.22.MRA.04 | [6 empty] | D8505 | Capital policies for SHUSA and its subsidiaries revised and implemented (Deliverable 1) | 2015-07-06 | 2016-04-01 | Finance transformation | Capital management
47 | SHUSA.FED.2014.04.22.MRA.04 | [6 empty] | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
48 | SHUSA.FED.2014.04.22.MRA.05 | CCAR 2014 MRA 5 | Aggregation of Projections | The board of directors is required to develop and implement an effective process for aggregating loss, revenue, expense, on- and off-balance sheet estimates, and RWA estimates. The process should ensure the accuracy and coherence of component estimates and aggregate results. Also, it should be subject to strong governance and controls as well as to an independent review by Internal Audit and validation. |  |  |  | D20264 | Standardized organization scheme for documents and quality assurance program (e.g., sign-offs from document owners) to ensure the consistent application of documentation standards | 2015-10-30 | 2015-10-30 | CCAR | Documentation
48 | SHUSA.FED.2014.04.22.MRA.05 | [6 empty] | D20331 | Policies and procedures governing the management self-assessment process | 2015-11-30 | 2015-11-30 | CCAR | Governance
49 | SHUSA.FED.2014.04.22.MRA.06 | CCAR 2014 MRA 6 | Internal Control Framework | The board of directors is required to ensure that an effective internal controls framework is put into place for the end-to-end capital planning process. |  |  |  | d20002 | Inventory of spreadsheets & other similar calculation tools used in the CCAR process | 2015-08-03 | 2015-09-28 | CCAR | End-to-end internal controls
49 | SHUSA.FED.2014.04.22.MRA.06 | [6 empty] | d20018 | Change Management Process to oversee the E2E process to identify and document changes and required internal controls | 2015-09-01 | 2015-12-31 | CCAR | End-to-end internal controls
49 | SHUSA.FED.2014.04.22.MRA.06 | [6 empty] | d7436 | Enhance CCAR/DFAST Internal Control framework and methodology | 2015-06-01 | 2016-08-30 | Finance Transformation | internal Controls
50 | SHUSA.FED.2014.04.22.MRA.07 | CCAR 2014 MRA 7 | Internal Audit Strategy and Plan | The board of directors is required to develop an Internal Audit strategy and plan for 2014 that details audit coverage of the end-to-end capital planning process. The strategy should include capital planning training for Internal Audit staff and the development of detailed Internal Audit scopes and testing plans. |  |  |  | AUDIT | #N/A | #N/A | #N/A |  | Audit
51 | SHUSA.FED.2014.04.22.MRA.08 | CCAR 2014 MRA 8 | RWA Forecasting Framework | The board of directors is required to develop a sound RWA forecasting framework. At a minimum, this should include: 1. A robust process to forecast RWAs that is based on a well-supported methodology consistent with the regulatory risk-weighting approaches associated with different asset and off-balance sheet categories and changes of credit quality. This should include the use of defensible assumptions behind all projections, including those used in the SSFA; 2. Comprehensive documentation of the RWA forecasting process and methodologies; and, 3. Validation and independent review of the RWA forecasting framework, including relevant testing and sensitivity analysis. Review of assumptions and resulting estimates is expected to be completed to ensure the forecasting framework results in appropriate translation of projections of exposures into credible RWA estimates. |  |  |  | D20263 | Documentation standards and templates for each category to ensure consistent inclusion of relevant information defined | 2015-09-15 | 2015-09-15 | CCAR
51 | SHUSA.FED.2014.04.22.MRA.08 | [6 empty] | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR
51 | SHUSA.FED.2014.04.22.MRA.08 | [6 empty] | D20333 | Updated SHUSA-wide Review & Challenge Framework | 2016-02-15 | 2016-02-15 | CCAR
51 | SHUSA.FED.2014.04.22.MRA.08 | [6 empty] | d9282 | Enhancement of RWA Forecasting process for SHUSA and material entities (Deliverable 5) | 2015-07-13 | 2015-12-31 | Finance Transformation | Capital management
52 | SHUSA.FED.2014.04.22.MRIA.01 | CCAR 2014 MRIA 1 | Leadership and Staffing | The board of directors is required to immediately strengthen capital planning leadership and staff. A comprehensive skills and staffing assessment and hiring strategy should be developed for the implementation of an effective capital planning process. The assessment and strategy should address resource needs for the entire organization. |  |  |  | d20045 | Centralized oversight and execution of CCAR cycle run process (i.e. develop the organization that will provide centralized oversight and execution of centralized components of the CCAR cycle run process) | 2015-06-02 | 2015-08-31 | CCAR | End-to-end process
56 | SHUSA.FED.2014.04.22.MRIA.02 | CCAR 2014 MRIA 2 | Governance Structure | The board of directors is required to immediately develop a capital planning governance structure that includes committee, organizational, and policy structures that incorporate all legal entities within the bank holding company. These oversight structures should provide a foundation for effective challenge of the capital planning process. Accountability for capital planning program oversight and management should be clearly and consistently communicated through committee charters, policies and procedures, managerial reporting lines, and individual job descriptions. |  |  |  | D20039 | Centralized oversight and execution of CCAR cycle run process | 2015-08-31 | 2015-08-31 | CCAR
56 | SHUSA.FED.2014.04.22.MRIA.02 | [6 empty] | d20370 | Updated SHUSA-wide Review & Challenge Framework | 2015-06-29 | 2016-02-15 | CCAR
56 | SHUSA.FED.2014.04.22.MRIA.02 | [6 empty] | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
56 | SHUSA.FED.2014.04.22.MRIA.02 | [6 empty] | d11770 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | Risk Transformation | Risk Governance & Org
57 | SHUSA.FED.2014.04.22.MRIA.03 | CCAR 2014 MRIA 3 | Project Planning | The board of directors is required to immediately develop a comprehensive and detailed multi-year project plan to implement an effective capital planning process. This plan should contain a gap analysis against the ROPE paper and action steps to remediate identified gaps and deficiencies, including those already identified by management and those contained in this report. The project plan should be administered by experienced project managers who can oversee project plan milestones and granular tasks as well as interim completion dates. |  |  |  | Covered across whole CART program - please refer to all detailed workplans | Covered across whole CART program - please refer to all detailed workplans | #N/A
58 | SHUSA.FED.2014.04.22.MRIA.04 | CCAR 2014 MRIA 4 | Risk Identification Process | The board of directors is required to develop a risk identification process that aligns with the expectations of the ROPE paper. These processes should evaluate the full set of potential exposures stemming from on- and off-balance sheet positions, including those that could arise from provisions of non-contractual support to off-balance-sheet entities, and risks conditional on changing economic and financial conditions during periods of stress. |  |  |  | D11041 | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 2015-02-02 | 2016-01-15 | Risk Transformation | Risk ID & Measurement
58 | SHUSA.FED.2014.04.22.MRIA.04 | [6 empty] | d11475 | Updated material risk inventory template and guidance for Material Risk Program | 2016-01-18 | 2016-02-26 | Risk Transformation | Risk ID & Measurement
58 | SHUSA.FED.2014.04.22.MRIA.04 | [6 empty] | d11439 | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 2016-01-18 | 2016-05-27 | Risk Transformation | Risk ID & Measurement
59 | SHUSA.FED.2014.04.22.MRIA.05 | CCAR 2014 MRIA 5 | Model Risk Management | The board of directors is required to immediately improve model risk management of capital planning models. At a minimum, the board of directors is required to: 1. Develop a detailed and comprehensive inventory of models used in the capital planning process; 2. Perform rigorous validation of capital planning models within an appropriate timeline and remediate validation findings; 3. Complete comprehensive model documentation and validation reports for all models; and 4. Provide clear communication in the capital plan and reporting to the board on the validation status of all models as well as limitations and related validation findings. |  |  |  | D13112 | Liquidity Risk Framework Validation | 2015-07-14 | 2016-05-27 | Model Risk Management | Model Validation
59 | SHUSA.FED.2014.04.22.MRIA.05 | [6 empty] | D12968 | Address Legacy Model Validation Backlog | 2015-06-19 | 2016-07-15 | Model Risk Management | Model Validation
59 | SHUSA.FED.2014.04.22.MRIA.05 | [6 empty] | D12813 | MILESTONE: Select and implement long-term Model Inventory and Reporting System (MIRS) | 2015-09-15 | 2016-10-28 | Model Risk Management | Model Validation
59 | SHUSA.FED.2014.04.22.MRIA.05 | [6 empty] | D13121 | Implement Periodic Revalidation Process | 2016-01-04 | 2017-03-31 | Model Risk Management | Model Validation
59 | SHUSA.FED.2014.04.22.MRIA.05 | [6 empty] | D13006 | Validate Models | 2015-06-15 | 2017-12-29 | Model Risk Management | Model Validation
60 | SHUSA.FED.2014.04.22.MRIA.06 | CCAR 2014 MRIA 6 | Data Governance and Quality | The board of directors is required to immediately develop a plan to comprehensively identify, define, and remediate data deficiencies in order to measure and monitor risk, conduct capital planning, and complete required regulatory reporting. The plan should also include a data governance and data quality program to oversee data remediation efforts and ensure robust data collection and maintenance practices going forward. |  |  |  | d20631 | Provide controlled data access for modeling and as of data set for CCAR 2016 Forecasting Process | 2015-06-01 | 2015-07-31 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d20568 | Define CCAR Data requirements for CCAR 2016 Forecasting Process | 2015-06-01 | 2015-07-31 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d20603 | Develop Data Glossary for CCAR 2016 Forecasting Process | 2015-07-20 | 2015-09-30 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d20653 | CCAR 14A Data Tagging | 2015-06-22 | 2015-11-02 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d20706 | Generate Data Quality analysis for CCAR 2016 Data Set (Completed Data Dictionary for Prioritized KDE’s) | 2015-06-29 | 2015-12-31 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d20641 | Generate Data reconciliation process and reconcile as of and modeling data sets | 2015-09-01 | 2015-12-31 | CCAR | Data Quality
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D21024 | Identify Governance operating model, guidelines and process requirements for T&O | 2015-06-01 | 2015-07-30 | Data / IT | Data Delivery
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D23943 | Establish data governance routines | 2014-06-13 | 2015-10-31 | Data / IT | Data Delivery
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D23761 | Create Chief Data Office (CDO) organization | 2014-05-05 | 2015-12-31 | Data / IT | Data Delivery
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D24227 | Establish a comprehensive data control framework | 2015-07-01 | 2015-12-31 | Data / IT | Data Delivery
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D25809 | Develop process and reporting for technology incidents, findings and remediation plans | 2015-06-01 | 2016-03-31 | Data / IT | Effective data governance and data quality program
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D21192 | Approve & publish IT governance document in EPAP-compliant format | 2015-04-01 | 2016-04-30 | Data / IT | Data Delivery
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D24240 | Build and automate data controls | 2015-07-01 | 2016-12-31 | Data / IT | Effective data governance and data quality program
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D25510 | Create “data clearinghouse” to drive a repeatable process for gathering functional data requirements | 2015-07-01 | 2017-06-30 | Data / IT | Effective data governance and data quality program
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D25552 | Document data lineage and controls for critical manual processes (e.g., FRY-14A) | 2015-07-15 | 2017-12-31 | Data / IT | Effective data governance and data quality program
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D25828 | Implement SHUSA/SBNA/SCUSA Data Security protection including malware, antivirus, code review and configuration management | 2015-07-31 | 2017-12-31 | Data / IT | Technology and capabilities gap assesment
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | D25927 | Implement SHUSA/SBNA/SCUSA Detection activities – Data loss prevention, security information and event monitoring and threat intelligence | 2015-01-26 | 2017-12-31 | Data / IT | Technology and capabilities gap assesment
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d9332 | Consolidated reporting across SHUSA and subsidiaries (SEC, Regulatory, Tax, & Management); improved processes & controls including reconciliations between sources of historical data & reporting; & increased amount of general ledger information… | 2015-01-15 | 2016-06-30 | Finance Transformation | FT_Accounting & Reporting
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d65 | Complete build out of Asset Liability Management (ALM) data warehouse | 2015-02-02 | 2017-06-30 | Finance transformation
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d65 | Complete build out of Asset Liability Management (ALM) data warehouse | 2015-02-02 | 2017-06-30 | Finance Transformation
60 | SHUSA.FED.2014.04.22.MRIA.06 | [6 empty] | d12287 | Initiate Issue ID and Loss Data Capture | 2015-08-01 | 2017-12-31 | Operational Risk | Risk ID & Measurement
53 | SHUSA.FED.2014.04.22.MRIA.10 | CCAR 2014 MRIA 10 | Pre-Provision Net Revenue (PPNR) | The board of directors is required to immediately implement processes that ensure the capital plan and supporting materials incorporate a complete description of how PPNR projections were determined, why methodologies were chosen, and ensure FR Y-14 regulatory reports are consistent with CCAR instructions. Further, the board is immediately required to develop a centralized and credible review and challenge process that incorporates: 1. An effective internal review and challenge of the quantitative and qualitative processes at both the subsidiary level and the enterprise level; 2. The use of supplemental estimation approaches (including challenger models or benchmarking) to support and challenge projected outcomes; 3. The use of sensitivity analysis or supplemental analytics to enhance the robustness and support for projected outcomes across the enterprise; 4. Policies and procedures that include a clear articulation of accountability for accuracy of results to support the challenge framework at each stage of the process and across entities; 5. Aggregation checks and formal sign-off throughout the process to ensure information entered into regulatory schedules (FR Y-14's) and models is adequate; 6. Strong internal review with meeting minutes that speak directly to key sensitivities and limitations of the process; and 7. The incorporation of effective board challenge that includes a regular review of highlighted limitations and uncertainties of the PPNR projection process. |  |  |  | d20292 | Standardized organization scheme for documents and quality assurance program (e.g., sign-offs from document owners) to ensure the consistent application of documentation standards | 2015-06-29 | 2015-10-30 | CCAR | Documentation
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d20315 | Capital Plan Submission Enhanced | 2015-07-10 | 2015-11-11 | CCAR | Documentation
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d20404 | Education sessions for the Board & Sr. Management to improve their ability to more effectively challenge outputs of the CCAR process designed & Rolled out | 2015-06-01 | 2015-12-10 | CCAR | Governance
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d20071 | E2E Process Documentation | 2015-08-03 | 2015-12-31 | CCAR | End-to-end process
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d20370 | Updated SHUSA-wide Review & Challenge Framework | 2015-06-29 | 2016-02-15 | CCAR | Governance
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d20542 | Develop repeatable approach to sensitivity analysis that covers end-to-end capital planning process | 2016-01-04 | 2016-06-30 | CCAR
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d8047 | Implementation of robust set of assumptions for PPNR models and non-modelled assumptions for CCAR 2016 | 2015-06-01 | 2015-12-31 | Finance transformation | FP&A
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | d7436 | Enhance CCAR/DFAST Internal Control framework and methodology | 2015-06-01 | 2016-08-30 | Finance Transformation | internal Controls
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D13724 | Auto Lending PPNR (Origination and Pricing) | 2015-06-15 | 2015-10-30 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D13753 | Deposit PPNR (Balance and Pricing) | 2015-11-13 | 2016-02-29 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D13815 | CRE PPNR (Origination and Pricing) | 2015-12-07 | 2016-04-29 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D13840 | CRE PPNR (Utilization and Prepay) | 2015-12-07 | 2016-06-30 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D13902 | C&I PPNR (Origination, Utilization, Prepay and Pricing) | 2016-01-04 | 2016-07-28 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D14012 | Residential RE PPNR (Origination, Utilization and Pricing) | 2016-05-16 | 2016-09-30 | Model Development
53 | SHUSA.FED.2014.04.22.MRIA.10 | [6 empty] | D14074 | Residential RE PPNR (HELOAN - Origination and Pricing) | 2017-01-20 | 2017-06-06 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | CCAR 2014 MRIA 11 | Pre-Provision Net Revenue (PPNR) | The board is required to immediately implement a net interest income projection process to meet supervisory expectations of the ROPE paper. At a minimum, the board is required to: 1. Develop and incorporate sufficient cash flow modeling for SCUSA to capture dynamic portfolio characteristics and more granular segmentation; 2. Develop transparent linkage between asset and deposit pricing (yields and spreads) assumptions and scenario conditions. Further, these assumptions should be fully documented, supported, challenged, and subject to validation; and 3. Incorporate nonaccruals directly in the net interest income projection process and ensure consistent treatment of nonaccruals in the loss forecasting and net interest income projection processes. |  |  |  | d20071 | E2E Process Documentation | 2015-08-03 | 2015-12-31 | CCAR | End-to-end process
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D9278 | Develop, document and test customized SAS forecast and aggregation process and tool (detailed milestones in FP&A sub-workstream that is responsible for implementation) (Milestone 2) | 0 | 0 | Finance Transformation | Capital management
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | d8047 | Implementation of robust set of assumptions for PPNR models and non-modelled assumptions for CCAR 2016 | 2015-06-01 | 2015-12-31 | Finance transformation | FP&A
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D13724 | Auto Lending PPNR (Origination and Pricing) | 2015-06-15 | 2015-10-30 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D13753 | Deposit PPNR (Balance and Pricing) | 2015-11-13 | 2016-02-29 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D13815 | CRE PPNR (Origination and Pricing) | 2015-12-07 | 2016-04-29 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D13840 | CRE PPNR (Utilization and Prepay) | 2015-12-07 | 2016-06-30 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D13902 | C&I PPNR (Origination, Utilization, Prepay and Pricing) | 2016-01-04 | 2016-07-28 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D14012 | Residential RE PPNR (Origination, Utilization and Pricing) | 2016-05-16 | 2016-09-30 | Model Development
54 | SHUSA.FED.2014.04.22.MRIA.11 | [6 empty] | D14074 | Residential RE PPNR (HELOAN - Origination and Pricing) | 2017-01-20 | 2017-06-06 | Model Development
55 | SHUSA.FED.2014.04.22.MRIA.12 | CCAR 2014 MRIA 12 | Capital Plan Transparency and Documentation | The board of directors is required to immediately improve documentation of the capital plan and supporting materials. |  |  |  | D20262 | Documentation landscape and inventory of key document categories | 2015-07-31 | 2015-07-31 | CCAR | Documentation
55 | SHUSA.FED.2014.04.22.MRIA.12 | [6 empty] | D20263 | Documentation standards and templates for each category to ensure consistent inclusion of relevant information defined | 2015-09-15 | 2015-09-15 | CCAR | Documentation
55 | SHUSA.FED.2014.04.22.MRIA.12 | [6 empty] | D20264 | Standardized organization scheme for documents and quality assurance program (e.g., sign-offs from document owners) to ensure the consistent application of documentation standards | 2015-10-30 | 2015-10-30 | CCAR | Documentation
55 | SHUSA.FED.2014.04.22.MRIA.12 | [6 empty] | D20265 | Capital Plan Submission Enhanced | 2015-11-11 | 2015-11-11 | CCAR | Documentation
61 | SHUSA.FED.2014.11.21.MRA.01 | LBO Coordinated Liquidity Review MRA 1 | Liquidity Stress Scenarios | Before May 31, 2015, SHUSA's board of directors and senior management are required to develop and implement an effective scenario design process that produces scenarios that appropriately stress SHUSA's liquidity risk profile and capture all cash flows and material risk exposures. |  |  |  | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
61 | SHUSA.FED.2014.11.21.MRA.01 | [6 empty] | d886 | Independent Review of LRM adequacy and effectiveness completed | 2015-09-25 | 2016-05-27 | ELS
62 | SHUSA.FED.2014.11.21.MRA.02 | LBO Coordinated Liquidity Review MRA 2 | Liquidity Stress Testing Time Horizons | Before May 31, 2015, SHUSA's board of directors and senior management are required to ensure liquidity stress testing is conducted over multiple meaningful time horizons. Furthermore, liquidity needs should be assessed over the most stressful periods of the scenarios and incorporated into the day-to-day liquidity risk management. |  |  |  | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
63 | SHUSA.FED.2014.11.21.MRA.03 | LBO Coordinated Liquidity Review MRA 3 | Liquidity Stress Testing Governance | Before May 31, 2015, SHUSA's board of directors and senior management are required to develop and implement comprehensive policies and procedures for liquidity stress testing. |  |  |  | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
64 | SHUSA.FED.2014.11.21.MRA.04 | LBO Coordinated Liquidity Review MRA 4 | Liquidity Stress Testing Governance | Before May 31, 2015, SHUSA's board of directors and senior management are required to develop and implement a comprehensive review and effective challenge process for liquidity stress testing with associated timelines for aspects of the process not yet completed. The process should incorporate the role of the board, senior management, relevant committees, as well as the independent assurance functions. |  |  |  | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
64 | SHUSA.FED.2014.11.21.MRA.04 | [6 empty] | d9160 | Implementation of enhanced reporting to Board and Management Capital Committee to enable effective governance (Deliverable 3) | 2015-05-04 | 2016-01-22 | Finance Transformation | Capital management
65 | SHUSA.FED.2014.11.21.MRA.05 | LBO Coordinated Liquidity Review MRA 5 | Reporting and Use of Liquidity Stress Testing Results | Before May 31, 2015, the board of directors and senior management are required to materially strengthen reporting and use of liquidity stress testing results. At a minimum, the board of directors and senior management are required to: a) Develop granular, transparent, and effective reporting that is clear and actionable. Reporting should include clearly identified liquidity sources, uses, and mitigating actions presented at sufficiently granular time intervals; b) Ensure reporting is used and thoroughly discussed at board and senior management committees on a periodic basis; and c) Incorporate stress testing results into day-to-day liquidity risk management, strategic planning, and risk appetite and limit setting processes. |  |  |  | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
65 | SHUSA.FED.2014.11.21.MRA.05 | [6 empty] | d7974 | FP&A Policy Documentation and Implementation Completed | 2015-06-01 | 2015-10-30 | Finance Transformation | FP&A
66 | SHUSA.FED.2014.11.21.MRA.06 | LBO Coordinated Liquidity Review MRA 6 | Parent Company-Only Stress Testing | Before May 31,2015, the board of directors and senior management are required to improve parent company stress testing. At a minimum, the board of directors and senior management are required to: a) Incorporate subsidiary funding needs into parent company-only funding requirements within the stress tests; b) Exclude access to capital markets within the stress tests; and c) Implement stress liquidity limits and metrics. |  |  |  | d810 | Enterprise Liquidity Risk Management | 2015-06-26 | 2015-11-30 | ELS
66 | SHUSA.FED.2014.11.21.MRA.06 | [6 empty] | d886 | Independent Review of LRM adequacy and effectiveness completed | 2015-09-25 | 2016-05-27 | ELS
67 | SHUSA.FED.2014.11.21.MRIA.01 | LBO Coordinated Liquidity Review MRIA 1 | Consolidated Liquidity Stress Testing | Before January 31, 2015, SHUSA's board of directors and senior management are required to immediately develop a project plan to establish and implement sound liquidity stress testing practices for the consolidated bank holding company. The plan must include a budget, milestones, tasks, and specific timeframes for completion. The plan must be administered by experienced project managers to formally oversee the plan, including appropriate monitoring and reporting of progress and escalation of issues. Any delays in implementation or completion of the plan should be reported to this Reserve Bank. At a minimum, the plan should address and include: a) A liquidity stress testing framework for the consolidated bank holding company; b) Robust methods for comprehensively projecting cash flows arising from assets, liabilities, and off-balance sheet items at a sufficiently granular level and at frequent intervals; and c) A liquidity buffer based on the consolidated stress testing framework and other relevant metrics and limits. |  |  |  | D1518 | Integration with liquidity funding plan | 2015-04-30 | 2015-05-19 | ELS
67 | SHUSA.FED.2014.11.21.MRIA.01 | [6 empty] | d1330 | Identify Liquidity Buffer | 2015-01-05 | 2015-05-20 | ELS
67 | SHUSA.FED.2014.11.21.MRIA.01 | [6 empty] | D1521 | Integration with liquidity limit and risk tolerance setting process | 2015-04-30 | 2015-05-29 | ELS
67 | SHUSA.FED.2014.11.21.MRIA.01 | [6 empty] | d847 | Target Operating Model Implemented | 2015-04-03 | 2016-03-14 | ELS
67 | SHUSA.FED.2014.11.21.MRIA.01 | [6 empty] | d886 | Independent Review of LRM adequacy and effectiveness completed | 2015-09-25 | 2016-05-27 | ELS
68 | SHUSA.FED.2014.11.21.MRIA.02 | LBO Coordinated Liquidity Review MRIA 2 | Contingency Funding Plan | Before February 28, 2015, SHUSA's board of directors and senior management are immediately required to materially strengthen the contingency funding plan. At a minimum, the board of directors and senior management are required to: a) Strengthen the CFP activation process, including a process for notifying and engaging the board; b) Define and document roles and responsibilities for all parties involved with the CFP, including defining membership of the Liquidity Contingency Action Teams; c) Improve contingency actions in the CFP to ensure that they are specific, well defined, and include any necessary approval or process requirements; d) Document a crisis communication plan for both internal and external stakeholders; e) Define and test enhanced liquidity reporting requirements for contingency situations; f) Assess the feasibility and impact of contingency actions for stress scenarios and include processes to refine these estimates based on stress testing results; g) Develop qualitative early warning indicators to supplement quantitative early warning indicators; and h) Develop a plan to integrate liquidity stress testing with the CFP. |  |  |  | D1493 | Preliminary Integration with Contingency Funding Plan | 2015-01-02 | 2015-02-09 | ELS
68 | SHUSA.FED.2014.11.21.MRIA.02 | [6 empty] | D1285 | Update and Implement Contingency Funding Plan | 2015-01-05 | 2015-05-29 | ELS
68 | SHUSA.FED.2014.11.21.MRIA.02 | [6 empty] | D1497 | Final Integration with Contingency Funding Plan | 2015-03-17 | 2015-05-29 | ELS
75 | SHUSA.FED.2015.04.22.MRA.01 | CCAR 2015 MRA 1 | Loss Estimation Methodologies--Retail Credit Risk | Senior management is required to analyze and mitigate limitations imposed by the vendor's application. In particular, SHUSA should better support and document the specification of the maturation curves, taking into account the dispersion of the firm's data. This should include analysis to support that the chosen curve-fitting approach is robust, including comparisons to simpler curve-fitting approaches. SHUSA is also required to perform rigorous, end-to-end back-testing, which reflects the stress testing timeframe by accounting for the compounding of errors at each sequential step. Instead of relying on dummy variables by default, SHUSA is required to research and document noticeable breaks in the dependent variable time series to properly account for internal and external risk factor exposures. Further, the firm is required to explore alternate segmentation methods or demonstrate that the current approach substantively captures the unique sensitivities of each segment to economic variables. Finally, SHUSA is required to confirm that the vendor's method of recursively linking transformations of feeder models' outcomes is sound. |  |  |  | D13699 | Auto Lending Loss Estimation (PD and LGD) | 2015-06-09 | 2015-10-30 | Model Development
75 | SHUSA.FED.2015.04.22.MRA.01 | [6 empty] | D13963 | Residential RE Loss Estimation (Mortgage and HELOC - PD and LGD) | 2016-05-16 | 2016-09-22 | Model Development
75 | SHUSA.FED.2015.04.22.MRA.01 | [6 empty] | D14049 | Residential RE Loss Estimation (HELOAN - PD and LGD) | 2017-01-20 | 2017-05-30 | Model Development
76 | SHUSA.FED.2015.04.22.MRA.02 | CCAR 2015 MRA 2 | Loss Estimation Methodologies--Securities | Senior management is required to ensure the OTTI models meet the expectations for third-party models in the ROPE paper and SR Letter 11-7. At a minimum, this includes working with the vendor to obtain and demonstrate an understanding of: - Necessary model documentation from the vendor that more fully describes the model theory, key assumptions, limitations, and appropriateness of data and usage for the firm's portfolio; - Sufficient information for validation of all components of the model - including but not limited to inputs, processing, outputs and reports - and for comprehensive validation of the model's conceptual soundness (model design, construction, empirical evidence in support of the methods used and variables selected for the model), model implementation, and outcomes analysis; and - Necessary data to allow for a thorough model validation. |  |  |  | D13951 | OTTI (new vendor) | 2016-03-01 | 2016-07-29 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | CCAR 2015 MRA 3 | Pre-Provision Net Revenue (PPNR)--Asset and Liability Balance Projections | Senior management is required to conduct a comprehensive review of balance projection practices for both assets and liabilities and ensure that practices used are well suited to capture all relevant impacts from assumed scenario conditions and meet the expectations of the ROPE paper. This includes ensuring that models are conceptually sound, transparent, well supported by empirical evidence, and generate credible results. Macroeconomic variables used for projections should be consistent with business reasoning and considered relevant to the underlying product. If modeled approaches are used, and they need not be in all cases, outstanding validation concerns should be addressed prior to usage. |  |  |  | d8047 | Implementation of robust set of assumptions for PPNR models and non-modelled assumptions for CCAR 2016 | 2015-06-01 | 2015-12-31 | Finance Transformation
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D13724 | Auto Lending PPNR (Origination and Pricing) | 2015-06-15 | 2015-10-30 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D13753 | Deposit PPNR (Balance and Pricing) | 2015-11-13 | 2016-02-29 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D13815 | CRE PPNR (Origination and Pricing) | 2015-12-07 | 2016-04-29 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D13840 | CRE PPNR (Utilization and Prepay) | 2015-12-07 | 2016-06-30 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D13902 | C&I PPNR (Origination, Utilization, Prepay and Pricing) | 2016-01-04 | 2016-07-28 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D14012 | Residential RE PPNR (Origination, Utilization and Pricing) | 2016-05-16 | 2016-09-30 | Model Development | CCAR Landscape
77 | SHUSA.FED.2015.04.22.MRA.03 | [6 empty] | D14074 | Residential RE PPNR (HELOAN - Origination and Pricing) | 2017-01-20 | 2017-06-06 | Model Development | CCAR Landscape
78 | SHUSA.FED.2015.04.22.MRA.04 | CCAR 2015 MRA 4 | Pre-Provision Net Revenue (PPNR)--Non-Interest Income | Senior management is required to reassess the forecasting methodologies for non-interest income and non-interest expense to ensure they are conceptually sound, use well-supported assumptions and relevant data, and are appropriately sensitive to scenario conditions. These methodologies and assumptions should be transparent, well documented, and conservative in areas where there is a high level of uncertainty. These approaches should meet the expectations of the ROPE paper. Not all items must be modeled and thoughtful consideration of the business drivers of these revenue and expense items and translation into estimates in a more qualitative manner, if well documented and supported, is preferable to reliance on weak or unintuitive models. |  |  |  | D8047 | Implementation of robust set of assumptions for PPNR models and non-modelled assumptions for CCAR 2016 | 2015-06-01 | 2015-12-31 | Finance transformation
78 | SHUSA.FED.2015.04.22.MRA.04 | [6 empty] | D13650 | Identify Roadmap for non-modeled solutions | 2015-05-04 | 2015-08-14 | Model Development
79 | SHUSA.FED.2015.04.22.MRA.05 | CCAR 2015 MRA 5 | BHC Scenario Design and Selection | Senior management is required to develop robust processes for designing and selecting scenarios for enterprise-wide scenario analysis. The scenario-design process should be linked to the risk identification process and produce scenarios that reflect the BHC's unique business activities and associated vulnerabilities. Further, the process should be designed to develop a suite of scenarios that collectively capture the firm's material risks and vulnerabilities under a variety of stressful circumstances. The scenario-selection process should engage a broad range of internal stakeholders such as risk experts, business managers, and senior management. Policies and procedures should be developed to govern the scenario-design and scenario-selection processes, including requiring the use of actual data for the starting values within the scenario. These processes should be subject to review and effective challenge by senior management and the board. |  |  |  | D20434 | Policies & procedures for the scenario design and scenario selection process | 2015-09-30 | 2015-09-30 | CCAR | Scenario generation
79 | SHUSA.FED.2015.04.22.MRA.05 | [6 empty] | D20435 | Scenario Generation Process Enhancements | 2015-12-31 | 2015-12-31 | CCAR | Scenario generation
79 | SHUSA.FED.2015.04.22.MRA.05 | [6 empty] | D20333 | Updated SHUSA-wide Review & Challenge Framework | 2016-02-15 | 2016-02-15 | CCAR | Scenario generation
80 | SHUSA.FED.2015.04.22.MRIA.01 | CCAR 2015 MRIA 1 | Loss Estimation Methodologies--Wholesale Credit Risk | The board of directors and senior management are required to immediately develop a robust wholesale credit risk measurement and loss forecasting framework that meets the expectations of the ROPE paper. At a minimum, this must include: - Most critically, the redevelopment of a wholesale credit risk rating system that is able to adequately rank order default risk and can serve as a fundamental building block of the firm's ratings transition model; - Once a well-calibrated risk rating system is implemented, development of a segmentation scheme that is well supported by the firm's data and analysis with sufficient granularity to capture exposures that react differently to risk drivers under stressed conditions; - Data limitations should be thoroughly analyzed and addressed. In addition, management should consider modeling alternatives to excluding a significant amount of SHUSA's limited recovery data. Further, the use of supplemental external data should be evaluated when the firm's internal data provide insufficient observations for robust model development. If external data are used, documentation and analysis should be developed to demonstrate the quality and relevance of external data to the firm's portfolios; - Selection of risk factors that are well supported by documented statistical evidence, business and economic rationale, as well as model performance test results, including out-of-sample back-testing; - Comprehensive sensitivity analysis to assess the impact of changes in ratings at the beginning of the forecast horizon, and in other key assumptions and risk drivers; and - Enhancement of the EAD methodology to ensure EAD estimates are consistent with the severity of the scenario conditions. Historical analysis should make efficient use of the firm's limited data, and the EAD methodology should be supported by comprehensive documentation and analyses. |  |  |  | d13658 | CRE Risk Rating - Wholesale | 2015-06-29 | 2015-08-17 | Model Development | CCAR Landscape
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d13662 | C&I Risk Rating | 2015-06-22 | 2015-10-30 | Model Development | CCAR Landscape
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d13865 | C&I Loss Estimation (PD,LGD,EAD) | 2017-04-06 | 2017-09-29 | Model Development | CCAR Landscape
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d13621 | CRE Loss Estimation (PD, LGD and EAD) | 2017-09-29 | 2017-09-29 | Model Development | CCAR Landscape
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d10927 | Rollout redesigned C&I rating models | 2015-06-22 | 2016-01-14 | Risk Transformation | Risk Management
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d11007 | Perform high-level review and revision of wholesale credit process limits and controls and delegation of authority at SCUSA and SBNA | 2016-02-01 | 2016-03-31 | Risk Transformation | Risk Management
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d10915 | Rollout redesigned CRE rating models | 2015-06-29 | 2016-05-27 | Risk Transformation | Risk Management
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | D10902 | Rollout Commercial Risk Ratings | 2015-06-01 | 2017-04-15 | Risk Transformation | CCAR Landscape
80 | SHUSA.FED.2015.04.22.MRIA.01 | [6 empty] | d10902 | Rollout Commercial Risk Ratings | 2015-06-01 | 2017-04-15 | Risk Transformation | Risk Management
81 | SHUSA.FED.2015.04.22.MRIA.02 | CCAR 2015 MRIA 2 | Loss Estimation Methodologies--Retail Credit Risk | The board of directors and senior management are required to immediately develop retail loss estimation models that meet the supervisory expectations of the ROPE paper and SR Letter 11-7. At a minimum, this must include: - Segmentation that is well supported by the firm's data and analysis with sufficient granularity to capture exposures that react differently to risk drivers under stressed conditions; - Selection of risk factors that is supported by documented statistical testing and business rationale. The models should also include portfolio risk factors that, where necessary, capture the appropriate loan characteristics; - Data limitations should be thoroughly analyzed and addressed; and - Models should be appropriately sensitive to the stressed scenario conditions and analyzed by thorough sensitivity analysis. |  |  |  | D13617 | Unsecured Loss Estimation (PD and LGD) | 2015-10-15 | 2015-10-15 | Model Development
81 | SHUSA.FED.2015.04.22.MRIA.02 | [6 empty] | D13618 | Auto Lending Loss Estimation (PD and LGD) | 2015-10-30 | 2015-10-30 | Model Development
81 | SHUSA.FED.2015.04.22.MRIA.02 | [6 empty] | D13627 | Residential RE Loss Estimation (Mortgage and HELOC - PD and LGD) | 2016-09-22 | 2016-09-22 | Model Development
81 | SHUSA.FED.2015.04.22.MRIA.02 | [6 empty] | D13629 | Residential RE Loss Estimation (HELOAN - PD and LGD) | 2017-05-30 | 2017-05-30 | Model Development
86 | SHUSA.FED.2015.06.29.MRA.01B | Report of Inspection MRA 1 | Improve policies, procedures, and practices surrounding new business initiatives | By December 31, 2015, SHUSA is required to improve the policies, procedures, and practices surrounding new business initiatives. The policy should clearly define what a new business initiative is, assure new business initiatives are aligned to the corporate strategy, and include a full risk assessment and a formal evaluation of controls and operational readiness as well as have proper sign-offs. The procedure should define the necessary actions and controls to implement the policy in a safe and sound manner, and practices should adhere to the policy and procedure. The board should be provided sufficient time and information to evaluate proposed initiatives prior to approval and to review new initiatives against their goals and objectives post launch. |  |  |  | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
84 | SHUSA.FED.2015.06.29.MRIA.01 | Report of Inspection MRIA 1 | Board and Senior Management Oversight of Consolidated Organization | Within 60 days, SHUSA is required to immediately develop and implement an acceptable plan to materially strengthen board and senior management oversight of the consolidated organization. This plan must include a budget, milestones, tasks, and specific timeframes for completion. The plan must be administered by experienced project managers to formally oversee the plan, including appropriate monitoring and reporting of progress and escalation of issues. The implementation of this plan must begin within 90 days and any delays in implementation should be reported to this Reserve Bank. At a minimum, the plan should address and include: (a) Corporate governance guidelines that formally document and clarify the responsibilities of the board and management. The guidelines should describe the organizational structure and how that structure will be governed through the board and committees thereof and board-appointed management committees. The guidelines should address director composition and leadership requirements of the board members and outline processes surrounding board operations, including the board and CEO evaluation processes; (b) Once the corporate governance structures have been revisited, an assessment and gap analysis of board and management resources needed to implement and maintain appropriate oversight of risk taking and risk management activities, and comply with supervisory expectations for large US-based commercial banking organizations must be conducted. The plan should also detail steps that will be taken to close identified gaps; (c) A consolidated risk appetite statement and limit structure as well as the means of communicating risk appetite decisions and risk levels to the risk management function, business line management, and affected employees; (d) A policy approval framework that ensures that policies related to all material business lines and operations and those required by law and regulations are approved by the board of directors and related procedures and guidelines are approved by governing bodies appointed by the board. The framework should address the timing of approvals on a routine basis and in the event of a material change in business activities or economic and market conditions; and (e) A board reporting framework that outlines the nature, format, and frequency of information the board needs to receive from various committees and members of senior management. Such information is to be timely, meaningful, and adequately portray the condition of the corporation and address the risks impacting the corporation. Regular reporting requirements for committees should be outlined in their charters. |  |  |  | d10731 | Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols | 2015-06-15 | 2015-08-17 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11627 | Test Strategic Plan against SHUSA (top-level), SBNA, and SCUSA RAS | 2015-08-17 | 2015-09-04 | Risk Transformation | Risk Appetite
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d10748 | Define target exec. Mgmt risk reporting landscape and scope of remediation (link to committee structure) | 2015-07-27 | 2015-09-07 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d10759 | Develop and implement Wave 1 of exec. Mgmt. reporting enhancements | 2015-08-31 | 2015-11-09 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d10773 | Develop and implement Wave 2 of exec. Mgmt. reporting enhancements | 2015-10-05 | 2015-12-28 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11497 | Develop SHUSA, SBNA, and SCUSA RAS, and obtain approvals | 2015-06-08 | 2015-12-31 | Risk Transformation | Risk Appetite
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11788 | Enhance top of the house risk policies with clear articulation of roles and responsibilities across the Three Lines of Defense (3 LOD) | 2015-07-13 | 2016-01-08 | Risk Transformation | Risk Governance & Org
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11636 | Initiate embedding of RAS in material SHUSA processes and plan for embedding RAS across the enterprise | 2015-11-02 | 2016-01-12 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11770 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | Risk Transformation | Risk Governance & Org
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d10786 | Develop and implement Wave 3 of exec. Mgmt. reporting enhancements | 2015-12-28 | 2016-04-01 | Risk Transformation | Risk Monitoring / Reporting
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11604 | Design RAS for remaining subsidiaries (NY, Puerto Rico, Miami) and obtain approvals | 2016-02-01 | 2016-06-30 | Risk Transformation | Risk Appetite
84 | SHUSA.FED.2015.06.29.MRIA.01 | [6 empty] | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | Report of Inspection MRIA 2 | Enterprise-wide Risk Management Program | Within 60 days, SHUSA is required to immediately develop an acceptable plan to materially strengthen the consolidated bank holding company's enterprise-wide risk management program. This plan must include a budget, milestones, tasks, and specific timeframes for completion. The plan must be administered by experienced project managers to formally oversee the plan, including appropriate monitoring and reporting of progress and escalation of issues. The implementation of this plan must begin within 90 days and any delays in implementation should be reported to this Reserve Bank. At a minimum, the plan should address and include: (a) An assessment of the effectiveness of the current enterprise-wide risk management program and requirements to strengthen risk management contained in this, and previously-issued, supervisory letters; (b) Development and implementation of meaningful risk management policies and procedures that reflect the consolidated organization's risk profile, risk management practices, limits, and controls. Processes should be in place to ensure policies and procedures are promptly modified in response to significant changes in business activities, conditions, and risk; (c) Comprehensive definition of enterprise-wide risk management roles and responsibilities that address authority and accountability and include clear delineation between risk taking and risk management activities; (d) Strengthening of risk monitoring and management information systems that identify and measure on- and off-balance sheet risks of the consolidated bank holding company. Risk measurement, reporting, and aggregation of risk and exposure data on a consolidated basis must be strengthened, along with related IT systems; and (e) Implementation of incentives that are consistent with risk management objectives and measurement standards. |  |  |  | d11777 | Implement routine Risk-Business reviews with standardized materials and reports | 2015-07-13 | 2015-07-31 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d10731 | Assess current reporting landscape and make quick-win enhancements to priority reports (Board and Level 1 Risk Committees) and reporting protocols | 2015-06-15 | 2015-08-17 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d10748 | Define target exec. Mgmt risk reporting landscape and scope of remediation (link to committee structure) | 2015-07-27 | 2015-09-07 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d10759 | Develop and implement Wave 1 of exec. Mgmt. reporting enhancements | 2015-08-31 | 2015-11-09 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11699 | Draft overarching Governance and Oversight Framework Document for SHUSA; syndicate and finalize | 2015-07-15 | 2015-11-30 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11789 | Assessment and Enhancement to Existing Risk Management Performance Scorecards | 2015-06-15 | 2015-12-18 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d10773 | Develop and implement Wave 2 of exec. Mgmt. reporting enhancements | 2015-10-05 | 2015-12-28 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11041 | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 2015-02-02 | 2016-01-15 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11770 | Conduct gap analysis against the overarching Governance and Oversight Framework document, identify gaps and develop multi-year execution plans | 2015-12-01 | 2016-01-31 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d10786 | Develop and implement Wave 3 of exec. Mgmt. reporting enhancements | 2015-12-28 | 2016-04-01 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11439 | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 2016-01-18 | 2016-05-27 | Risk Transformation | Risk Management
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | D11894 | Rollout systematic performance assessments and compensation structures | 2016-04-01 | 2017-01-02 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11806 | Design Operating Model across Risk types aligned with principles of 3 LOD, develop rollout plans and implement - by risk type / function | 2015-06-22 | 2017-05-02 | Risk Transformation | Risk Governance & Org
85 | SHUSA.FED.2015.06.29.MRIA.02 | [6 empty] | d11457 | Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification | 2016-05-30 | 2017-05-31 | Risk Transformation | Risk Management
END ---------- | END ---------- | END ---------- | END ---------- | END ---------- |  |  |  | END ---------- | END ---------- | END ---------- | END ---------- | END ---------- | END ---------- | END ----------
risk management
Note on J10: Zhang, Zhiyi: Should be Risk Management
Note on J14: Zhang, Zhiyi: Should be Risk Mgmt
Note on J22: Zhang, Zhiyi: belongs to Gov. & Org. not Management
Note on J39: Zhang, Zhiyi: Should be Riks Mgmt
Note on J262: Zhang, Zhiyi: Correct date is 7/29/16 phase II implementation T&O task
Note on J276: Zhang, Zhiyi: Should be RAS
Note on J282: Zhang, Zhiyi: should be Reporting
Note on J283: Zhang, Zhiyi: Should be Reporting
Note on J284: Zhang, Zhiyi: Wave 1, 2, 3 should be Reporting
Note on J286: Zhang, Zhiyi: Wording, "Assess existing Risk Management Performance Scorecards and identify gaps" in Fed slide
Note on J288: Zhang, Zhiyi: Should be Risk ID
Note on J291: Zhang, Zhiyi: Should be Risk ID
Note on J294: Zhang, Zhiyi: Should be Risk ID